## Index (hidden)
CANARA BANK DC MIGRATION – CBS INFRASTRUCTURE MIGRATION RUNBOOK
| Project Name | Canara Bank DC Migration – CBS infrastructure lift & shift
| Event | CNB-DC-MIG – CBS Wave (Batches 1–3)
| Source → Target | ITI → STT
| Migration window | 24/10/2026 – 27/10/2026 (see Wave Dashboard)
| Version | V1.2 – Truck loading re-planned (45 boxes / truck; Batch 1: Director + P10 + tape first, NDC next)
Primary Contact
Secondary Contact
Conference Bridge
Use the hyperlinks below to open each worksheet.
| # | Worksheet / Tab | Description
| 1 | Wave Dashboard | Overall status: batch windows, device counts, task progress (live)
| 2 | Change Log | Runbook revision history
| 3 | HIGH-LEVEL | One line per truck: scope, handover, ITI departure, STT arrival, mounting, power-on
| 4 | Network Runbook | Network device runbook (FTD, Fortigate, Checkpoint, F5, WAN) with pre-migration and movement steps
| 5 | Pre-Event Checklist | Event prerequisites with owner, status and RAG
| 6 | GO-NOGO Checklist | Overall and per-batch GO / NO-GO gates with automatic decision
| 7 | Cutover - Day Activities | Detailed runbook – sections per batch, steps per phase and per truck (live schedule)
| 8 | Scope | All physical and virtual devices in one list with batch, truck and status tracking
| 9 | Shutdown_Startup_Seq | Device-level shutdown sequence and startup order with owners
| 10 | Batch_App_Summary | Application owner groups vs batches (live counts)
| 11 | Truck_Tracker | Planned vs actual departure / arrival, gate pass, e-way bill, seal
| 12 | Truck_Load_Plan | Loading sequence per truck
| 13 | Racks for CBS | Target rack positions at STT (rackmap) with rack movement, batch and truck
| 14 | Rack_Movement_Plan | Disposition of every source rack
| 15 | Target_Rack_Readiness | Target rack-U readiness for loose devices
| 16 | SAN_Fabric_Map | Fabric chains, switch batches, ISL checks and PPT storage endpoints
| 17 | Migration Squad | Team members and roles
| 18 | Roster | Shift roster per batch
| 19 | Stakeholder List | Stakeholders and communication preferences
| 20 | Escalation Detail | Escalation process and contacts
| 21 | Command Centre Comms | Communication framework and live checkpoint schedule
| 22 | Runbook Calls_SS | Runbook walkthrough calls per application group
| 23 | Change Records | Change records per batch
| 24 | Action log | Open actions
| 25 | Issue Log | Issues raised during the event
| 26 | Risk Log | Risks with rating, mitigation and contingency
| 27 | Lessons Learnt | Lessons carried forward from DR migration and Wave 2
| 28 | Assumptions | Basis of plan
The information contained in this document is company confidential.

## Wave Dashboard (hidden)
OVERALL MIGRATION STATUS – CBS INFRASTRUCTURE LIFT & SHIFT (ITI → STT)
| Wave Number | CNB-DC-MIG – CBS Wave
| Planned Cutover Start | 2026-10-24 03:00
| Planned Cutover End | 2026-10-27 21:15
| Source DC | ITI (CBS DC – F21 / NDC GR racks)
| Target DC | STT
| Downtime starts (Batches 2 & 3) | 24/10/2026 – Batch 1 from 03:00; Batches 2 & 3 from 22:00 (servers) → 23:45 (network)
| Hypercare until | 2026-10-29 22:15
Actual Start / End
Overall RAG
| Batch | Theme | Physical Rows | AIX LPARs | Hyper-V VMs | Trucks | Empty Racks | OEM Loaded Racks | Planned Start | Planned End | Tasks | Closed | In Progress | Blocked | % Complete | Trucks Arrived
| 1 | Batch 1 – Pre-agreed (BLR512B-G7-SW2, NDC, CBS tape, P10 frame 78A1DE8 / rack C3) | 40 | 1 | 10 | 5 | 6 | 4 | 2026-10-24 03:00 | 2026-10-26 07:20 | 60 | 0 | 0 | 0 | 0% | 0
| 2 | Batch 2 – Merged SAN batch incl. UAT fabric (BLR128B-G7-SW1/SW2 and connected devices) | 239 | 198 | 155 | 14 | 3 | 20 | 2026-10-24 17:00 | 2026-10-27 21:15 | 155 | 0 | 0 | 0 | 0% | 0
| 3 | Batch 3 – Standalone (no SAN) | 117 | 0 | 0 | 4 | 3 | 0 | 2026-10-24 22:00 | 2026-10-26 11:15 | 38 | 0 | 0 | 0 | 0% | 0
| TOTAL | All batches | 396 | 199 | 165 | 23 | 12 | 24 | 2026-10-24 03:00 | 2026-10-27 21:15 | 253 | 0 | 0 | 0 | 0% | 0
Task status by phase
| Location | Tasks | Open | In Progress | Closed | Blocked | % Complete
| Source | 110 | 110 | 0 | 0 | 0 | 0%
| Transit | 23 | 23 | 0 | 0 | 0 | 0%
| Target | 124 | 124 | 0 | 0 | 0 | 0%
| Source/Target | 2 | 2 | 0 | 0 | 0 | 0%
Activities Completed:
Next Activities:
Issues:
Charts
Formulas:
Planned Start = MIN(J15:[Planned Start, row above])
Planned End = MAX(K15:[Planned End, row above])

## Change Log (hidden)
Runbook ChangeLog
Manual changes made to this document by revision.
Item # | App or Tab | Change Description | Change by | Date | Comments
1 | Whole Workbook | Initial version of CBS runbook: batches, trucks and timings from inventory_Batch_Plan_v3.xlsx; structure from CNB_DC_MIG_Bubble_Runbook_v2.2 (Cutover, HIGH-LEVEL, Pre-Event, GO-NOGO, Scope) and CNB-CBS-MIG-Runbook V1.0 (Index, Wave Dashboard, Startup&Shutdown, Connected App list, Calls, Change Records, Stakeholders, Escalation, Issue Log). | Hareesh | 2026-10-17 | Draft for review
2 | Scope, Cutover, HIGH-LEVEL, trucks, racks | V1.1: Rack C3 (P10 frame 78A1DE8) → Batch 1; UAT switches 787413W/787414D + connected devices (C2, D1, D2, D3, K6/L5 FS9100, K6 ToR, UAT LPARs) → Batch 2; Transport Mode per Scope V2 (IBM racks loaded); Racks for CBS from rackmap.xlsx; new Hyper-V VM DCHRMAPP1 completed; trucks, load plan, rack plan, target readiness, shutdown sequence, dashboard rebuilt; customer cutover dates/times retained. | Hareesh | 2026-10-19 | For review
3 | Trucks, Cutover, HIGH-LEVEL, Truck sheets | V1.2: Truck loading re-planned – 45 boxes per truck (1 box = 1×2U or 2×1U). Batch 1 order: SAN Director + P10 frame + tape library first, NDC devices in the next consecutive trucks. Trucks: Batch 1 5, Batch 2 14, Batch 3 4 (total 23). Cutover truck steps, Task IDs, Scope truck/time, Truck_Load_Plan, Truck_Tracker, HIGH-LEVEL and rack sheets regenerated; all customer dates/times and manual edits retained. | Hareesh | 2026-10-21 | For review

## HIGH-LEVEL (hidden)
CANARA BANK DC MIGRATION ¦ CBS HIGH-LEVEL MOVEMENT PLAN (ITI → STT)
|  |  |  | Unmounted Device | 249 | 249 loose device rows unracked and packed in boxes (1 box = 1×2U or 2×1U) – Batch 1: 29, Batch 2: 103, Batch 3: 117
|  |  |  | Empty Rack | 12 | Empty (Lift & Shift per rackmap) - C1, X5, GR-A3, GR-A4, GR-A2, GR-A1, D5, W3, W4, W5, W6, A4
|  |  |  | Loaded Racks | 24 | Loaded (IBM/OEM) - A1, A2, A5, A6, C2, C3, C4, C5, C6, D1, D3, D6, K3, K2, K1, K4, K6, L1, L2, L3, L5, D2, F7, K5
Source ITI → Target STT (travel 2 h)
| Batch | Truck No | Truck Ft | Scope | Start of Activity | Handover to RI | Start Time _ITI | Reach Time _STT | Unpack/ Mounting | PowerOn/ Troubleshoot | Devices | Racks | Source Rack | Target Rack | Remarks
| 1 | TR-1 |  | Empty racks + OEM loaded racks + SAN director/switch, storage/backup/tape | 2026-10-24 03:00 | 2026-10-24 06:00 | 2026-10-24 12:30 | 2026-10-24 14:30 | 2026-10-24 15:45 | 2026-10-24 22:20 | 3 | 2 | C3, D5 ¦ loose from: A4, D5 | D-04, F-01, H-14 | 1 OEM loaded rack(s) (8 device rows inside); 1 empty rack(s); 1 SAN director/switch, 2 storage/backup/tape in 11 box(es); 44.75/45 boxes
| 1 | TR-1.1 |  | OEM loaded racks + storage/backup/tape | 2026-10-24 03:00 | 2026-10-24 06:00 | 2026-10-24 13:00 | 2026-10-24 15:00 | 2026-10-24 16:15 | 2026-10-24 22:20 | 1 | 1 | L1 ¦ loose from: D5 | C-01, D-04 | 1 OEM loaded rack(s) (1 device rows inside); 1 storage/backup/tape in 2 box(es); 24.5/45 boxes
| 1 | TR-1.2 |  | OEM loaded racks | 2026-10-24 03:00 | 2026-10-24 06:00 | 2026-10-24 13:30 | 2026-10-24 15:30 | 2026-10-24 15:45 | 2026-10-24 22:20 | 0 | 2 | L2, L3 | C-02, C-03 | 2 OEM loaded rack(s) (2 device rows inside); 45/45 boxes
| 1 | TR-1.3 |  | Empty racks | 2026-10-24 03:00 | 2026-10-24 06:00 | 2026-10-24 14:00 | 2026-10-24 16:00 | 2026-10-24 16:15 | 2026-10-24 22:20 | 0 | 4 | GR-A1, GR-A2, GR-A3, GR-A4 | N-01, N-02, N-03, N-04 | 4 empty rack(s); 45/45 boxes
| 1 | TR-1.4 |  | NDC: Empty racks + SAN director/switch, network/security, server, storage/backup/tape | 2026-10-24 03:00 | 2026-10-24 06:00 | 2026-10-24 14:30 | 2026-10-24 16:30 | 2026-10-24 17:45 | 2026-10-24 22:20 | 25 | 1 | A4 ¦ loose from: GR-A1, GR-A2, GR-A3, GR-A4 | F-15, H-10, H-11, L-10, L-11, N-01, N-02, N-03, N-04 | 1 empty rack(s); 2 SAN director/switch, 6 storage/backup/tape, 6 server, 11 network/security in 22 box(es); 33.25/45 boxes
| 2 | TR-2 |  | Empty racks + SAN director/switch, storage/backup/tape | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 06:00 | 2026-10-25 08:00 | 2026-10-25 12:15 | 2026-10-25 23:45 | 6 | 3 | C1, W6, X5 ¦ loose from: A3, B2, D3, F5 | C-08, D-06, D-09, E-16, H-06, J-07 | 3 empty rack(s); 2 SAN director/switch, 4 storage/backup/tape in 11 box(es); 44.75/45 boxes
| 2 | TR-2.1 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 06:30 | 2026-10-25 08:30 | 2026-10-25 08:45 | 2026-10-25 23:45 | 0 | 2 | A1, A2 | G-13, G-14 | 2 OEM loaded rack(s) (18 device rows inside); 45/45 boxes
| 2 | TR-2.2 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 07:00 | 2026-10-25 09:00 | 2026-10-25 09:15 | 2026-10-25 23:45 | 0 | 2 | A5, A6 | C-12, D-13 | 2 OEM loaded rack(s) (13 device rows inside); 45/45 boxes
| 2 | TR-2.3 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 07:30 | 2026-10-25 09:30 | 2026-10-25 09:45 | 2026-10-25 23:45 | 0 | 2 | C2, C4 | G-15, H-13 | 2 OEM loaded rack(s) (18 device rows inside); 45/45 boxes
| 2 | TR-2.4 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 08:00 | 2026-10-25 10:00 | 2026-10-25 10:15 | 2026-10-25 23:45 | 0 | 2 | C5, C6 | G-17, H-17 | 2 OEM loaded rack(s) (19 device rows inside); 45/45 boxes
| 2 | TR-2.5 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 08:30 | 2026-10-25 10:30 | 2026-10-25 10:45 | 2026-10-25 23:45 | 0 | 2 | D1, D2 | C-11, H-15 | 2 OEM loaded rack(s) (15 device rows inside); 45/45 boxes
| 2 | TR-2.6 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 09:00 | 2026-10-25 11:00 | 2026-10-25 11:15 | 2026-10-25 23:45 | 0 | 2 | D3, D6 | C-07, D-09 | 2 OEM loaded rack(s) (10 device rows inside); 45/45 boxes
| 2 | TR-2.7 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 09:30 | 2026-10-25 11:30 | 2026-10-25 11:45 | 2026-10-25 23:45 | 0 | 2 | F7, K1 | F-15, H-09 | 2 OEM loaded rack(s) (8 device rows inside); 45/45 boxes
| 2 | TR-2.8 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 10:00 | 2026-10-25 12:00 | 2026-10-25 12:15 | 2026-10-25 23:45 | 0 | 2 | K2, K3 | G-09, H-08 | 2 OEM loaded rack(s) (14 device rows inside); 45/45 boxes
| 2 | TR-2.9 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 10:30 | 2026-10-25 12:30 | 2026-10-25 12:45 | 2026-10-25 23:45 | 0 | 2 | K4, K5 | G-08 | 2 OEM loaded rack(s) (12 device rows inside); 45/45 boxes
| 2 | TR-2.10 |  | OEM loaded racks | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 11:00 | 2026-10-25 13:00 | 2026-10-25 13:15 | 2026-10-25 23:45 | 0 | 2 | K6, L5 | G-20, H-19 | 2 OEM loaded rack(s) (9 device rows inside); 45/45 boxes
| 2 | TR-2.11 |  | SAN director/switch, storage/backup/tape | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 11:30 | 2026-10-25 13:30 | 2026-10-25 14:15 | 2026-10-25 23:45 | 22 | 0 | loose from: B2, F3, F5, F6, G7, K6, K7, L5, L6, S6 | C-05, C-08, D-06, E-01, E-02, F-16, G-20, H-19 | 3 SAN director/switch, 19 storage/backup/tape in 45 box(es); 45/45 boxes
| 2 | TR-2.12 |  | server, storage/backup/tape | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 12:00 | 2026-10-25 14:00 | 2026-10-25 14:15 | 2026-10-25 23:45 | 39 | 0 | loose from: E2, E3, F2, F3, F4, F5, F6, J2, M1, M5, S6, W6 | A-10, B-10, C-05, C-14, D-06, D-14, H-01, H-02, H-06, I-06, J-07, L-01, L-02 | 10 storage/backup/tape, 29 server in 45 box(es); 45/45 boxes
| 2 | TR-2.13 |  | network/security, server | 2026-10-24 17:00 | 2026-10-25 00:30 | 2026-10-25 12:30 | 2026-10-25 14:30 | 2026-10-25 14:45 | 2026-10-25 23:45 | 36 | 0 | loose from: B2, C1, K6, M1, M5, M7, N5, O5, P1, X2 | A-10, B-10, D-10, E-05, F-03, G-11, I-08, I-10, J-05, J-07, J-08, L-01, L-11, Scrap | 32 server, 4 network/security in 32 box(es); 32/45 boxes
| 3 | TR-3 |  | Empty racks + server, storage/backup/tape | 2026-10-24 22:00 | 2026-10-25 09:30 | 2026-10-25 11:30 | 2026-10-25 13:30 | 2026-10-25 14:45 | 2026-10-25 20:15 | 12 | 3 | W3, W4, W5 ¦ loose from: M4, V3, W3, W4 | D-14, G-03, G-04, G-05, NA | 3 empty rack(s); 11 storage/backup/tape, 1 server in 11 box(es); 44.75/45 boxes
| 3 | TR-3.1 |  | network/security, server, storage/backup/tape | 2026-10-24 22:00 | 2026-10-25 09:30 | 2026-10-25 12:00 | 2026-10-25 14:00 | 2026-10-25 14:45 | 2026-10-25 20:15 | 37 | 0 | loose from: G3, G6, H2, H3, H4, N1, W4, W5, W7 | D-10, E-07, E-08, F-07, F-08, F-09, G-03, G-04, H-05, I-06, K-08, OOS, Scrap | 21 storage/backup/tape, 4 server, 12 network/security in 45 box(es); 45/45 boxes
| 3 | TR-3.2 |  | network/security | 2026-10-24 22:00 | 2026-10-25 09:30 | 2026-10-25 12:30 | 2026-10-25 14:30 | 2026-10-25 14:45 | 2026-10-25 20:15 | 27 | 0 | loose from: H4, I1, I2, I3, J6, N3 | E-06, E-07, E-08, E-09, E-11, F-05, F-07, F-09, F-11, F-12, TBD | 27 network/security in 45 box(es); 45/45 boxes
| 3 | TR-3.3 |  | network/security | 2026-10-24 22:00 | 2026-10-25 09:30 | 2026-10-25 13:00 | 2026-10-25 15:00 | 2026-10-25 15:15 | 2026-10-25 20:15 | 41 | 0 | loose from: N4, O1, O6, W3, W4, W5, W7 | E-11, E-12, F-11, G-03, G-04, G-05, H-05, H-06, H-10, H-11, N/W | 41 network/security in 27 box(es); 27/45 boxes
| Total | [9 empty] | 249 | 36

## Network Runbook
|  | Customer Approval on Network Activity Start Date | 2026-10-21 13:00
46316.5417
SR. NO | Task Activity | Activity | Target Date | Time Duration in Min | Plan Start Time | Plan End Time | Owner | Status | Dependancy/Remark
1 | Pre-migrations | Raise the case with Cisco in advance for failover testing & and physical migration and ensure the availability of OEM standby support during the migration. | 2026-10-15 |  |  |  |  | Completed | Standby chassis for migration purpose
1 | Pre-migrations Core FTD Firewall readiness | Raise the CR Ticket for movement of the FTD migrations | 2026-10-20 |  |  |  | BAU & Project Team | Completed
2 | Pre-migrations Core FTD Firewall readiness | Make sure Firewalls in Sync & Take the backup of FW and keep it with local machine and Laptop | 2026-10-21 13:00 | 30 | 46316.5625 |  | BAU & Project Team | In Progress
3 | Pre-migrations Core FTD Firewall readiness | Failover testing of the Primary FW. i. Physically shut the Primary FW and check that the other active/standby FW will be catering to all traffic as per the expectations. | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
4 | Pre-migrations Core FTD Firewall readiness | Note down any challenges during failover | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
1 | Pre-migrations Core Fortigate Firewall readiness | Raise the CR Ticket for movement of the core Fortigate migrations | 2026-10-21 13:00 |  |  |  | BAU & Project Team | Completed
2 | Pre-migrations Core Fortigate Firewall readiness | Make sure Firewalls in Sync & Take the backup of FW and keep it with local machine and Laptop | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
3 | Pre-migrations Core Fortigate Firewall readiness | Failover testing of the Primary FW. i. Physically shut the Primary FW and check that the other active/standby FW will be catering to all traffic as per the expectations. | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
4 | Pre-migrations Core Fortigate Firewall readiness | Note down any challenges during failover | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
1 | Pre-migrations Internet Checkpoint Firewall readiness | Raise the CR Ticket for movement of the Internet checkpint migrations | 2026-10-21 13:00 |  |  |  | BAU & Project Team | Completed
2 | Pre-migrations Internet Checkpoint Firewall readiness | Make sure Firewalls in Sync & Take the backup of FW and keep it with local machine and Laptop | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
3 | Pre-migrations Internet Checkpoint Firewall readiness | Failover testing of the Primary FW. i. Physically shut the Primary FW and check that the other active/standby FW will be catering to all traffic as per the expectations. | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
4 | Pre-migrations Internet Checkpoint Firewall readiness | Note down any challenges during failover | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
1 | Pre-migrations ipv6 to ipv4 Fortigate Firewall readiness | Raise the CR Ticket for movement of the ipv6 to ipv4 Fortigate migrations | 2026-10-20 |  |  |  | BAU & Project Team | Completed
2 | Pre-migrations ipv6 to ipv4 Fortigate Firewall readiness | Make sure Firewalls in Sync & Take the backup of FW and keep it with local machine and Laptop | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
3 | Pre-migrations ipv6 to ipv4 Fortigate Firewall readiness | Failover testing of the Primary FW. i. Physically shut the Primary FW and check that the other active/standby FW will be catering to all traffic as per the expectations. | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
4 | Pre-migrations ipv6 to ipv4 Fortigate Firewall readiness | Note down any challenges during failover | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
1 | Pre-migrations Internal F5 load balancer readiness | Raise the CR Ticket for movement of the Internal - F5 load balancer migrations | 2026-10-20 |  |  |  | BAU & Project Team | Completed
2 | Pre-migrations Internal F5 load balancer readiness | Make sure LBs in Sync & Take the backup of LB and keep it with local machine and Laptop | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
3 | Pre-migrations Internal F5 load balancer readiness | Failover testing of the Primary LB. i. Physically shut the Primary LB and check that the other active/standby LB will be catering to all traffic as per the expectations. | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
4 | Pre-migrations Internal F5 load balancer readiness | Note down any challenges during failover | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
1 | Pre-migrations DMZ- F5-BIG-LTM-I11800 load balancer readiness | Raise the CR Ticket for movement of the DMZ F5 load balancer migrations | 2026-10-20 |  |  |  | BAU & Project Team | Completed
2 | Pre-migrations DMZ- F5-BIG-LTM-I11800 load balancer readiness | Make sure LBs in Sync & Take the backup of LB and keep it with local machine and Laptop | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
3 | Pre-migrations DMZ- F5-BIG-LTM-I11800 load balancer readiness | Failover testing of the Primary LB. i. Physically shut the Primary LB and check that the other active/standby LB will be catering to all traffic as per the expectations. | 2026-10-21 13:00 |  |  |  | BAU & Project Team | In Progress
4 | Pre-migrations DMZ- F5-BIG-LTM-I11800 load balancer readiness | Note down any challenges during failover | 2026-10-21 13:00 | 2026-10-21 17:48 |  |  | BAU & Project Team | In Progress
1 | Pre-migrations L2 Readiness | STT Wan Switch L2 and STT Wan switch L3 trunk Port-channel connectivity | 2026-10-21 13:00 | 30 |  |  | BAU & Project Team | Completed | checkpoint need to in standby
2 | Pre-migrations L2 Readiness | Configure STT L3 WAN switch Vlans in STT L2 WAN switch | 2026-10-22 |  |  |  | BAU & Project Team | Completed
3 | Pre-migrations L2 Readiness | STT Wan Switch L2 and STT Wan switch L2 trunk Port-channel connectivity over ISP links | 2026-10-22 | 20 |  |  | BAU & Project Team | Completed | Link availibility
4 | Pre-migrations L2 Readiness | STT Wan Switch L2 and STT Wan switch L3 trunk Port-channel connectivity | 2026-10-22 | 30 |  |  | BAU & Project Team | Completed
5 | Pre-migrations L2 Readiness | Configure STT L3 WAN switch Vlans in STT L2 WAN switch | 2026-10-22 |  |  |  | BAU & Project Team | Completed
1 | Pre-migrations WAN router R2 & Temp replication traffic Readiness for Bubble Storage readiness | Configure Router WAN R2 (Temp) in STT DC except BGP,OSPF | 2026-10-20 | 40 |  |  | BAU & Project Team | Completed
2 | Pre-migrations WAN router R2 & Temp replication traffic Readiness for Bubble Storage readiness | Configure All require ports for R2 on L2 WAN switch and L3 WAN switch | 2026-10-20 | 20 |  |  | BAU & Project Team | Completed
4 | Pre-migrations WAN router R2 & Temp replication traffic Readiness for Bubble Storage readiness | Configure Replication link on Juniper L3 switch | 2026-10-20 | 5 |  |  | BAU & Project Team | Completed
5 | Pre-migrations WAN router R2 & Temp replication traffic Readiness for Bubble Storage readiness | Connect Juniper L2 and Juniper L3 switch with L2 connectivity. | 2026-10-20 | 5 |  |  | BAU & Project Team | Completed
7 | Pre-migrations WAN router R2 & Temp replication traffic Readiness for Bubble Storage readiness | Connect Mpls secondary links Jio and Airtel Links on STT ASR router | 2026-10-21 13:00 | 5 |  |  | BAU & Project Team | In Progress | The link build-up is ready.Port showing up. | S# | HighLevel Network Plan
8 | Pre-migrations WAN router R2 & Temp replication traffic Readiness for Bubble Storage readiness | Establish BGP for Links and check the received routes ( Do not Advertise any routes) | 2026-10-21 13:00 | 5 |  |  | BAU & Project Team | In Progress |  | 1 | #REF!
1 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure Core FTD firewall WAN side port on WAN switch in STT | 2026-10-22 | 10 |  |  |  | Completed |  | 3 | #REF!
2 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure Core Fortigate firewall WAN side port on WAN switch in STT | 2026-10-22 | 10 |  |  |  | Completed |  | 4 | #REF!
3 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure Core Fortigate firewall LAN side port on TEMP Core switch L3 in STT | 2026-10-22 | 10 |  |  |  | Completed |  | 5 | #REF!
4 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure Internet checkpoint firewall Inside side port on Aggrigation switch in STT | 2026-10-22 | 10 |  |  |  | Completed |  | 6 | #REF!
5 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure Internet checkpoint firewall LAN side port on DMZ switch in STT | 2026-10-22 | 10 |  |  |  | Completed |  | 7 | #REF!
6 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure F5 LB port on switch in STT | 2026-10-22 | 10 |  |  |  | Completed |  | 8 | #REF!
7 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure Internal - F5-BIG-IP I5800 LB port on switch in STT | 2026-10-22 | 10 |  |  |  | Completed |  | 9 | #REF!
8 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure DMZ F5-BIG-LTM-I11800 LB port on switch in STT | 2026-10-22 | 10 |  |  |  | Completed
9 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure ASR1006-X DC-N10-GM-2 VPN router Inside side port on WAN switch L3 in STT. | 2026-10-22 | 10 |  |  |  | Completed
10 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure ASR1006-X DC-N10-GM-2 VPN router Outside side port on WAN switch L2 in STT. | 2026-10-22 | 10 |  |  |  | Completed
11 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure ASR 1002-X DC-N10-KS-2 router Outside side port on WAN switch L2 in STT. | 2026-10-22 | 10 |  |  |  | Completed
12 | On 22nd Oct 2026 - Pre-migrations activities for secodary device Movement- Offline Config | Configure ASR 1002-X DC-N10-KS-1 router Outside side port on WAN switch L2 in STT. | 2026-10-22 | 10 |  |  |  | Completed
1 | On 22nd Oct 2026 (Thursday Movement) :- Pre-migrations activities for secodary device Movement | Big IP logs entry for secondary DCDMZADC02- F5-BIG-LTM-I11800 need to be removed from BIG IQ | 2026-10-22 | 30 |  |  |  | In Progress
2 | On 22nd Oct 2026 (Thursday Movement) :- Pre-migrations activities for secodary device Movement | Ping and trace need to be enabled other than internet facing firewall | 2026-10-22 | 15 |  |  |  | In Progress
3 | On 22nd Oct 2026 (Thursday Movement) :- Pre-migrations activities for secodary device Movement | Take Arp and Mac table on firewalls and Firewall connecting switches before this activity | 2026-10-22 | 45 |  |  |  | In Progress
A | On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | FMC Movement | [5 empty] | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | latest Backup of the devices | 2026-10-23 | 120 | 46316.5417 | 46316.625 |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Power shutdown | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | colling time | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | BAU team will confirm on status, | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Royal will dismental the same and packing | 2026-10-23 |  |  |  |  | In Progress
B | On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Core Switch Secondary | [5 empty] | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | latest Backup of the devices | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Power shutdown | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | colling time | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | BAU team will confirm on traffic failover on Primary Core Switch | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Royal will dismental the same and packing | 2026-10-23 |  |  |  |  | In Progress
C | On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Fortinet Core Firewall Standby shutdown activity | [5 empty] | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | latest Backup of the devices | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Power shutdown | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | colling time | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | BAU team will confirm on traffic failover on standby fortinet, then we will dismental the same and packing | 2026-10-23 |  |  |  |  | In Progress
D | On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | FTD-CHASSIS-2 | [5 empty] | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | latest Backup of the devices | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | BAU team will Confirm traffic pattern | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Shutdown both Service modules in chassis 2 | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Check if the service modules showing down | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Shutdown Chassis 2 | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | colling time | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | BAU team will Confirm traffic pattern | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | we will dismental the same and packing | 2026-10-23 |  |  |  |  | In Progress
| On 22nd Oct 2026 :- Secondary Device Shutdown activity - FMC, Fortinet, Core Switch and FTD | Loadding , gatepass,movement throuhh Small truck separately | 2026-10-23 | 240 | 46316.625 | 46316.7917 |  | In Progress
0 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT ( 19:00) | Device Rack and Stack in the Rack | 2026-10-24 | 300 | 46316.7917 | 46317 |  | In Progress
1 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT ( 19:00) | Power On All the devices except FTD Chassis 2 | 2026-10-24 |  |  |  |  | In Progress
2 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT ( 19:00) | Connect All the Network Cables to Firewalls but ports should be in a shutdown state from Switch end | 2026-10-24 |  |  |  |  | In Progress
3 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT ( 19:00) | Power On FTD Chassis 2 | 2026-10-24 |  |  |  |  | In Progress
4 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT ( 19:00) | Connect All the Network Cables to FTD Chassis 2 with HA cables but ports should be in shutdown state from Switch end | 2026-10-24 |  |  |  |  | In Progress
5 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT ( 19:00) | Make secondary core switch up and STT DC, connect the switch with temporary Core switch. | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026 :- Pre-migrations activities for Primary device Movement | Take Arp and Mac table for all devices at ITI DC before this activity | 2026-10-24 | 60 | 46317 | 46317.0417 |  | In Progress
A | On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Core FTD activity | 2026-10-24 | 90 | 1:00 | 2:30 |  | In Progress
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Remove the cable from FTD Chassis-1 and Unshut all ports Switch end including managemnt & Cluster ports of FTD Chassis 2 | 2026-10-24 |  |  |  |  | In Progress
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Power on Service modules , check staus of SM | 2026-10-24 |  |  |  |  | In Progress
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Make one of the SM as master | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Check status of Cluster | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | In FTD chassis 1 shutdown both SM , Remove cables and shutdown chassis | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Check next hop reachability | 2026-10-24 |  |  |  |  | In Progress
B | On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | MPLS Router activity | 2026-10-24 |  |  |  |  | In Progress
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Shutdown router R1 at ITI | 2026-10-24 |  |  |  |  | In Progress
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Shutdown MPLS links at STT on R2 ( But replication links should be active) | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Publish MPLS network at bgp connected to STT on MPLS links | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Swap the Ip adDCess 172.25.215.135 and 172.25.215.150 between routers | 2026-10-24 |  |  |  |  | In Progress | Downtime
C | On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Fortinet Firewall Standby start activity | 2026-10-24 |  |  |  |  | In Progress
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Power shutdown Active device CORE FW - Fortinet | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Wait for 5 Min | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Unshut the cables connected ports from switches to the Core Fw Forti-Fw01 Stabdby Device | 2026-10-24 |  |  |  |  | In Progress | Downtime
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Check health status | 2026-10-24 |  |  |  |  | In Progress
| On 23-Oct-26 :- Primary Device Shutdown activity for FTD, Fortinet firewall. | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
|  | Observations | 2026-10-24 | 30 | 2:30 | 3:00
A | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Internal LB shutdown activity | 2026-10-24 | 360 | 3:00 | 9:00 |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby load balancer, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
B | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | DMZ NTB Device shutdown activity | 2026-10-24 |  |  |  |  | In Progress | SOC Team to perform
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby load balancer, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
C | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | DMZ- F5-BIG-LTM-I11800 load balancer shutdown activity | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby load balancer, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
D | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | ASR1006-X DC-N10-GM-2 VPN router shutdown activity | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby load balancer, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
E | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | ASR 1002-X DC-N10-KS-2 and SDWAN Device | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby load balancer, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
F | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | ASR 1002-X DC-N10-KS-1 | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby load balancer, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
G | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | DMZ, Cloud, Proxy Standby FW - Check Point standby FW load balancer shutdown activity | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby checkpoint, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
H | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | DMZ-IPv6 to IPv4 convertor Standby | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby checkpoint, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
I | On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | DMZ-DDOS ARBOR Standby -1Gig bypass Ddos | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | latest Backup of the devices | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | Power shutdown | 2026-10-24 |  |  |  |  | In Progress
| On 23 Oct 2026:- Secondary Device Shutdown activity - Morning Hours | BAU team will confirm on traffic failover on standby checkpoint, then we will dismental the same and packing | 2026-10-24 |  |  |  |  | In Progress
|  | Device packing, loading and trasit to STT | 2026-10-24 | 120 | 9:00 | 11:00
1 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT | Power On All the devices Except Firewall. | 2026-10-24 | 300 | 11:00 | 16:00 |  | In Progress
2 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT | Connect All the Network Cables to Firewalls but ports should be in a shutdown state from Switch end | 2026-10-24 |  |  |  |  | In Progress
3 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT | Power On Checkpoint Firewall | 2026-10-24 |  |  |  |  | In Progress
4 | On 23 Oct 2026 :- Secondary Devices physically delivered at STT | Connect All the Network Cables to Checkpoint Firewall with HA cables but ports should be in shutdown state from Switch end | 2026-10-24 |  |  |  |  | In Progress
|  | Make all the device active in STT and start shutdown in ITI once by one | 2026-10-24 | 300 | 16:00 | 21:00
A | On 23-24-Oct-26 :- Primary Device Shutdown activity | DMZ/Proxy/Cloud- Standby FW - Check Point standby FW load balancer startup activity | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Power shutdown Active DMZ/Proxy/Partner firewall | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Wait for 5 Min | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the Checkpoint firewall | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check health status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
B | On 23-24-Oct-26 :- Primary Device Shutdown activity | ASR 1002-X KS-2 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the ASR 1002-X DC-KS-2 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
C | On 23-24-Oct-26 :- Primary Device Shutdown activity | ASR 1002-X KS-1 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the ASR 1002-X DC-KS-1 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
D | On 23-24-Oct-26 :- Primary Device Shutdown activity | ASR1006-X GM-2 VPN router startup activity | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the ASR1006-X DC-GM-2 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
E | On 23-24-Oct-26 :- Primary Device Shutdown activity | DMZ- DCDMZADC02- F5-BIG-LTM-I11800 load balancer startup activity | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Shutdown DCDMZADC02- F5-BIG-LTM-I11800 load balancer Primary Loadbalancer | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the DMZ- DCDMZADC02- F5-BIG-LTM-I11800 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
F | On 23-24-Oct-26 :- Primary Device Shutdown activity | Internal - DCCINTADC02 - F5-BIG-IP I5800 load balancer startup activity | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Shutdown F5-BIG-IP I5800 load balancer Primary Loadbalancer | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the - F5-BIG-IP I5800 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
G | On 23-24-Oct-26 :- Primary Device Shutdown activity | DMZ-IPv6 to IPv4 convertor Standby Startup Device | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the DMZ-IPv6 to IPv4 convertor | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
H | On 23-24-Oct-26 :- Primary Device Shutdown activity | DMZ-DDOS ARBOR Standby | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the DMZ-DDOS ARBOR | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
L | On 23-24-Oct-26 :- Primary Device Shutdown activity | DMZ-L3 Switch | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the DMZ-L3 Switch | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
M | On 23-24-Oct-26 :- Primary Device Shutdown activity | DMZ-INternet R2 Router Standby | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Unshut the cables connected ports from switches to the DMZ-INternet R2 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check Health Status | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Ping next hope gateways and reachability of devices | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
N | On 23-24-Oct-26 :- Primary Device Shutdown activity | Core-Switch-1 | 2026-10-24 | 120 | 21:00 | 23:00 |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Move all the remaining uplink Links connected to existing N9508 Core Switch-1 to New Temparory Coreswitch | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Shutdown the Core-Switch-1 | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Shifting of Core-Switch from ITI to STT | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity |  | 2026-10-24 |  |  |  |  | In Progress
O | On 23-24-Oct-26 :- Primary Device Shutdown activity | WAN R1 routers | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Take backup of R1 router | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Switch off R1 router at STT | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Pack up R1 router and sent to STT | 2026-10-24 |  |  |  |  | In Progress
| On 23-24-Oct-26 :- Primary Device Shutdown activity | Check health stattus and next hop router reachability | 2026-10-24 |  |  |  |  | In Progress
A | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | FTD-CHASSIS-1 start activity | 2026-10-25 | 360 | 23:00 | 29:00 |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | connect all cables of FTD chassis -1 | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect Failover/Cluster Cables as well between FTD chassis | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Power on FTD chassis 1 | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check health status of FTD chassis on FMC | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
B | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | CORE FW - Fortinet Active start activity | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the Core Fw Forti-Fw01 Active Device | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Power on Core Fw Forti-Fw01 Active Device | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check health status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
C | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | DMZ/Cloud/Proxy- Standby FW - Check Point Active FW load balancer startup activity | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the Check Point Active Device | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Power on Check Point Active Device | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check health status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
D | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | ASR1006-X DC-GM-1 VPN router startup activity | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the ASR1006-X DC-GM-1 | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
E | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | DMZ- F5-BIG-LTM-I11800 Active load balancer startup activity | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the DMZ- DCDMZADC02- F5-BIG-LTM-I11800 Active | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
F | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Internal - F5-BIG-IP I5800 load balancer Active startup activity | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the DCCINTADC02 - F5-BIG-IP I5800 Active | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
G | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | DMZ-IPv6 to IPv4 convertor Active Startup Device | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the DMZ-IPv6 to IPv4 convertor Active | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
H | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | DMZ-DDOS ARBOR & NTB Device | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the DMZ-DDOS ARBOR & NTB Device | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
I | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | DMZ-INternet R1 Router Standby | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the DMZ-INternet R1 | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
J | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s |  | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | MPLS Router activity | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect cables to the MPLS R1 | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
K | On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Core Switch activity | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Connect all the uplink cables to the Core-Switch | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Check Health Status | 2026-10-25 |  |  |  |  | In Progress
| On 25th Oct 2026 :- Primary Devices physically delivered at Ctls-s | Ping next hope gateways and reachability of devices | 2026-10-25 |  |  |  |  | In Progress
Formulas:
Target Date = [Target Date, row above]
Time Duration in Min = [Target Date]+0.2

## Pre-Event Checklist (hidden)
CBS PRE-EVENT CHECKLIST
Owners update Status, % Completion and RAG. All items must be Closed / Green before the GO/NO-GO for the batch.
# | Phase | Location | Scope / Application | Description | Owner | Target Date | Migration Date | Status | % Completion | Planned Date | Actual Date | RAG | Frequency | Comments
A1 | Inventory | Source / Target | All | Freeze CBS device list (Scope sheet: 396 physical rows, 364 LPAR/VM incl. new Hyper-V VM DCHRMAPP1) and verify primary/sub-serial, source rack-U and target rack-U. | Kyndryl Migration / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A2 | Application | Source / Target | All applications | Confirm application owner group, application name, Bank SPOC and vendor contacts for every group in Batch_App_Summary. | Application Teams / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A3 | Application | Source | All applications | Application / DB shutdown, startup, validation and rollback procedures per application (Shutdown_Startup_Seq). | Application Teams / Vendors |  | 2026-10-23 | Open | 0% |  |  |  | Once
A4 | Application | Source / Target | All applications | Runbook walkthrough calls completed with every application group (Runbook Calls_SS). | Kyndryl Migration / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Per app group
A5 | SAN | Source / Target | SAN-connected devices | Validate connected-device shutdown gates, port mapping, ISL plan and zoning freeze; configuration backups of all switches, SVC and FlashSystem (P-02). | SAN / Storage / Vendors |  | 2026-10-23 | Open | 0% |  |  |  | Once
A6 | SAN | Target | Batch 1 / Batch 2 switches | Confirm target ISL cabling between Batch 1 switch BLR512B-G7-SW2 and Batch 2 switches (BLR128B-G7-SW2, DCX-BLR512B-2, BLR512B-G7-SW1 etc.) and the inter-site DWDM/FCIP link for BLRDCREP ↔ BLRNDC. | SAN / Network / STT |  | 2026-10-23 | Open | 0% |  |  |  | Once
A7 | SAN | Source | Single-fabric devices | Confirm second HBA / path for single-fabric devices D2SXMZ3, 3QGL6C2, 7PRRDV2, 7V1N0V3 (SAN_Dependency_Check in v3 plan). | SAN / Server Teams |  | 2026-10-23 | Open | 0% |  |  |  | Once
A8 | Rack Readiness | Target | Loose devices | Confirm target rack-U for every loose device (Target_Rack_Readiness): 225 OK, 24 CHECK (TBD / N/W / Spare / Scrap / rack shift at STT), 0 RISK. | Migration / STT / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A9 | Rack Readiness | Target | Batch 1 temporary positions | UAT fabric (BLR128B-G7-SW1/SW2) and all connected devices now move together in Batch 2 with racks C2, D1, D2, D3, K6, L5 – temporary positions at target are no longer required. Confirm with Bank. | Migration / STT |  | 2026-10-23 | Not Applicable | 0% |  |  |  | Once
A10 | Rack Readiness | Source / Target | All racks | Confirm rack movement per rackmap (Racks for CBS): 12 empty racks and 24 OEM-loaded racks; empty racks travel first in each batch. | Migration / Royal / STT |  | 2026-10-23 | Open | 0% |  |  |  | Once
A11 | Transport | Source / Target | All batches | Confirm truck plan: 23 trucks (Batch 1: 5, Batch 2: 14, Batch 3: 4), capacity rule (45 boxes per truck: 1 box = 1×2U or 2×1U; empty rack 11.25 / OEM-loaded rack 22.5 box-equivalents), Batch 1 loading order (SAN Director + P10 frame + tape library first, NDC next), departure slots, two-hour travel, gate pass, e-way bill and insurance. | Migration / Royal / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A12 | Target | Target | All batches | Confirm power, PDU, network (ToR / core), SAN cabling, console access and onsite resources. | STT / Kyndryl / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A13 | Network | Target | Batch 3 network & security | Confirm target core network / firewalls can serve Batches 1–2 before Batch 3 network & security devices arrive. | Network / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A14 | Network | Source | DC-K6-N9K-TOR-SW1 | FDO24130M76 (K6 ToR, 28 P2P links) now moves in Batch 2 together with the frames, directors and tape it serves – confirm no re-patch needed. | Network / Bank |  | 2026-10-23 | Not Applicable | 0% |  |  |  | Once
A15 | OEM | Source / Target | OEM racks | Confirm OEM engineers (IBM, Dell, Hitachi) for OEM-loaded rack moves, power-on and health checks. | Kyndryl Migration / OEMs |  | 2026-10-23 | Open | 0% |  |  |  | Once
A16 | Data Gaps | Source | Storage endpoints | Resolve PPT gaps: Data Domain (W6) serials, HPE StoreOnce in D5 and D4 (rack D4 not in inventory), DCDLRACSTORAGE serial mismatch. | Storage / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A17 | Data Gaps | Source | Moving racks | Confirm W2W in-scope devices inside moving racks that are not in the inventory (e.g. 8 in rack D5) travel with the rack. | Migration / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A18 | Scope | Source | Scrap / OOS | Confirm movement of devices flagged Scrap / OOS: 3131AG435894, 847C10W, 84B6FAW, 12DGGQ00100002. | Bank |  | 2026-10-23 | Open | 0% |  |  |  | Once
A19 | Power Status | Target | Devices OFF at source | Devices powered OFF at source must stay OFF at target (AJ29019530, FCJXJ03, 3DCYM03). | Migration / BAU |  | 2026-10-23 | Open | 0% |  |  |  | Once
A20 | Backup | Source | All batches | Backups completed before shutdown; backup schedules suspended for the window. | Backup / BAU |  | 2026-10-23 | Open | 0% |  |  |  | Per batch
A21 | Monitoring | Source / Target | All batches | Alert-suppression windows registered with SOC for every batch. | SOC / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Per batch
A22 | Change | Source / Target | All batches | Change records approved for Batches 1, 2 and 3 (Change Records sheet). | Kyndryl / Bank |  | 2026-10-23 | Open | 0% |  |  |  | Per batch
B1 | Batch Readiness | Source / Target | Batch 1 | Confirm batch application contacts, device scope, shutdown, handover, trucks TR-1 … TR-1.4 and target positions (incl. P10 frame 78A1DE8 in rack C3). | Migration / Application / Infra Teams |  | 2026-10-23 | Open | 0% |  |  |  | Per batch
B2 | Batch Readiness | Source / Target | Batch 2 | Confirm batch application contacts, device scope, shutdown, handover, trucks TR-2 … TR-2.13 and target positions (incl. UAT fabric). | Migration / Application / Infra Teams |  | 2026-10-23 | Open | 0% |  |  |  | Per batch
B3 | Batch Readiness | Source / Target | Batch 3 | Confirm batch application contacts, device scope, shutdown, handover, trucks TR-3 … TR-3.3 and target positions. | Migration / Application / Infra Teams |  | 2026-10-23 | Open | 0% |  |  |  | Per batch

## GO-NOGO Checklist (hidden)
GO / NO-GO Checklist
Sr. No. | Gates | Description | Criteria | Approved By | Sign-off Received | GO / NO-GO | Notes
GO / NO-GO – overall gates
1 | Target DC is Ready | Power, network, racks available in the target DC | Responsible teams verified and confirmed readiness | Bank – Anandhamani M | N | Pending
2 | Application / Business readiness | Application owners aware of the migration and have test cases | Test cases and testing resources aligned | Application owners, OEMs & Vendors | N | Pending
3 | Approvals from stakeholders | Migration approvals from group owners and Canara Bank | Approvals received | Bank | N | Pending
4 | Network readiness | ToR / core placement and network cabling at target | Responsible teams verified and confirmed | Bank / Kyndryl Network & Migration Team | N | Pending
5 | Documentation ready | E-way bill, insurance, exit gate pass at ITI and inward gate pass at STT | Responsible teams verified and confirmed | Bank / Royal International | N | Pending
6 | External factors | Weather and any other external factor | Verify on the day of migration | Kyndryl Migration | N | Pending
7 | Command Centre & Runbook readiness | Command centre, bridge and runbook ready | Command centre ready; runbook signed off | Kyndryl | N | Pending
8 | Change Approval | Change records raised and approved for all batches | Approved change | Bank / Kyndryl | N | Pending
9 | Team availability | All resources aligned (Bank, Kyndryl, OEMs, Royal, STT) | Leads approval across workstreams | Event PM / Architect | N | Pending
10 | Pre-Event Checklist | Technical and event milestones achieved | All Pre-Event items Closed / Green | Event PM / Architect | N | Pending
11 | Sign-offs taken for risks | Open risks in Risk Log accepted by Bank | Risk sign-off received | Bank – Anandhamani M | N | Pending
Batch 1 gates (24/10/2026 03:15)
12 | CBS Fabric-A health | All CBS production hosts have healthy paths via BLR512B-G7-SW1 before BLR512B-G7-SW2 leaves | Multipath report clean | SAN / AIX BAU | N | Pending
13 | P10 frame 78A1DE8 (C3) in Batch 1 | Bank accepts Core DB-2 frame 78A1DE8 moving in Batch 1 with SAN paths via BLR512B-G7-SW2 only until Batch 2 | Bank / AIX BAU confirmation | Network / Bank | N | Pending
14 | UAT fabric in Batch 2 | BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected UAT devices (78C7868, 78C7848, UAT storage) moved to Batch 2 | Bank / UAT owners confirmation | Migration / STT | N | Pending
15 | Replication pause | DC→NDC replication pause accepted (until Batch 2) | Bank acceptance | Bank | N | Pending
Batch 2 gates (24/10/2026 21:30)
16 | Batch 1 closed | Batch 1 target validation complete | Batch 1 closure task Closed | Kyndryl Migration | N | Pending
17 | Target SAN readiness | ISL cabling to Batch 1 switches and DWDM/FCIP link ready; zoning freeze agreed | SAN / Network confirmation | SAN / Network | N | Pending
18 | Truck readiness | 14 trucks (TR-2 … TR-2.13) confirmed with slots | Royal confirmation | Royal International | N | Pending
19 | Application shutdown readiness | All Batch 2 application groups confirmed shutdown / startup owners | App SPOC confirmations | Application Teams | N | Pending
Batch 3 gates
20 | Target network core | Target core network / firewalls able to serve migrated workloads | Network confirmation | Network / Bank | N | Pending
21 | Truck readiness | 4 trucks (TR-3 … TR-3.3) confirmed | Royal confirmation | Royal International | N | Pending
|  |  |  | DECISION |  | PENDING

## Cutover - Day Activities
CANARA BANK DC MIGRATION ¦ CBS CUTOVER DAY ACTIVITIES
CBS Wave Start Time: 23rd Oct - 1PM ; End Time - 27th Oct 9.15PM (Refer Row # 233)
Sl. No. | Movement Batch | Task ID | Location | Description | Responsible Team | Planned Duration (Minutes) | Planned Start Date | Planned End Date | Planned Start Time | Planned End Time | Actual Duration | Actual Start Date/Time | Actual End Date/Time | Status | Dependencies | Comments | App Owner Group | Application Name | Application SPOC Name | Application Scope Contact | Application Vendor Name | Application Vendor Contact | Allocated Resource | Truck No | Checkpoint / Notification | Planned Start (Date-Time) | Planned End (Date-Time)
PRE-EVENT (T-1) – PREPARATION
1 | Pre-Event | P-01 | Source | Label all in-scope devices, cables (both ends) and rails with batch / truck / target rack-U labels; take front & rear photos of every rack. | Power-IT / SAN / Royal / Bank | 480 | 2026-10-22 | 2026-10-22 | 10:00 | 18:00 |  |  |  | Open | [11 empty] | 2026-10-22 10:00 | 2026-10-22 18:00
2 | Pre-Event | P-02 | Source | Take configuration backups: all SAN switches/directors (configupload / supportsave), SVC & FlashSystem configs, network devices, HMC. | SAN / Storage / Network | 480 | 2026-10-22 | 2026-10-22 | 10:00 | 18:00 |  |  |  | Open | [11 empty] | 2026-10-22 10:00 | 2026-10-22 18:00
3 | Pre-Event | P-05 | Source/Target | Final GO/NO-GO readiness review (GO-NOGO Checklist) | Kyndryl Migration / Bank | 180 | 2026-10-24 | 2026-10-24 | 0:00 | 3:00 |  |  |  | Open | [10 empty] | Checkpoint | 2026-10-24 | 2026-10-24 03:00
BATCH 1 – PRE-AGREED: BLR512B-G7-SW2, NDC, CBS TAPE & P10 FRAME 78A1DE8 (C3) ¦ 24/10/2026 ¦ TR-1 … TR-1.4
▸ Source – readiness & controlled shutdown
4 | 1 | B1-01 | Source | Activate migration bridge; verify approved change, backups and risk sign-off for Batch 1. | Kyndryl Migration / Bank | 15 | 2026-10-24 | 2026-10-24 | 3:00 | 3:15 |  |  |  | Open | [10 empty] | Bridge open | 2026-10-24 03:00 | 2026-10-24 03:15
5 | 1 | B1-02 | Source | GO/NO-GO decision to begin Batch 1 cutover based on FTD Migration | Kyndryl Migration / Bank | 15 | 2026-10-24 | 2026-10-24 | 3:15 | 3:30 |  |  |  | Open | B1-01 | [9 empty] | GO/NO-GO | 2026-10-24 03:15 | 2026-10-24 03:30
6 | 1 | B1-03 | Source | Suppress monitoring alerts for all Batch 1 devices (40 physical devices, 1 LPAR(s), 10 VMs). | SOC / Bank | 15 | 2026-10-24 | 2026-10-24 | 3:30 | 3:45 |  |  |  | Open | B1-02 | [10 empty] | 2026-10-24 03:30 | 2026-10-24 03:45
7 | 1 | B1-04 | Source | Confirm every CBS production host shows healthy Fabric-A paths via BLR512B-G7-SW1 (787100G) – CBS runs single-fabric from 10:00 until 22:00 once BLR512B-G7-SW2 (755231F) is removed. | SAN / AIX BAU | 30 | 2026-10-24 | 2026-10-24 | 3:30 | 4:00 |  |  |  | Open | B1-02 | Risk: single-fabric CBS production for ~12 h. | [9 empty] | 2026-10-24 03:30 | 2026-10-24 04:00
8 | 1 | B1-05 | Source | Confirm all applications on Batch 1 servers (NDC, P10 frame 78A1DE8 in C3) are stopped and OEMs are engaged for the tape libraries (D5, L1, L2, L3). | Network / Bank | 60 | 2026-10-24 | 2026-10-24 | 3:30 | 4:30 |  |  |  | Open | B1-02 | Recommendation in v3 plan: Batch 2 with rack K6. | [9 empty] | 2026-10-24 03:30 | 2026-10-24 04:30
9 | 1 | B1-06 | Source | Pause DC→NDC replication (BLRDCSV3/BLRDCSV2 → NDC). BLRNDC_64BG7_SW1/SW2 move now; BLRDCREP principal switches move in Batch 2 – replication stays down until Batch 2 is up. | Storage / Replication | 30 | 2026-10-24 | 2026-10-24 | 3:30 | 4:00 |  |  |  | Open | B1-02 | [10 empty] | 2026-10-24 03:30 | 2026-10-24 04:00
10 | 1 | B1-07 | Source | Stop applications – Data Center Operations Section (ITI) (NDR HMC, CBS Allied Application, DCO, Database Server - NDC - ASBA n Dpsecure); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 30 | 2026-10-24 | 2026-10-24 | 4:00 | 4:30 |  |  |  | Open | B1-03 | Scope: 10 device(s): 9 physical, 1 LPAR, 0 VM | Data Center Operations Section (ITI) | NDR HMC, CBS Allied Application, DCO, Database Server - NDC - ASBA n Dpsecure | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | 47206 |  |  |  | 2026-10-24 04:00 | 2026-10-24 04:30
11 | 1 | B1-08 | Source | Stop applications – IT Assets Management Section (RAP Remote); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 0 | 2026-10-24 | 2026-10-24 | 4:00 | 4:00 |  |  |  | Open | B1-03 | Scope: 4 device(s): 0 physical, 0 LPAR, 4 VM | IT Assets Management Section | RAP Remote | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com |  | Sonata technology pvt ltd | Dinesh ¦ 9920710330 ¦ dinesh.pratahkal@sonata-software.com |  |  |  | 2026-10-24 04:00 | 2026-10-24 04:00
12 | 1 | B1-09 | Source | Stop applications – SPMS (ASBA); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 0 | 2026-10-24 | 2026-10-24 | 4:00 | 4:00 |  |  |  | Open | B1-03 | Scope: 3 device(s): 0 physical, 0 LPAR, 3 VM | SPMS | ASBA | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com | [6 empty] | 2026-10-24 04:00 | 2026-10-24 04:00
13 | 1 | B1-10 | Source | Stop applications – Service Unit Section (SFMS); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 0 | 2026-10-24 | 2026-10-24 | 4:00 | 4:00 |  |  |  | Open | B1-03 | Scope: 2 device(s): 2 physical, 0 LPAR, 0 VM | Service Unit Section | SFMS | [7 empty] | 2026-10-24 04:00 | 2026-10-24 04:00
14 | 1 | B1-11 | Source | Stop applications – DPSecure (Dpsecure); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 0 | 2026-10-24 | 2026-10-24 | 4:00 | 4:00 |  |  |  | Open | B1-03 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com |  | Landmark Solutions | Ajikya Hatim ¦ 9768524076 ¦ ajinkya@lsssoftware.com |  |  |  | 2026-10-24 04:00 | 2026-10-24 04:00
15 | 1 | B1-12 | Source | Stop applications – To Be Confirmed (apps TBC); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 0 | 2026-10-24 | 2026-10-24 | 4:00 | 4:00 |  |  |  | Open | B1-03 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | To Be Confirmed | [8 empty] | 2026-10-24 04:00 | 2026-10-24 04:00
16 | 1 | B1-13 | Source | Stop databases hosted on Batch 1 LPARs / VMs / servers (NDC DBs, Core DB-2 LPAR on 78A1DE8) in the agreed sequence. | DB / Kyndryl Migration | 0 | 2026-10-24 | 2026-10-24 | 8:30 | 8:30 |  |  |  | Open | B1-07, B1-08, B1-09, B1-10, B1-11, B1-12 | [10 empty] | 2026-10-24 08:30 | 2026-10-24 08:30
17 | 1 | B1-14 | Source | Shut down 1 AIX LPAR(s) on P10 frame 78A1DE8 (C3) and 10 Hyper-V VMs on NDC-BASENDC-APP cleanly; verify all are down. | AIX BAU / Virtualization | 30 | 2026-10-24 | 2026-10-24 | 4:30 | 5:00 |  |  |  | Open | B1-13 | [10 empty] | 2026-10-24 04:30 | 2026-10-24 05:00
18 | 1 | B1-15 | Source | Power off physical servers/frames: CR1130RH6A, 3185702, ndrfccdb, 78DA08X, NDC-BASENDC-APP, DCC0GRN24, C3-9080-HEX-SN78A1DE8-CORE_DB-2. | AIX BAU / Kyndryl Migration | 30 | 2026-10-24 | 2026-10-24 | 5:00 | 5:30 |  |  |  | Open | B1-14 | [10 empty] | 2026-10-24 05:00 | 2026-10-24 05:30
19 | 1 | B1-16 | Source | Validate all SAN hosts are down; shut down storage, SVC and tape (12 rows): 5ZWGVP3, H4XGVP3, TAPEINV22, 78BB816, 78DB196, SANINV379, SANINV378, 78DB197, 78E3NKE2, SANINV382 (+2 more). | SAN / Storage / IBM | 30 | 2026-10-24 | 2026-10-24 | 5:30 | 6:00 |  |  |  | Open | B1-15 | [10 empty] | 2026-10-24 05:30 | 2026-10-24 06:00
20 | 1 | B1-17 | Source | Shut down SAN switches: BLRNDC_64BG7_SW1/SW2 (786731M/786729Z), then BLR512B-G7-SW2 (755231F) only after B1-04 confirmed. | SAN / IBM | 30 | 2026-10-24 | 2026-10-24 | 6:00 | 6:30 |  |  |  | Open | B1-16, B1-04 | [10 empty] | 2026-10-24 06:00 | 2026-10-24 06:30
21 | 1 | B1-18 | Source | Shut down network & security (14 rows): CB-NDR-P2P-SW, NDR-Cisco-Nexus-SW1, NDR-Cisco-Nexus-SW2, 2161392000161, SY2511A-131200531 / SY2304-131203010, CAEZ2226, CAN-NDR-FORTINET-FW2, CAN-NDR-FORTINET-FW1, NDR-DMZ-SW-01, NDR_DMZ_SW_02 (+3 more). | Network / Bank | 60 | 2026-10-24 | 2026-10-24 | 6:30 | 7:30 |  |  |  | Open | B1-17, B1-05 | [10 empty] | 2026-10-24 06:30 | 2026-10-24 07:30
22 | 1 | B1-19 | Source | Verify every Batch 1 device is powered off; record cabling, port labels and photos; update Scope status. | Kyndryl Migration / Bank | 15 | 2026-10-24 | 2026-10-24 | 7:30 | 7:45 |  |  |  | Open | B1-18 | [9 empty] | Notify: Batch 1 down | 2026-10-24 07:30 | 2026-10-24 07:45
▸ Source – Royal handover, unracking, packing & loading
23 | 1 | B1-20 | Source | Royal handover. Unmount and pack 29 loose device empty racks GR-A3, GR-A4, GR-A2, GR-A1, D5, A4 go first (keep rails, screws and power cables with each device). | Royal International / Bank / Kyndryl | 240 | 2026-10-24 | 2026-10-24 | 6:00 | 10:00 |  |  |  | Open | B1-19 | [9 empty] | Handover to Royal | 2026-10-24 06:00 | 2026-10-24 10:00
24 | 1 | B1-21 | Source | Prepare 4 OEM-loaded racks C3, L1, L2, L3 for transport (secure devices, remove external cabling, OEM sign-off). | OEM Vendor (IBM) / Royal | 300 | 2026-10-24 | 2026-10-24 | 6:00 | 11:00 |  |  |  | Open | B1-19 | [10 empty] | 2026-10-24 06:00 | 2026-10-24 11:00
25 | 1 | B1-22 | Source | Carefully unrack BLR512B-G7-SW2 (755231F) from rack A4 – adjacent production devices remain powered on until 22:00. | Royal / SAN / Network | 120 | 2026-10-24 | 2026-10-24 | 9:00 | 11:00 |  |  |  | Open | B1-19 | Adjacent production devices remain powered on. | [9 empty] | 2026-10-24 09:00 | 2026-10-24 11:00
26 | 1 | B1-23 | Source | Verify devices against scope; prepare gate pass and e-way bill for TR-1 … TR-1.4. | Kyndryl Migration / Bank | 180 | 2026-10-24 | 2026-10-24 | 9:00 | 12:00 |  |  |  | Open | B1-20 | [10 empty] | 2026-10-24 09:00 | 2026-10-24 12:00
▸ Transport & target receiving – per truck
27 | 1 | B1-24 | Source | Load & seal TR-1 – Racks: C3 (OEM loaded), D5 (empty); loose: 1 SAN director/switch, 2 storage/backup/tape. Loose devices packed in 11 box(es) (1 box = 1×2U or 2×1U); Truck load 44.75/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-24 | 2026-10-24 | 12:00 | 12:30 |  |  |  | Open | B1-23 | [8 empty] | TR-1 |  | 2026-10-24 12:00 | 2026-10-24 12:30
28 | 1 | B1-25 | Transit | Transport TR-1 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-24 | 2026-10-24 | 12:30 | 14:30 |  |  |  | Open | B1-24 | [8 empty] | TR-1 | Notify command centre on departure & arrival | 2026-10-24 12:30 | 2026-10-24 14:30
29 | 1 | B1-26 | Target | TR-1: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-24 | 2026-10-24 | 14:30 | 14:45 |  |  |  | Open | B1-25 | [8 empty] | TR-1 |  | 2026-10-24 14:30 | 2026-10-24 14:45
30 | 1 | B1-27 | Target | TR-1: position and fix racks at target (C3→H-14, D5→D-04); connect PDUs. Empty racks first so loose devices can be re-racked. | Royal / STT / Power-IT | 60 | 2026-10-24 | 2026-10-24 | 14:45 | 15:45 |  |  |  | Open | B1-26 | [8 empty] | TR-1 |  | 2026-10-24 14:45 | 2026-10-24 15:45
31 | 1 | B1-28 | Target | TR-1: unpack and mount 3 loose device(s) in mapped target rack-U (target racks: D-04, F-01). | Royal / Power-IT / Kyndryl Migration | 45 | 2026-10-24 | 2026-10-24 | 15:45 | 16:30 |  |  |  | Open | B1-27 | [8 empty] | TR-1 |  | 2026-10-24 15:45 | 2026-10-24 16:30
32 | 1 | B1-29 | Source | Load & seal TR-1.1 – Racks: L1 (OEM loaded); loose: 1 storage/backup/tape. Loose devices packed in 2 box(es) (1 box = 1×2U or 2×1U); Truck load 24.5/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-24 | 2026-10-24 | 12:30 | 13:00 |  |  |  | Open | B1-23 | [8 empty] | TR-1.1 |  | 2026-10-24 12:30 | 2026-10-24 13:00
33 | 1 | B1-30 | Transit | Transport TR-1.1 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-24 | 2026-10-24 | 13:00 | 15:00 |  |  |  | Open | B1-29 | [8 empty] | TR-1.1 | Notify command centre on departure & arrival | 2026-10-24 13:00 | 2026-10-24 15:00
34 | 1 | B1-31 | Target | TR-1.1: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-24 | 2026-10-24 | 15:00 | 15:15 |  |  |  | Open | B1-30 | [8 empty] | TR-1.1 |  | 2026-10-24 15:00 | 2026-10-24 15:15
35 | 1 | B1-32 | Target | TR-1.1: position and fix racks at target (L1→C-01); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-24 | 2026-10-24 | 15:15 | 16:15 |  |  |  | Open | B1-31 | [8 empty] | TR-1.1 |  | 2026-10-24 15:15 | 2026-10-24 16:15
36 | 1 | B1-33 | Target | TR-1.1: unpack and mount 1 loose device(s) in mapped target rack-U (target racks: D-04). Wait for target rack(s) on TR-1. | Royal / Power-IT / Kyndryl Migration | 35 | 2026-10-24 | 2026-10-24 | 16:15 | 16:50 |  |  |  | Open | B1-32, B1-27 | [8 empty] | TR-1.1 |  | 2026-10-24 16:15 | 2026-10-24 16:50
37 | 1 | B1-34 | Source | Load & seal TR-1.2 – Racks: L2 (OEM loaded), L3 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-24 | 2026-10-24 | 13:00 | 13:30 |  |  |  | Open | B1-23 | [8 empty] | TR-1.2 |  | 2026-10-24 13:00 | 2026-10-24 13:30
38 | 1 | B1-35 | Transit | Transport TR-1.2 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-24 | 2026-10-24 | 13:30 | 15:30 |  |  |  | Open | B1-34 | [8 empty] | TR-1.2 | Notify command centre on departure & arrival | 2026-10-24 13:30 | 2026-10-24 15:30
39 | 1 | B1-36 | Target | TR-1.2: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-24 | 2026-10-24 | 15:30 | 15:45 |  |  |  | Open | B1-35 | [8 empty] | TR-1.2 |  | 2026-10-24 15:30 | 2026-10-24 15:45
40 | 1 | B1-37 | Target | TR-1.2: position and fix racks at target (L2→C-02, L3→C-03); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-24 | 2026-10-24 | 15:45 | 16:45 |  |  |  | Open | B1-36 | [8 empty] | TR-1.2 |  | 2026-10-24 15:45 | 2026-10-24 16:45
41 | 1 | B1-38 | Source | Load & seal TR-1.3 – Racks: GR-A1 (empty), GR-A2 (empty), GR-A3 (empty), GR-A4 (empty). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-24 | 2026-10-24 | 13:30 | 14:00 |  |  |  | Open | B1-23 | [8 empty] | TR-1.3 |  | 2026-10-24 13:30 | 2026-10-24 14:00
42 | 1 | B1-39 | Transit | Transport TR-1.3 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-24 | 2026-10-24 | 14:00 | 16:00 |  |  |  | Open | B1-38 | [8 empty] | TR-1.3 | Notify command centre on departure & arrival | 2026-10-24 14:00 | 2026-10-24 16:00
43 | 1 | B1-40 | Target | TR-1.3: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-24 | 2026-10-24 | 16:00 | 16:15 |  |  |  | Open | B1-39 | [8 empty] | TR-1.3 |  | 2026-10-24 16:00 | 2026-10-24 16:15
44 | 1 | B1-41 | Target | TR-1.3: position and fix racks at target (GR-A1→N-01, GR-A2→N-02, GR-A3→N-03, GR-A4→N-04); connect PDUs. Empty racks first so loose devices can be re-racked. | Royal / STT / Power-IT | 60 | 2026-10-24 | 2026-10-24 | 16:15 | 17:15 |  |  |  | Open | B1-40 | [8 empty] | TR-1.3 |  | 2026-10-24 16:15 | 2026-10-24 17:15
45 | 1 | B1-42 | Source | Load & seal TR-1.4 – Racks: A4 (empty); loose: 2 SAN director/switch, 6 storage/backup/tape, 6 server, 11 network/security. Loose devices packed in 22 box(es) (1 box = 1×2U or 2×1U); Truck load 33.25/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-24 | 2026-10-24 | 14:00 | 14:30 |  |  |  | Open | B1-23 | [8 empty] | TR-1.4 |  | 2026-10-24 14:00 | 2026-10-24 14:30
46 | 1 | B1-43 | Transit | Transport TR-1.4 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-24 | 2026-10-24 | 14:30 | 16:30 |  |  |  | Open | B1-42 | [8 empty] | TR-1.4 | Notify command centre on departure & arrival | 2026-10-24 14:30 | 2026-10-24 16:30
47 | 1 | B1-44 | Target | TR-1.4: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-24 | 2026-10-24 | 16:30 | 16:45 |  |  |  | Open | B1-43 | [8 empty] | TR-1.4 |  | 2026-10-24 16:30 | 2026-10-24 16:45
48 | 1 | B1-45 | Target | TR-1.4: position and fix racks at target (A4→F-15); connect PDUs. Empty racks first so loose devices can be re-racked. | Royal / STT / Power-IT | 60 | 2026-10-24 | 2026-10-24 | 16:45 | 17:45 |  |  |  | Open | B1-44 | [8 empty] | TR-1.4 |  | 2026-10-24 16:45 | 2026-10-24 17:45
49 | 1 | B1-46 | Target | TR-1.4: unpack and mount 25 loose device(s) in mapped target rack-U (target racks: H-10, H-11, L-10, L-11, N-01, N-02, N-03, N-04). Wait for target rack(s) on TR-1.3. | Royal / Power-IT / Kyndryl Migration | 155 | 2026-10-24 | 2026-10-24 | 17:45 | 20:20 |  |  |  | Open | B1-45, B1-41 | [8 empty] | TR-1.4 |  | 2026-10-24 17:45 | 2026-10-24 20:20
`
50 | 1 | B1-47 | Target | Connect power, network and SAN cables per port map; validate labels and paths. | Power-IT / Network / SAN | 120 | 2026-10-24 | 2026-10-24 | 20:20 | 22:20 |  |  |  | Open | B1-28, B1-33, B1-37, B1-41, B1-46 | [10 empty] | 2026-10-24 20:20 | 2026-10-24 22:20
51 | 1 | B1-48 | Target | Power on network & security: CB-NDR-P2P-SW, NDR-Cisco-Nexus-SW1, NDR-Cisco-Nexus-SW2, 2161392000161, SY2511A-131200531 / SY2304-131203010, CAEZ2226, CAN-NDR-FORTINET-FW2, CAN-NDR-FORTINET-FW1 (+5 more); verify uplinks. | Network / Bank | 30 | 2026-10-24 | 2026-10-24 | 22:20 | 22:50 |  |  |  | Open | B1-47 | [10 empty] | 2026-10-24 22:20 | 2026-10-24 22:50
52 | 1 | B1-49 | Target | Power on SAN switches BLRNDC_64BG7_SW1/SW2 and BLR512B-G7-SW2; verify fabric health. BLR512B-G7-SW2 runs without ISL partners (BLR128B-G7-SW2, DCX-BLR512B-2 arrive in Batch 2). No zoning changes. | SAN / IBM | 180 | 2026-10-24 | 2026-10-25 | 22:50 | 1:50 |  |  |  | Open | B1-48 | [10 empty] | 2026-10-24 22:50 | 2026-10-25 01:50
53 | 1 | B1-50 | Target | Power on NDC storage/SVC and tape libraries (D5 tape drives, L1/L2/L3). | Storage / IBM | 120 | 2026-10-25 | 2026-10-25 | 1:50 | 3:50 |  |  |  | Open | B1-49 | [10 empty] | 2026-10-25 01:50 | 2026-10-25 03:50
54 | 1 | B1-51 | Target | Power on P10 frame 78A1DE8 (C3) and NDC servers; run frame health checks. | OEM Vendor (IBM) / AIX BAU | 120 | 2026-10-25 | 2026-10-25 | 3:50 | 5:50 |  |  |  | Open | B1-50 | [10 empty] | 2026-10-25 03:50 | 2026-10-25 05:50
55 | 1 | B1-52 | Target | Bring up VIOS, 1 LPAR(s) on 78A1DE8 and 10 Hyper-V VMs; verify OS boot, disks (multipath) and network. Note: 78A1DE8 has Fabric-A path via BLR512B-G7-SW1 only after Batch 2. | AIX BAU / Virtualization | 60 | 2026-10-25 | 2026-10-25 | 5:50 | 6:50 |  |  |  | Open | B1-51 | [10 empty] | 2026-10-25 05:50 | 2026-10-25 06:50
56 | 1 | B1-53 | Target | Start databases. | DB / Kyndryl Migration | 720 | 2026-10-25 | 2026-10-25 | 6:50 | 18:50 |  |  |  | Open | B1-52 | [10 empty] | 2026-10-25 06:50 | 2026-10-25 18:50
57 | 1 | B1-54 | Target | Start and validate applications – Data Center Operations Section (ITI); obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 18:50 | 6:50 |  |  |  | Open | B1-53 | Scope: 10 device(s): 9 physical, 1 LPAR, 0 VM | Data Center Operations Section (ITI) | NDR HMC, CBS Allied Application, DCO, Database Server - NDC - ASBA n Dpsecure | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | 47206 |  |  |  | 2026-10-25 18:50 | 2026-10-26 06:50
58 | 1 | B1-55 | Target | Start and validate applications – IT Assets Management Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 18:50 | 6:50 |  |  |  | Open | B1-53 | Scope: 4 device(s): 0 physical, 0 LPAR, 4 VM | IT Assets Management Section | RAP Remote | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com |  | Sonata technology pvt ltd | Dinesh ¦ 9920710330 ¦ dinesh.pratahkal@sonata-software.com |  |  |  | 2026-10-25 18:50 | 2026-10-26 06:50
59 | 1 | B1-56 | Target | Start and validate applications – SPMS; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 18:50 | 6:50 |  |  |  | Open | B1-53 | Scope: 3 device(s): 0 physical, 0 LPAR, 3 VM | SPMS | ASBA | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com | [6 empty] | 2026-10-25 18:50 | 2026-10-26 06:50
60 | 1 | B1-57 | Target | Start and validate applications – Service Unit Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 18:50 | 6:50 |  |  |  | Open | B1-53 | Scope: 2 device(s): 2 physical, 0 LPAR, 0 VM | Service Unit Section | SFMS | [7 empty] | 2026-10-25 18:50 | 2026-10-26 06:50
61 | 1 | B1-58 | Target | Start and validate applications – DPSecure; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 18:50 | 6:50 |  |  |  | Open | B1-53 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com |  | Landmark Solutions | Ajikya Hatim ¦ 9768524076 ¦ ajinkya@lsssoftware.com |  |  |  | 2026-10-25 18:50 | 2026-10-26 06:50
62 | 1 | B1-59 | Target | Start and validate applications – To Be Confirmed; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 18:50 | 6:50 |  |  |  | Open | B1-53 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | To Be Confirmed | [8 empty] | 2026-10-25 18:50 | 2026-10-26 06:50
63 | 1 | B1-60 | Target | Restore monitoring, complete batch validation and hand over to BAU / DCM. Note: tape backup via DCX-BLR512B-1/2 and NDC replication resume only after Batch 2. | Migration / BAU / Bank | 30 | 2026-10-26 | 2026-10-26 | 6:50 | 7:20 |  |  |  | Open | B1-54, B1-55, B1-56, B1-57, B1-58, B1-59 | [9 empty] | Notify: Batch 1 complete | 2026-10-26 06:50 | 2026-10-26 07:20
BATCH 2 – MERGED SAN BATCH incl. UAT FABRIC (BLR128B-G7-SW1/SW2, BLR512B-G7-SW1, DCX-BLR512B-1/2, DCX-BLR3SSWPC2111/2112, BLRDCREP) ¦ 24–25/10/2026 ¦ TR-2 … TR-2.13
▸ Source – readiness & controlled shutdown (downtime from 22:00)
64 | 2 | B2-01 | Source | Activate migration bridge for Batch 2; verify approved change, backups and risk sign-off. | Kyndryl Migration / Bank | 30 | 2026-10-24 | 2026-10-24 | 17:00 | 17:30 |  |  |  | Open | [10 empty] | Bridge open | 2026-10-24 17:00 | 2026-10-24 17:30
65 | 2 | B2-02 | Source | GO/NO-GO decision to begin Batch 2 (and Batch 3 source shutdown). | Kyndryl Migration / Bank | 15 | 2026-10-24 | 2026-10-24 | 17:30 | 17:45 |  |  |  | Open | B2-01 | [9 empty] | GO/NO-GO | 2026-10-24 17:30 | 2026-10-24 17:45
66 | 2 | B2-03 | Source | Suppress monitoring alerts for all Batch 2 devices (239 physical 198 LPARs, 155 VMs). | SOC / Bank | 15 | 2026-10-24 | 2026-10-24 | 17:45 | 18:00 |  |  |  | Open | B2-02 | [10 empty] | 2026-10-24 17:45 | 2026-10-24 18:00
67 | 2 | B2-04 | Source | Freeze zoning on all directors; confirm latest config backups (P-02) for SAN, SVC and FlashSystem. | SAN / Storage | 120 | 2026-10-24 | 2026-10-24 | 17:45 | 19:45 |  |  |  | Open | B2-02 | [10 empty] | 2026-10-24 17:45 | 2026-10-24 19:45
68 | 2 | B2-05 | Source | Stop applications – Data Center Operations Section (ITI) (SFMS, DCO, CBS Allied Application, No application installed, Audit Vault Database Firewall, NCBS RAC (+15 more)); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 162 device(s): 103 physical, 53 LPAR, 6 VM | Data Center Operations Section (ITI) | SFMS, DCO, CBS Allied Application, No application installed, Audit Vault Database Firewall, NCBS RAC, RAC DB, Middleware Hyper V Cluster, Tracs UAT DB, PeopleSoft HRMS (+11 more) | Rajeev ¦ rajeevkumar.j@canarabank.com, DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com, Sangeetha ¦ sangeetha_r@canarabank.com, Debjoy - 9874753518 ¦ debjoyroy@canarabank.com (+4 more) | [6 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
69 | 2 | B2-06 | Source | Stop applications – CBS(UTKARSH) (CBS(UTKARSH)); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 62 device(s): 0 physical, 62 LPAR, 0 VM | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com, VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | [6 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
70 | 2 | B2-07 | Source | Stop applications – EWIRM Section (IRMS); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 44 device(s): 14 physical, 0 LPAR, 30 VM | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com |  | M/s Kyndryl, M/s SAS Institute India Pvt. Ltd | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com, Naga Sai ¦ 8074105412 ¦ puttanagasaikumar@kyndryl.com, Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
71 | 2 | B2-08 | Source | Stop applications – Online Banking Technology Net banking Section (OFFLINE OTP, OBDX, OBT NET Banking Section - Report Server, OBT NET Banking Server - Jenkins Server, PKI, GIFTCITY OBDX); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 29 device(s): 1 physical, 24 LPAR, 4 VM | Online Banking Technology Net banking Section | OFFLINE OTP, OBDX, OBT NET Banking Section - Report Server, OBT NET Banking Server - Jenkins Server, PKI, GIFTCITY OBDX | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com, RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com, RAGHURAM ¦ 8908226867 ¦ RAGHURAMP@canarabank.com, VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com |  | MANIPAL TECHNOLOGY, OFSS, AROOT TECHNOLOGY | SUBRAMANIYAM ¦ 9741797150 ¦ offlineotp@canarabank.com, RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com, RAGHAV ¦ raghavendra.shivaram@oracle.com (+1 more) |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
72 | 2 | B2-09 | Source | Stop applications – Digital Lending and LAPS Section (CORPORATE LOAN MODULE, GST SAHAY, LAPS); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 21 device(s): 0 physical, 10 LPAR, 11 VM | Digital Lending and LAPS Section | CORPORATE LOAN MODULE, GST SAHAY, LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com |  | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
73 | 2 | B2-10 | Source | Stop applications – SPMS (CRM, Portal, DOCUMENT MANAGEMENT SYSTEM, Queue Management System, SPMS); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 18 device(s): 0 physical, 0 LPAR, 18 VM | SPMS | CRM, Portal, DOCUMENT MANAGEMENT SYSTEM, Queue Management System, SPMS | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com, Gururaj Pamidi ¦ 9535105108 ¦ gururajnaidu.pamidi@kyndryl.com /Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com, Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com, Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com (+2 more) |  | TechMatrix consulting pvt ltd, OSPYN, M/s AurionPro, M/s BoardPAC | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com, Manoj ¦ 9703145556 ¦ manoj.m@ospyn.com, sajeev/manoj ¦ 94892029040/9703145556 ¦ DOCMGMTSYS@GMAIL.COM (+2 more) |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
74 | 2 | B2-11 | Source | Stop applications – Government Business and Financial Inclusion Section (Aadhaar seeding through web, SFMS, FI, DC Aadhar Vault DB, DB server, EKYC (+3 more)); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 17 device(s): 9 physical, 7 LPAR, 1 VM | Government Business and Financial Inclusion Section | Aadhaar seeding through web, SFMS, FI, DC Aadhar Vault DB, DB server, EKYC, TAB, DB, CEDGE | arundhatikatolkar@canarabank.com, LEEMA ROSELIN K 9741644668, Kiran B R ¦ 7619453224 ¦ figsupport@canarabank.com & kiranbr@integramicro.co.in & hoditfimb@canarabank.com |  | Integra Micro Systems Pvt Ltd | Kiran B R ¦ 7619453224 ¦ kiranbr@integramicro.co.in & figsupport@canarabank.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
75 | 2 | B2-12 | Source | Stop applications – FCUBS (FCUBS); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 16 device(s): 0 physical, 15 LPAR, 1 VM | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com, Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com / PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com, Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  | SUNIL KASHIKAR, MADHAVI GEDELA, Karthik Manoharan | 9900139448 ¦ sunilr.kashikar@kyndryl.com, 6304027118 ¦ madhavi.gedela@kiya.ai, +91 8147387273 ¦ mk@wecodee.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
76 | 2 | B2-13 | Source | Stop applications – To Be Confirmed (apps TBC); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 15 device(s): 0 physical, 7 LPAR, 8 VM | To Be Confirmed | [8 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
77 | 2 | B2-14 | Source | Stop applications – HRMS Technical Section (PeopleSoft HRMS); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 15 device(s): 0 physical, 0 LPAR, 15 VM | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com |  | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
78 | 2 | B2-15 | Source | Stop applications – Canara Collection and Payment Services Section (CCPS-Canara Collections and Payments system); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 13 device(s): 0 physical, 0 LPAR, 13 VM | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com, Rajesh A, Kengal Veerendra Patil ¦ 7810073373/9880283138 ¦ hoccmssection@canarabank.com/hoccpstech@canarabank.com |  | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com, Naveen/Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
79 | 2 | B2-16 | Source | Stop applications – Software Project Management Section (apps TBC); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 12 device(s): 0 physical, 0 LPAR, 12 VM | Software Project Management Section |  | THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com, Vijey/Ankit ¦ 9487691736/7038831744 ¦ hotoncbs@canarabank.com;vijeyvr@canarabank.com;ankitsr@canarabank.com, Saket/Gaurav Baberwal, Vijey/Ankit |  | Ms Apmosys Technologies Pvt Ltd | Nandiratha ¦ 9938184406 ¦ rpasupport@canarabank.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
80 | 2 | B2-17 | Source | Stop applications – Online Banking Technology Mobile Banking (MOBILE BANKING, IMPS, UPI, MB); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 11 device(s): 1 physical, 5 LPAR, 5 VM | Online Banking Technology Mobile Banking | MOBILE BANKING, IMPS, UPI, MB | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com, NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com, Arjun ¦ 9952404855 ¦ hotomb@canarabank.com |  | NPST (Development), NPST | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com, Anandababu ¦ 7975771359 ¦ anandababu.m@npstx.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
81 | 2 | B2-18 | Source | Stop applications – ATM Section (ATM); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 8 device(s): 0 physical, 0 LPAR, 8 VM | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | [6 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
82 | 2 | B2-19 | Source | Stop applications – IIB(DCA) (IIB/ACE/ESB); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 8 device(s): 0 physical, 8 LPAR, 0 VM | IIB(DCA) | IIB/ACE/ESB | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | [6 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
83 | 2 | B2-20 | Source | Stop applications – Service Unit Section (RTGS, SFMS); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 5 device(s): 4 physical, 0 LPAR, 1 VM | Service Unit Section | RTGS, SFMS | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com, DEBJOY ROY ¦ 9874753518 ¦ AAQ_CanaraBank_NEFT_RTGS.xlsx |  | IFTAS | IFTAS (RBI SUBSIDIARY ) ¦ 914047524085 ¦ sfms.team@iftas.in |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
84 | 2 | B2-21 | Source | Stop applications – API Banking Section (APG (Google API Gatway)); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 5 device(s): 0 physical, 0 LPAR, 5 VM | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com |  | Comportement Software Private Limited, Digital API Craft | Murali ¦ 9880041498 ¦ murali@comportement.in, Sandeep Kenkare Satya Janardhana ¦ 9886236345 ¦ sandeep.k@digitalapi.ai, DCM ¦ DCM |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
85 | 2 | B2-22 | Source | Stop applications – Fintech Engagement & Partnership Section (Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 4 device(s): 0 physical, 0 LPAR, 4 VM | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com |  | M/S Olive Crypto Systems Pvt Ltd | Sunil Kumar Lokanadam ¦ 917893603440 ¦ sunil.l@olivecrypto.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
86 | 2 | B2-23 | Source | Stop applications – FCR Deposits Section (RAC DB, CKYC); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 3 device(s): 1 physical, 0 LPAR, 2 VM | FCR Deposits Section | RAC DB, CKYC | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com |  | ADROIT | SAKTHIVEL ¦ 9688969398 ¦ sakthiveli' <sakthiveli@adroitcorporate.com> |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
87 | 2 | B2-24 | Source | Stop applications – Data Warehouse Section (Data Warehouse); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 1 physical, 1 LPAR, 0 VM | Data Warehouse Section | Data Warehouse | [7 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
88 | 2 | B2-25 | Source | Stop applications – Network Administration Section (NCCM); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 2 physical, 0 LPAR, 0 VM | Network Administration Section | NCCM | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com |  | Inspira | Inspira ¦ Inspira ¦ nmssupport@canarabank.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
89 | 2 | B2-26 | Source | Stop applications – Government Business Module (GBM) IT Hub -New delhI (PM-Vidyalaxmi); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 0 physical, 2 LPAR, 0 VM | Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | DBA Team | [6 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
90 | 2 | B2-27 | Source | Stop applications – Online Banking Technology UPI and INFRA Section (UPI DB); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 0 physical, 2 LPAR, 0 VM | Online Banking Technology UPI and INFRA Section | UPI DB | [7 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
91 | 2 | B2-28 | Source | Stop applications – Compliance Department section (Compliance Kartavya); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | Compliance Department section | Compliance Kartavya | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com |  | Alphaplus Technologies | Phani Kumar N ¦ 9182989492 ¦ phani@alphaplustech.com,apt.projects@alphaplustech.com, apt.projects-technical@alphaplustech.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
92 | 2 | B2-29 | Source | Stop applications – Compliance Department (Compliance Kartavya); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | Compliance Department | Compliance Kartavya | [7 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
93 | 2 | B2-30 | Source | Stop applications – Online Banking Technology Mobile Banking,Digital Banking Wing (UPI); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com |  | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
94 | 2 | B2-31 | Source | Stop applications – DPSecure (Dpsecure); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com |  | Landmark Solutions | Ajikya Hatim ¦ 9768524076 ¦ ajinkya@lsssoftware.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
95 | 2 | B2-32 | Source | Stop applications – Application Development Section (In House) (ADM) (ADM); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Application Development Section (In House) (ADM) | ADM | Debarun, Yogesh ¦ 9398989380 ¦ yogeshsai@canarabank.com | [6 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
96 | 2 | B2-33 | Source | Stop applications – CTS (DEM); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | CTS | DEM | Shakti Narayan Gupta,Bhupesh Piplani,7975142177/9650976622,hoditcts@canarabank.com |  |  | In-House (ADM),ADM Team, IT Vertical,hoditadm@canarabank.com,NCR,NCR,9535040604,sharathkumar.manvi@ncratleos.com |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
97 | 2 | B2-34 | Source | Stop applications – New Initiatives-Technology Innovation Section (apps TBC); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | New Initiatives-Technology Innovation Section | [8 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
98 | 2 | B2-35 | Source | Stop applications – Online Banking Technology Mobile Banking Section (apps TBC); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | Online Banking Technology Mobile Banking Section | [8 empty] | 2026-10-24 20:00 | 2026-10-24 20:15
99 | 2 | B2-36 | Source | Stop applications – FCC Section (FSCM); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 1 device(s): 0 physical, 1 LPAR, 0 VM | FCC Section | FSCM | Manoj Kumar T ¦ 9300331307 ¦ manojkumart@canarabank.com |  |  | FCC Group |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
100 | 2 | B2-37 | Source | Stop applications – TM Section Integrated Treasury Wing (Swift); confirm clean stop with SPOC. | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 20:00 | 20:15 |  |  |  | Open | B2-03 | Scope: 1 device(s): 0 physical, 1 LPAR, 0 VM | TM Section Integrated Treasury Wing | Swift | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com |  | SWIFT | SWIFT DOMESTIC ¦ Swapnil ¦ 9743605215 |  |  |  | 2026-10-24 20:00 | 2026-10-24 20:15
101 | 2 | B2-38 | Source | Stop databases (Core DB / DB roles on LPARs, RAC nodes, Hyper-V VMs) in the agreed sequence. | DB / Kyndryl Migration | 15 | 2026-10-24 | 2026-10-24 | 20:15 | 20:30 |  |  |  | Open | B2-05, B2-06, B2-07, B2-08, B2-09, B2-10, B2-11, B2-12, B2-13, B2-14, B2-15, B2-16, B2-17, B2-18, B2-19, B2-20, B2-21, B2-22, B2-23, B2-24, B2-25, B2-26, B2-27, B2-28, B2-29, B2-30, B2-31, B2-32, B2-33, B2-34, B2-35, B2-36, B2-37 | [10 empty] | 2026-10-24 20:15 | 2026-10-24 20:30
102 | 2 | B2-39 | Source | Shut down 198 AIX LPARs (VIOS last) and 155 Hyper-V VMs; verify all are down (Shutdown_Startup_Seq sheet). | AIX BAU / Virtualization | 60 | 2026-10-24 | 2026-10-24 | 20:30 | 21:30 |  |  |  | Open | B2-38 | Window is tight – see Risk Log R-07. | [9 empty] | 2026-10-24 20:30 | 2026-10-24 21:30
103 | 2 | B2-40 | Source | Power off physical servers/frames/IO drawers/HMC (137 rows) incl. UAT frames 78C7868/78C7848, x86 & Hyper-V hosts. | AIX BAU / Windows / Linux | 30 | 2026-10-24 | 2026-10-24 | 21:30 | 22:00 |  |  |  | Open | B2-39 | [10 empty] | 2026-10-24 21:30 | 2026-10-24 22:00
104 | 2 | B2-41 | Source | Validate all SAN hosts are down; shut down SVC clusters BLRDCSV3 (A5/A6) and BLRDCSV2 (K6/L5). | Storage / IBM | 60 | 2026-10-24 | 2026-10-24 | 22:00 | 23:00 |  |  |  | Open | B2-40 | [10 empty] | 2026-10-24 22:00 | 2026-10-24 23:00
105 | 2 | B2-42 | Source | Shut down IBM back-end storage: FS9500 PROD/FCPROD (A5/A6), FS7300 PROD01/PROD2/ARCHIVAL (D6), FS9500_SV2_FCPROD (D3), V7000 ARCHIVAL (B2), UAT storage FS7300_UAT_01 / FS9500_ARCH_01 / FS7000 (D2) and FS9150_UAT_01/02 (K6/L5). | Storage / IBM | 30 | 2026-10-24 | 2026-10-24 | 23:00 | 23:30 |  |  |  | Open | B2-41 | [10 empty] | 2026-10-24 23:00 | 2026-10-24 23:30
106 | 2 | B2-43 | Source | Shut down Hitachi storage: VSP E790 & OneBlock (F6), G350 & HNAS 5200 (F5). | Storage / Hitachi Vantara | 30 | 2026-10-24 | 2026-10-24 | 23:00 | 23:30 |  |  |  | Open | B2-41 | [10 empty] | 2026-10-24 23:00 | 2026-10-24 23:30
107 | 2 | B2-44 | Source | Shut down DCDLRACSTORAGE (F3), backup appliances (W6) and tape storage (S6). | Storage / Backup / Dell | 30 | 2026-10-24 | 2026-10-24 | 23:00 | 23:30 |  |  |  | Open | B2-41 | [10 empty] | 2026-10-24 23:00 | 2026-10-24 23:30
108 | 2 | B2-45 | Source | Shut down SAN: BLR128B-G7-SW1/SW2 (UAT) → BLRDCREP_64BG7_SW1/SW2 → DCX-BLR3SSWPC2111/2112 → BLR512B-G7-SW1 → DCX-BLR512B-1/2 (core last). | SAN / IBM | 30 | 2026-10-24 | 2026-10-25 | 23:30 | 0:00 |  |  |  | Open | B2-42, B2-43, B2-44 | [10 empty] | 2026-10-24 23:30 | 2026-10-25
109 | 2 | B2-46 | Source | Shut down ToR / rack network switches of Batch 2 racks (management access last). | Network / Bank | 30 | 2026-10-25 | 2026-10-25 | 0:00 | 0:30 |  |  |  | Open | B2-45 | [10 empty] | 2026-10-25 | 2026-10-25 00:30
110 | 2 | B2-47 | Source | Verify every Batch 2 device is powered off; record cabling, labels and photos; update Scope status. | Kyndryl Migration / Bank | 30 | 2026-10-25 | 2026-10-25 | 0:30 | 1:00 |  |  |  | Open | B2-46 | [9 empty] | Notify: Batch 2 down | 2026-10-25 00:30 | 2026-10-25 01:00
▸ Source – Royal handover, unracking, packing & loading
111 | 2 | B2-48 | Source | Royal handover. Unmount and pack 103 loose device; empty racks C1, X5, W6 go first (TR-2). | Royal International / Bank / Kyndryl | 180 | 2026-10-25 | 2026-10-25 | 0:30 | 3:30 |  |  |  | Open | B2-47 | [9 empty] | Handover to Royal | 2026-10-25 00:30 | 2026-10-25 03:30
112 | 2 | B2-49 | Source | Prepare 20 OEM-loaded racks (A1, A2, A5, A6, C2, C4, C5, C6, D1, D3, D6, K3, K2, K1, K4, K6, L5, D2, F7, K5) – secure devices, remove external cabling, OEM sign-off. | OEM Vendors (IBM / Dell / Hitachi) / Royal | 1080 | 2026-10-25 | 2026-10-25 | 0:30 | 18:30 |  |  |  | Open | B2-47 | [10 empty] | 2026-10-25 00:30 | 2026-10-25 18:30
113 | 2 | B2-50 | Source | Verify devices against scope; prepare gate passes and e-way bills for TR-2 … TR-2.13. | Kyndryl Migration / Bank | 240 | 2026-10-25 | 2026-10-25 | 1:30 | 5:30 |  |  |  | Open | B2-48 | [10 empty] | 2026-10-25 01:30 | 2026-10-25 05:30
▸ Transport & target receiving – per truck
114 | 2 | B2-51 | Source | Load & seal TR-2 – Racks: C1 (empty), W6 (empty), X5 (empty); loose: 2 SAN director/switch, 4 storage/backup/tape. Loose devices packed in 11 box(es) (1 box = 1×2U or 2×1U); Truck load 44.75/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 5:30 | 6:00 |  |  |  | Open | B2-50 | [8 empty] | TR-2 |  | 2026-10-25 05:30 | 2026-10-25 06:00
115 | 2 | B2-52 | Transit | Transport TR-2 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 6:00 | 8:00 |  |  |  | Open | B2-51 | [8 empty] | TR-2 | Notify command centre on departure & arrival | 2026-10-25 06:00 | 2026-10-25 08:00
116 | 2 | B2-53 | Target | TR-2: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 8:00 | 8:15 |  |  |  | Open | B2-52 | [8 empty] | TR-2 |  | 2026-10-25 08:00 | 2026-10-25 08:15
117 | 2 | B2-54 | Target | TR-2: position and fix racks at target (C1→C-08, W6→H-06, X5→J-07); connect PDUs. Empty racks first so loose devices can be re-racked. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 8:15 | 9:15 |  |  |  | Open | B2-53 | [8 empty] | TR-2 |  | 2026-10-25 08:15 | 2026-10-25 09:15
118 | 2 | B2-55 | Target | TR-2: unpack and mount 6 loose device(s) in mapped target rack-U (target racks: C-08, D-06, D-09, E-16). Wait for target rack(s) on TR-2.6. | Royal / Power-IT / Kyndryl Migration | 60 | 2026-10-25 | 2026-10-25 | 12:15 | 13:15 |  |  |  | Open | B2-54, B2-79 | [8 empty] | TR-2 |  | 2026-10-25 12:15 | 2026-10-25 13:15
119 | 2 | B2-56 | Source | Load & seal TR-2.1 – Racks: A1 (OEM loaded), A2 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 6:00 | 6:30 |  |  |  | Open | B2-50 | [8 empty] | TR-2.1 |  | 2026-10-25 06:00 | 2026-10-25 06:30
120 | 2 | B2-57 | Transit | Transport TR-2.1 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 6:30 | 8:30 |  |  |  | Open | B2-56 | [8 empty] | TR-2.1 | Notify command centre on departure & arrival | 2026-10-25 06:30 | 2026-10-25 08:30
121 | 2 | B2-58 | Target | TR-2.1: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 8:30 | 8:45 |  |  |  | Open | B2-57 | [8 empty] | TR-2.1 |  | 2026-10-25 08:30 | 2026-10-25 08:45
122 | 2 | B2-59 | Target | TR-2.1: position and fix racks at target (A1→G-13, A2→G-14); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 8:45 | 9:45 |  |  |  | Open | B2-58 | [8 empty] | TR-2.1 |  | 2026-10-25 08:45 | 2026-10-25 09:45
123 | 2 | B2-60 | Source | Load & seal TR-2.2 – Racks: A5 (OEM loaded), A6 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 6:30 | 7:00 |  |  |  | Open | B2-50 | [8 empty] | TR-2.2 |  | 2026-10-25 06:30 | 2026-10-25 07:00
124 | 2 | B2-61 | Transit | Transport TR-2.2 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 7:00 | 9:00 |  |  |  | Open | B2-60 | [8 empty] | TR-2.2 | Notify command centre on departure & arrival | 2026-10-25 07:00 | 2026-10-25 09:00
125 | 2 | B2-62 | Target | TR-2.2: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 9:00 | 9:15 |  |  |  | Open | B2-61 | [8 empty] | TR-2.2 |  | 2026-10-25 09:00 | 2026-10-25 09:15
126 | 2 | B2-63 | Target | TR-2.2: position and fix racks at target (A5→D-13, A6→C-12); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 9:15 | 10:15 |  |  |  | Open | B2-62 | [8 empty] | TR-2.2 |  | 2026-10-25 09:15 | 2026-10-25 10:15
127 | 2 | B2-64 | Source | Load & seal TR-2.3 – Racks: C2 (OEM loaded), C4 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 7:00 | 7:30 |  |  |  | Open | B2-50 | [8 empty] | TR-2.3 |  | 2026-10-25 07:00 | 2026-10-25 07:30
128 | 2 | B2-65 | Transit | Transport TR-2.3 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 7:30 | 9:30 |  |  |  | Open | B2-64 | [8 empty] | TR-2.3 | Notify command centre on departure & arrival | 2026-10-25 07:30 | 2026-10-25 09:30
129 | 2 | B2-66 | Target | TR-2.3: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 9:30 | 9:45 |  |  |  | Open | B2-65 | [8 empty] | TR-2.3 |  | 2026-10-25 09:30 | 2026-10-25 09:45
130 | 2 | B2-67 | Target | TR-2.3: position and fix racks at target (C2→G-15, C4→H-13); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 9:45 | 10:45 |  |  |  | Open | B2-66 | [8 empty] | TR-2.3 |  | 2026-10-25 09:45 | 2026-10-25 10:45
131 | 2 | B2-68 | Source | Load & seal TR-2.4 – Racks: C5 (OEM loaded), C6 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 7:30 | 8:00 |  |  |  | Open | B2-50 | [8 empty] | TR-2.4 |  | 2026-10-25 07:30 | 2026-10-25 08:00
132 | 2 | B2-69 | Transit | Transport TR-2.4 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 8:00 | 10:00 |  |  |  | Open | B2-68 | [8 empty] | TR-2.4 | Notify command centre on departure & arrival | 2026-10-25 08:00 | 2026-10-25 10:00
133 | 2 | B2-70 | Target | TR-2.4: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 10:00 | 10:15 |  |  |  | Open | B2-69 | [8 empty] | TR-2.4 |  | 2026-10-25 10:00 | 2026-10-25 10:15
134 | 2 | B2-71 | Target | TR-2.4: position and fix racks at target (C5→G-17, C6→H-17); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 10:15 | 11:15 |  |  |  | Open | B2-70 | [8 empty] | TR-2.4 |  | 2026-10-25 10:15 | 2026-10-25 11:15
135 | 2 | B2-72 | Source | Load & seal TR-2.5 – Racks: D1 (OEM loaded), D2 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 8:00 | 8:30 |  |  |  | Open | B2-50 | [8 empty] | TR-2.5 |  | 2026-10-25 08:00 | 2026-10-25 08:30
136 | 2 | B2-73 | Transit | Transport TR-2.5 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 8:30 | 10:30 |  |  |  | Open | B2-72 | [8 empty] | TR-2.5 | Notify command centre on departure & arrival | 2026-10-25 08:30 | 2026-10-25 10:30
137 | 2 | B2-74 | Target | TR-2.5: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 10:30 | 10:45 |  |  |  | Open | B2-73 | [8 empty] | TR-2.5 |  | 2026-10-25 10:30 | 2026-10-25 10:45
138 | 2 | B2-75 | Target | TR-2.5: position and fix racks at target (D1→H-15, D2→C-11); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 10:45 | 11:45 |  |  |  | Open | B2-74 | [8 empty] | TR-2.5 |  | 2026-10-25 10:45 | 2026-10-25 11:45
139 | 2 | B2-76 | Source | Load & seal TR-2.6 – Racks: D3 (OEM loaded), D6 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 8:30 | 9:00 |  |  |  | Open | B2-50 | [8 empty] | TR-2.6 |  | 2026-10-25 08:30 | 2026-10-25 09:00
140 | 2 | B2-77 | Transit | Transport TR-2.6 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 9:00 | 11:00 |  |  |  | Open | B2-76 | [8 empty] | TR-2.6 | Notify command centre on departure & arrival | 2026-10-25 09:00 | 2026-10-25 11:00
141 | 2 | B2-78 | Target | TR-2.6: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 11:00 | 11:15 |  |  |  | Open | B2-77 | [8 empty] | TR-2.6 |  | 2026-10-25 11:00 | 2026-10-25 11:15
142 | 2 | B2-79 | Target | TR-2.6: position and fix racks at target (D3→D-09, D6→C-07); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 11:15 | 12:15 |  |  |  | Open | B2-78 | [8 empty] | TR-2.6 |  | 2026-10-25 11:15 | 2026-10-25 12:15
143 | 2 | B2-80 | Source | Load & seal TR-2.7 – Racks: F7 (OEM loaded), K1 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 9:00 | 9:30 |  |  |  | Open | B2-50 | [8 empty] | TR-2.7 |  | 2026-10-25 09:00 | 2026-10-25 09:30
144 | 2 | B2-81 | Transit | Transport TR-2.7 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 9:30 | 11:30 |  |  |  | Open | B2-80 | [8 empty] | TR-2.7 | Notify command centre on departure & arrival | 2026-10-25 09:30 | 2026-10-25 11:30
145 | 2 | B2-82 | Target | TR-2.7: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 11:30 | 11:45 |  |  |  | Open | B2-81 | [8 empty] | TR-2.7 |  | 2026-10-25 11:30 | 2026-10-25 11:45
146 | 2 | B2-83 | Target | TR-2.7: position and fix racks at target (F7→F-15, K1→H-09); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 11:45 | 12:45 |  |  |  | Open | B2-82 | [8 empty] | TR-2.7 |  | 2026-10-25 11:45 | 2026-10-25 12:45
147 | 2 | B2-84 | Source | Load & seal TR-2.8 – Racks: K2 (OEM loaded), K3 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 9:30 | 10:00 |  |  |  | Open | B2-50 | [8 empty] | TR-2.8 |  | 2026-10-25 09:30 | 2026-10-25 10:00
148 | 2 | B2-85 | Transit | Transport TR-2.8 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 10:00 | 12:00 |  |  |  | Open | B2-84 | [8 empty] | TR-2.8 | Notify command centre on departure & arrival | 2026-10-25 10:00 | 2026-10-25 12:00
149 | 2 | B2-86 | Target | TR-2.8: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 12:00 | 12:15 |  |  |  | Open | B2-85 | [8 empty] | TR-2.8 |  | 2026-10-25 12:00 | 2026-10-25 12:15
150 | 2 | B2-87 | Target | TR-2.8: position and fix racks at target (K2→G-09, K3→H-08); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 12:15 | 13:15 |  |  |  | Open | B2-86 | [8 empty] | TR-2.8 |  | 2026-10-25 12:15 | 2026-10-25 13:15
151 | 2 | B2-88 | Source | Load & seal TR-2.9 – Racks: K4 (OEM loaded), K5 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 10:00 | 10:30 |  |  |  | Open | B2-50 | [8 empty] | TR-2.9 |  | 2026-10-25 10:00 | 2026-10-25 10:30
152 | 2 | B2-89 | Transit | Transport TR-2.9 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 10:30 | 12:30 |  |  |  | Open | B2-88 | [8 empty] | TR-2.9 | Notify command centre on departure & arrival | 2026-10-25 10:30 | 2026-10-25 12:30
153 | 2 | B2-90 | Target | TR-2.9: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 12:30 | 12:45 |  |  |  | Open | B2-89 | [8 empty] | TR-2.9 |  | 2026-10-25 12:30 | 2026-10-25 12:45
154 | 2 | B2-91 | Target | TR-2.9: position and fix racks at target (K4→G-08, K5→G-08); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 12:45 | 13:45 |  |  |  | Open | B2-90 | [8 empty] | TR-2.9 |  | 2026-10-25 12:45 | 2026-10-25 13:45
155 | 2 | B2-92 | Source | Load & seal TR-2.10 – Racks: K6 (OEM loaded), L5 (OEM loaded). Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 10:30 | 11:00 |  |  |  | Open | B2-50 | [8 empty] | TR-2.10 |  | 2026-10-25 10:30 | 2026-10-25 11:00
156 | 2 | B2-93 | Transit | Transport TR-2.10 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 11:00 | 13:00 |  |  |  | Open | B2-92 | [8 empty] | TR-2.10 | Notify command centre on departure & arrival | 2026-10-25 11:00 | 2026-10-25 13:00
157 | 2 | B2-94 | Target | TR-2.10: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 13:00 | 13:15 |  |  |  | Open | B2-93 | [8 empty] | TR-2.10 |  | 2026-10-25 13:00 | 2026-10-25 13:15
158 | 2 | B2-95 | Target | TR-2.10: position and fix racks at target (K6→G-20, L5→H-19); connect PDUs. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 13:15 | 14:15 |  |  |  | Open | B2-94 | [8 empty] | TR-2.10 |  | 2026-10-25 13:15 | 2026-10-25 14:15
159 | 2 | B2-96 | Source | Load & seal TR-2.11 – No racks; loose: 3 SAN director/switch, 19 storage/backup/tape. Loose devices packed in 45 box(es) (1 box = 1×2U or 2×1U); Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 11:00 | 11:30 |  |  |  | Open | B2-50 | [8 empty] | TR-2.11 |  | 2026-10-25 11:00 | 2026-10-25 11:30
160 | 2 | B2-97 | Transit | Transport TR-2.11 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 11:30 | 13:30 |  |  |  | Open | B2-96 | [8 empty] | TR-2.11 | Notify command centre on departure & arrival | 2026-10-25 11:30 | 2026-10-25 13:30
161 | 2 | B2-98 | Target | TR-2.11: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 13:30 | 13:45 |  |  |  | Open | B2-97 | [8 empty] | TR-2.11 |  | 2026-10-25 13:30 | 2026-10-25 13:45
162 | 2 | B2-99 | Target | TR-2.11: unpack and mount 22 loose device(s) in mapped target rack-U (target racks: C-05, C-08, D-06, E-01, E-02, F-16, G-20, H-19). Wait for target rack(s) on TR-2, TR-2.10. | Royal / Power-IT / Kyndryl Migration | 140 | 2026-10-25 | 2026-10-25 | 14:15 | 16:35 |  |  |  | Open | B2-98, B2-54, B2-95 | [8 empty] | TR-2.11 |  | 2026-10-25 14:15 | 2026-10-25 16:35
163 | 2 | B2-100 | Source | Load & seal TR-2.12 – No racks; loose: 10 storage/backup/tape, 29 server. Loose devices packed in 45 box(es) (1 box = 1×2U or 2×1U); Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 11:30 | 12:00 |  |  |  | Open | B2-50 | [8 empty] | TR-2.12 |  | 2026-10-25 11:30 | 2026-10-25 12:00
164 | 2 | B2-101 | Transit | Transport TR-2.12 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 12:00 | 14:00 |  |  |  | Open | B2-100 | [8 empty] | TR-2.12 | Notify command centre on departure & arrival | 2026-10-25 12:00 | 2026-10-25 14:00
165 | 2 | B2-102 | Target | TR-2.12: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 14:00 | 14:15 |  |  |  | Open | B2-101 | [8 empty] | TR-2.12 |  | 2026-10-25 14:00 | 2026-10-25 14:15
166 | 2 | B2-103 | Target | TR-2.12: unpack and mount 39 loose device(s) in mapped target rack-U (target racks: A-10, B-10, C-05, C-14, D-06, D-14, H-01, H-02, H-06, I-06, J-07, L-01 …). Wait for target rack(s) on TR-2. | Royal / Power-IT / Kyndryl Migration | 180 | 2026-10-25 | 2026-10-25 | 14:15 | 17:15 |  |  |  | Open | B2-102, B2-54 | [8 empty] | TR-2.12 |  | 2026-10-25 14:15 | 2026-10-25 17:15
167 | 2 | B2-104 | Source | Load & seal TR-2.13 – No racks; loose: 32 server, 4 network/security. Loose devices packed in 32 box(es) (1 box = 1×2U or 2×1U); Truck load 32/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 12:00 | 12:30 |  |  |  | Open | B2-50 | [8 empty] | TR-2.13 |  | 2026-10-25 12:00 | 2026-10-25 12:30
168 | 2 | B2-105 | Transit | Transport TR-2.13 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 12:30 | 14:30 |  |  |  | Open | B2-104 | [8 empty] | TR-2.13 | Notify command centre on departure & arrival | 2026-10-25 12:30 | 2026-10-25 14:30
169 | 2 | B2-106 | Target | TR-2.13: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 14:30 | 14:45 |  |  |  | Open | B2-105 | [8 empty] | TR-2.13 |  | 2026-10-25 14:30 | 2026-10-25 14:45
170 | 2 | B2-107 | Target | TR-2.13: unpack and mount 36 loose device(s) in mapped target rack-U (target racks: A-10, B-10, D-10, E-05, F-03, G-11, I-08, I-10, J-05, J-07, J-08, L-01 …). Wait for target rack(s) on TR-2. | Royal / Power-IT / Kyndryl Migration | 180 | 2026-10-25 | 2026-10-25 | 14:45 | 17:45 |  |  |  | Open | B2-106, B2-54 | [8 empty] | TR-2.13 |  | 2026-10-25 14:45 | 2026-10-25 17:45
▸ Target – installation, power-on & validation
171 | 2 | B2-108 | Target | Connect power, network and SAN cabling for racks, SAN directors and storage (TR-2 … TR-2.13); validate labels and paths. | Power-IT / Network / SAN | 360 | 2026-10-25 | 2026-10-25 | 17:45 | 23:45 |  |  |  | Open | B2-55, B2-59, B2-63, B2-67, B2-71, B2-75, B2-79, B2-83, B2-87, B2-91, B2-95, B2-99, B2-103, B2-107 | [10 empty] | 2026-10-25 17:45 | 2026-10-25 23:45
172 | 2 | B2-109 | Target | Power on ToR / rack network switches; verify uplinks and management network for frames, HMC, SVC and directors. | Network / Bank | 360 | 2026-10-25 | 2026-10-26 | 23:45 | 5:45 |  |  |  | Open | B2-108 | [10 empty] | 2026-10-25 23:45 | 2026-10-26 05:45
173 | 2 | B2-110 | Target | Power on SAN: DCX-BLR512B-1/2 → BLR512B-G7-SW1 → DCX-BLR3SSWPC2111/2112 → BLRDCREP_64BG7_SW1/SW2 → BLR128B-G7-SW1/SW2 (UAT). Verify ISLs to Batch 1 switch BLR512B-G7-SW2, fabric merge (no segmentation), principal switch. Zoning freeze stays. | SAN / IBM | 360 | 2026-10-26 | 2026-10-26 | 5:45 | 11:45 |  |  |  | Open | B2-109 | [9 empty] | Checkpoint: fabrics merged | 2026-10-26 05:45 | 2026-10-26 11:45
174 | 2 | B2-111 | Target | Verify UAT fabric: BLR128B-G7-SW1/SW2 ISLs to BLR512B-G7-SW1/SW2 and paths of UAT frames 78C7868/78C7848 to UAT storage and DCX-BLR512B-1/2. | SAN / Storage / Network / Royal | 360 | 2026-10-26 | 2026-10-26 | 11:45 | 17:45 |  |  |  | Open | B2-110 | [10 empty] | 2026-10-26 11:45 | 2026-10-26 17:45
175 | 2 | B2-112 | Target | Power on IBM back-end storage (FS9500, FS7300, FS9500_SV2_FCPROD, V7000, UAT FS7300/FS9500/FS7000/FS9150), then SVC clusters BLRDCSV3 and BLRDCSV2; verify cluster health. | Storage / IBM | 360 | 2026-10-26 | 2026-10-26 | 11:45 | 17:45 |  |  |  | Open | B2-110 | [10 empty] | 2026-10-26 11:45 | 2026-10-26 17:45
176 | 2 | B2-113 | Target | Power on Hitachi (VSP E790, OneBlock, G350, HNAS 5200), DCDLRACSTORAGE, backup appliances and tape storage S6. | Storage / Hitachi Vantara / Dell | 360 | 2026-10-26 | 2026-10-26 | 11:45 | 17:45 |  |  |  | Open | B2-110 | [10 empty] | 2026-10-26 11:45 | 2026-10-26 17:45
177 | 2 | B2-114 | Target | Validate management network for frames/HMC; power on Power frames (incl. UAT 78C7868/78C7848) and IO drawers; run frame health checks. | OEM Vendor (IBM) / AIX BAU | 360 | 2026-10-26 | 2026-10-26 | 17:45 | 23:45 |  |  |  | Open | B2-112, B2-113 | [10 empty] | 2026-10-26 17:45 | 2026-10-26 23:45
178 | 2 | B2-115 | Target | Bring up VIOS, then 198 AIX LPARs (Core CBS DB LPARs first); verify disks, multipath (both fabrics) and network. | AIX BAU | 360 | 2026-10-26 | 2026-10-27 | 23:45 | 5:45 |  |  |  | Open | B2-114 | [10 empty] | 2026-10-26 23:45 | 2026-10-27 05:45
179 | 2 | B2-116 | Target | Connect power, network and SAN cabling for loose x86 / Hyper-V / RAC servers (TR-2.12, TR-2.13). | Power-IT / Network / SAN | 60 | 2026-10-27 | 2026-10-27 | 5:45 | 6:45 |  |  |  | Open | B2-103, B2-107 | [10 empty] | 2026-10-27 05:45 | 2026-10-27 06:45
180 | 2 | B2-117 | Target | Power on x86 servers and Hyper-V hosts; bring up 155 VMs and RAC nodes; verify disks and network. | Windows / Linux / Virtualization | 60 | 2026-10-27 | 2026-10-27 | 6:45 | 7:45 |  |  |  | Open | B2-116, B2-112, B2-113 | [10 empty] | 2026-10-27 06:45 | 2026-10-27 07:45
181 | 2 | B2-118 | Target | Network connectivity checks for all Batch 2 servers (application, management, backup VLANs). | Network / Kyndryl Migration | 30 | 2026-10-27 | 2026-10-27 | 7:45 | 8:15 |  |  |  | Open | B2-115, B2-117 | [10 empty] | 2026-10-27 07:45 | 2026-10-27 08:15
182 | 2 | B2-119 | Target | Start databases (Core CBS DB first). | DB / Kyndryl Migration | 30 | 2026-10-27 | 2026-10-27 | 8:15 | 8:45 |  |  |  | Open | B2-118 | [10 empty] | 2026-10-27 08:15 | 2026-10-27 08:45
183 | 2 | B2-120 | Target | Re-establish DC→NDC replication: confirm inter-site DWDM/FCIP link, BLRDCREP ↔ BLRNDC fabric, then resume BLRDCSV3/BLRDCSV2 replication and DB replication. | Storage / Replication / Network | 30 | 2026-10-27 | 2026-10-27 | 8:45 | 9:15 |  |  |  | Open | B2-119 | [10 empty] | 2026-10-27 08:45 | 2026-10-27 09:15
184 | 2 | B2-121 | Target | Start and validate applications – Data Center Operations Section (ITI); obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 162 device(s): 103 physical, 53 LPAR, 6 VM | Data Center Operations Section (ITI) | SFMS, DCO, CBS Allied Application, No application installed, Audit Vault Database Firewall, NCBS RAC, RAC DB, Middleware Hyper V Cluster, Tracs UAT DB, PeopleSoft HRMS (+11 more) | Rajeev ¦ rajeevkumar.j@canarabank.com, DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com, Sangeetha ¦ sangeetha_r@canarabank.com, Debjoy - 9874753518 ¦ debjoyroy@canarabank.com (+4 more) | [6 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
185 | 2 | B2-122 | Target | Start and validate applications – CBS(UTKARSH); obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 62 device(s): 0 physical, 62 LPAR, 0 VM | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com, VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | [6 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
186 | 2 | B2-123 | Target | Start and validate applications – EWIRM Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 44 device(s): 14 physical, 0 LPAR, 30 VM | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com |  | M/s Kyndryl, M/s SAS Institute India Pvt. Ltd | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com, Naga Sai ¦ 8074105412 ¦ puttanagasaikumar@kyndryl.com, Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
187 | 2 | B2-124 | Target | Start and validate applications – Online Banking Technology Net banking Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 29 device(s): 1 physical, 24 LPAR, 4 VM | Online Banking Technology Net banking Section | OFFLINE OTP, OBDX, OBT NET Banking Section - Report Server, OBT NET Banking Server - Jenkins Server, PKI, GIFTCITY OBDX | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com, RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com, RAGHURAM ¦ 8908226867 ¦ RAGHURAMP@canarabank.com, VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com |  | MANIPAL TECHNOLOGY, OFSS, AROOT TECHNOLOGY | SUBRAMANIYAM ¦ 9741797150 ¦ offlineotp@canarabank.com, RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com, RAGHAV ¦ raghavendra.shivaram@oracle.com (+1 more) |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
188 | 2 | B2-125 | Target | Start and validate applications – Digital Lending and LAPS Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 21 device(s): 0 physical, 10 LPAR, 11 VM | Digital Lending and LAPS Section | CORPORATE LOAN MODULE, GST SAHAY, LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com |  | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
189 | 2 | B2-126 | Target | Start and validate applications – SPMS; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 18 device(s): 0 physical, 0 LPAR, 18 VM | SPMS | CRM, Portal, DOCUMENT MANAGEMENT SYSTEM, Queue Management System, SPMS | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com, Gururaj Pamidi ¦ 9535105108 ¦ gururajnaidu.pamidi@kyndryl.com /Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com, Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com, Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com (+2 more) |  | TechMatrix consulting pvt ltd, OSPYN, M/s AurionPro, M/s BoardPAC | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com, Manoj ¦ 9703145556 ¦ manoj.m@ospyn.com, sajeev/manoj ¦ 94892029040/9703145556 ¦ DOCMGMTSYS@GMAIL.COM (+2 more) |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
190 | 2 | B2-127 | Target | Start and validate applications – Government Business and Financial Inclusion Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 17 device(s): 9 physical, 7 LPAR, 1 VM | Government Business and Financial Inclusion Section | Aadhaar seeding through web, SFMS, FI, DC Aadhar Vault DB, DB server, EKYC, TAB, DB, CEDGE | arundhatikatolkar@canarabank.com, LEEMA ROSELIN K 9741644668, Kiran B R ¦ 7619453224 ¦ figsupport@canarabank.com & kiranbr@integramicro.co.in & hoditfimb@canarabank.com |  | Integra Micro Systems Pvt Ltd | Kiran B R ¦ 7619453224 ¦ kiranbr@integramicro.co.in & figsupport@canarabank.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
191 | 2 | B2-128 | Target | Start and validate applications – FCUBS; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 16 device(s): 0 physical, 15 LPAR, 1 VM | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com, Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com / PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com, Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  | SUNIL KASHIKAR, MADHAVI GEDELA, Karthik Manoharan | 9900139448 ¦ sunilr.kashikar@kyndryl.com, 6304027118 ¦ madhavi.gedela@kiya.ai, +91 8147387273 ¦ mk@wecodee.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
192 | 2 | B2-129 | Target | Start and validate applications – To Be Confirmed; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 15 device(s): 0 physical, 7 LPAR, 8 VM | To Be Confirmed | [8 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
193 | 2 | B2-130 | Target | Start and validate applications – HRMS Technical Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 15 device(s): 0 physical, 0 LPAR, 15 VM | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com |  | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
194 | 2 | B2-131 | Target | Start and validate applications – Canara Collection and Payment Services Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 13 device(s): 0 physical, 0 LPAR, 13 VM | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com, Rajesh A, Kengal Veerendra Patil ¦ 7810073373/9880283138 ¦ hoccmssection@canarabank.com/hoccpstech@canarabank.com |  | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com, Naveen/Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
195 | 2 | B2-132 | Target | Start and validate applications – Software Project Management Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 12 device(s): 0 physical, 0 LPAR, 12 VM | Software Project Management Section |  | THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com, Vijey/Ankit ¦ 9487691736/7038831744 ¦ hotoncbs@canarabank.com;vijeyvr@canarabank.com;ankitsr@canarabank.com, Saket/Gaurav Baberwal, Vijey/Ankit |  | Ms Apmosys Technologies Pvt Ltd | Nandiratha ¦ 9938184406 ¦ rpasupport@canarabank.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
196 | 2 | B2-133 | Target | Start and validate applications – Online Banking Technology Mobile Banking; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 11 device(s): 1 physical, 5 LPAR, 5 VM | Online Banking Technology Mobile Banking | MOBILE BANKING, IMPS, UPI, MB | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com, NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com, Arjun ¦ 9952404855 ¦ hotomb@canarabank.com |  | NPST (Development), NPST | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com, Anandababu ¦ 7975771359 ¦ anandababu.m@npstx.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
197 | 2 | B2-134 | Target | Start and validate applications – ATM Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 8 device(s): 0 physical, 0 LPAR, 8 VM | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | [6 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
198 | 2 | B2-135 | Target | Start and validate applications – IIB(DCA); obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 8 device(s): 0 physical, 8 LPAR, 0 VM | IIB(DCA) | IIB/ACE/ESB | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | [6 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
199 | 2 | B2-136 | Target | Start and validate applications – Service Unit Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 5 device(s): 4 physical, 0 LPAR, 1 VM | Service Unit Section | RTGS, SFMS | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com, DEBJOY ROY ¦ 9874753518 ¦ AAQ_CanaraBank_NEFT_RTGS.xlsx |  | IFTAS | IFTAS (RBI SUBSIDIARY ) ¦ 914047524085 ¦ sfms.team@iftas.in |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
200 | 2 | B2-137 | Target | Start and validate applications – API Banking Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 5 device(s): 0 physical, 0 LPAR, 5 VM | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com |  | Comportement Software Private Limited, Digital API Craft | Murali ¦ 9880041498 ¦ murali@comportement.in, Sandeep Kenkare Satya Janardhana ¦ 9886236345 ¦ sandeep.k@digitalapi.ai, DCM ¦ DCM |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
201 | 2 | B2-138 | Target | Start and validate applications – Fintech Engagement & Partnership Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 4 device(s): 0 physical, 0 LPAR, 4 VM | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com |  | M/S Olive Crypto Systems Pvt Ltd | Sunil Kumar Lokanadam ¦ 917893603440 ¦ sunil.l@olivecrypto.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
202 | 2 | B2-139 | Target | Start and validate applications – FCR Deposits Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 3 device(s): 1 physical, 0 LPAR, 2 VM | FCR Deposits Section | RAC DB, CKYC | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com |  | ADROIT | SAKTHIVEL ¦ 9688969398 ¦ sakthiveli' <sakthiveli@adroitcorporate.com> |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
203 | 2 | B2-140 | Target | Start and validate applications – Data Warehouse Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 1 physical, 1 LPAR, 0 VM | Data Warehouse Section | Data Warehouse | [7 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
204 | 2 | B2-141 | Target | Start and validate applications – Network Administration Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 2 physical, 0 LPAR, 0 VM | Network Administration Section | NCCM | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com |  | Inspira | Inspira ¦ Inspira ¦ nmssupport@canarabank.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
205 | 2 | B2-142 | Target | Start and validate applications – Government Business Module (GBM) IT Hub -New delhI; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 0 physical, 2 LPAR, 0 VM | Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | DBA Team | [6 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
206 | 2 | B2-143 | Target | Start and validate applications – Online Banking Technology UPI and INFRA Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 0 physical, 2 LPAR, 0 VM | Online Banking Technology UPI and INFRA Section | UPI DB | [7 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
207 | 2 | B2-144 | Target | Start and validate applications – Compliance Department section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | Compliance Department section | Compliance Kartavya | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com |  | Alphaplus Technologies | Phani Kumar N ¦ 9182989492 ¦ phani@alphaplustech.com,apt.projects@alphaplustech.com, apt.projects-technical@alphaplustech.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
208 | 2 | B2-145 | Target | Start and validate applications – Compliance Department; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | Compliance Department | Compliance Kartavya | [7 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
209 | 2 | B2-146 | Target | Start and validate applications – Online Banking Technology Mobile Banking,Digital Banking Wing; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com |  | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
210 | 2 | B2-147 | Target | Start and validate applications – DPSecure; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 2 device(s): 0 physical, 0 LPAR, 2 VM | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com |  | Landmark Solutions | Ajikya Hatim ¦ 9768524076 ¦ ajinkya@lsssoftware.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
211 | 2 | B2-148 | Target | Start and validate applications – Application Development Section (In House) (ADM); obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Application Development Section (In House) (ADM) | ADM | Debarun, Yogesh ¦ 9398989380 ¦ yogeshsai@canarabank.com | [6 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
212 | 2 | B2-149 | Target | Start and validate applications – CTS; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | CTS | DEM | Shakti Narayan Gupta,Bhupesh Piplani,7975142177/9650976622,hoditcts@canarabank.com |  |  | In-House (ADM),ADM Team, IT Vertical,hoditadm@canarabank.com,NCR,NCR,9535040604,sharathkumar.manvi@ncratleos.com |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
213 | 2 | B2-150 | Target | Start and validate applications – New Initiatives-Technology Innovation Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | New Initiatives-Technology Innovation Section | [8 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
214 | 2 | B2-151 | Target | Start and validate applications – Online Banking Technology Mobile Banking Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 1 device(s): 0 physical, 0 LPAR, 1 VM | Online Banking Technology Mobile Banking Section | [8 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
215 | 2 | B2-152 | Target | Start and validate applications – FCC Section; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 1 device(s): 0 physical, 1 LPAR, 0 VM | FCC Section | FSCM | Manoj Kumar T ¦ 9300331307 ¦ manojkumart@canarabank.com |  |  | FCC Group |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
216 | 2 | B2-153 | Target | Start and validate applications – TM Section Integrated Treasury Wing; obtain SPOC sign-off. | Application / DB / Vendor Teams | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | Scope: 1 device(s): 0 physical, 1 LPAR, 0 VM | TM Section Integrated Treasury Wing | Swift | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com |  | SWIFT | SWIFT DOMESTIC ¦ Swapnil ¦ 9743605215 |  |  |  | 2026-10-27 08:45 | 2026-10-27 20:45
217 | 2 | B2-154 | Target | Test backups: tape libraries L1/L2/L3 (via DCX-BLR512B-1/2), S6 and Data Domain / backup appliances. | Backup / Storage | 720 | 2026-10-27 | 2026-10-27 | 8:45 | 20:45 |  |  |  | Open | B2-119 | [10 empty] | 2026-10-27 08:45 | 2026-10-27 20:45
218 | 2 | B2-155 | Target | Restore monitoring, complete batch validation and hand over to BAU / DCM. | Migration / BAU / Bank | 30 | 2026-10-27 | 2026-10-27 | 20:45 | 21:15 |  |  |  | Open | B2-121, B2-122, B2-123, B2-124, B2-125, B2-126, B2-127, B2-128, B2-129, B2-130, B2-131, B2-132, B2-133, B2-134, B2-135, B2-136, B2-137, B2-138, B2-139, B2-140, B2-141, B2-142, B2-143, B2-144, B2-145, B2-146, B2-147, B2-148, B2-149, B2-150, B2-151, B2-152, B2-153, B2-120, B2-154 | [9 empty] | Notify: Batch 2 complete | 2026-10-27 20:45 | 2026-10-27 21:15
BATCH 3 – STANDALONE (NO SAN): SERVERS, OBJECT STORAGE, NETWORK & SECURITY ¦ 24–25/10/2026 ¦ TR-3 … TR-3.3
▸ Source – controlled shutdown (downtime from 22:00)
219 | 3 | B3-01 | Source | Stop applications / services – Data Center Operations Section (ITI) (DCO). | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 22:00 | 22:15 |  |  |  | Open | B2-02 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Data Center Operations Section (ITI) | DCO | [7 empty] | 2026-10-24 22:00 | 2026-10-24 22:15
220 | 3 | B3-02 | Source | Stop applications / services – Service Unit Section (apps TBC). | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 22:00 | 22:15 |  |  |  | Open | B2-02 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Service Unit Section | [8 empty] | 2026-10-24 22:00 | 2026-10-24 22:15
221 | 3 | B3-03 | Source | Stop applications / services – Data Warehouse Section (Data Warehouse). | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 22:00 | 22:15 |  |  |  | Open | B2-02 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Data Warehouse Section | Data Warehouse | [7 empty] | 2026-10-24 22:00 | 2026-10-24 22:15
222 | 3 | B3-04 | Source | Stop applications / services – Online Banking Technology Net banking Section (WEB-OTP). | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 22:00 | 22:15 |  |  |  | Open | B2-02 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Online Banking Technology Net banking Section | WEB-OTP |  |  |  | To Be Confirmed |  |  |  | 2026-10-24 22:00 | 2026-10-24 22:15
223 | 3 | B3-05 | Source | Stop applications / services – TM Section Integrated Treasury Wing (Swift). | Application / BAU / Vendor Teams | 15 | 2026-10-24 | 2026-10-24 | 22:00 | 22:15 |  |  |  | Open | B2-02 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | TM Section Integrated Treasury Wing | Swift | Gambhirya Lokhande ¦ 7558713822 ¦ gambhiryatejrao@canarabank.com | [6 empty] | 2026-10-24 22:00 | 2026-10-24 22:15
224 | 3 | B3-06 | Source | Power off standalone servers (5 rows): CAN-DC-CELL7, DCDBSYNFRS, Server-8284-22A-SN84B6FAW, drswift02, UATWEB-OTP. | Windows / Linux / BAU | 15 | 2026-10-24 | 2026-10-24 | 22:15 | 22:30 |  |  |  | Open | B3-01, B3-02, B3-03, B3-04, B3-05 | [10 empty] | 2026-10-24 22:15 | 2026-10-24 22:30
225 | 3 | B3-07 | Source | Shut down object / storage servers (32 rows, racks W3/W4/W5/W7). | Storage / Dell | 15 | 2026-10-24 | 2026-10-24 | 23:00 | 23:15 |  |  |  | Open | B3-06 | [10 empty] | 2026-10-24 23:00 | 2026-10-24 23:15
226 | 3 | B3-08 | Source | Shut down network & security (80 rows: core, DMZ, firewalls, routers, NW servers) – core uplinks last, after Batch 2 network (B2 network step). | Network / Bank | 15 | 2026-10-24 | 2026-10-25 | 23:45 | 0:00 |  |  |  | Open | B3-07 | Core network shutdown affects management access – Risk Log R-09. | [9 empty] | 2026-10-24 23:45 | 2026-10-25
227 | 3 | B3-09 | Source | Verify every Batch 3 device is powered off; record cabling, labels and photos. | Kyndryl Migration / Bank | 15 | 2026-10-25 | 2026-10-25 | 0:00 | 0:15 |  |  |  | Open | B3-08 | [9 empty] | Notify: Batch 3 down | 2026-10-25 | 2026-10-25 00:15
▸ Source – Royal handover, unracking, packing & loading
228 | 3 | B3-10 | Source | Royal handover. Unmount and pack 117 loose device rows; empty racks W3, W4, W5 go first (TR-3). | Royal International / Bank / Kyndryl | 120 | 2026-10-25 | 2026-10-25 | 9:30 | 11:30 |  |  |  | Open | B3-09 | [9 empty] | Handover to Royal | 2026-10-25 09:30 | 2026-10-25 11:30
229 | 3 | B3-11 | Source | Prepare empty Dell racks W3, W4, W5 for transport once all devices are unracked (OEM sign-off). | OEM Vendor (Dell) / Royal | 120 | 2026-10-25 | 2026-10-25 | 11:30 | 13:30 |  |  |  | Open | B3-09 | [10 empty] | 2026-10-25 11:30 | 2026-10-25 13:30
230 | 3 | B3-12 | Source | Verify devices against scope; prepare gate passes and e-way bills for TR-3 … TR-3.3. | Kyndryl Migration / Bank | 30 | 2026-10-25 | 2026-10-25 | 10:30 | 11:00 |  |  |  | Open | B3-10 | [10 empty] | 2026-10-25 10:30 | 2026-10-25 11:00
▸ Transport & target receiving – per truck
231 | 3 | B3-13 | Source | Load & seal TR-3 – Racks: W3 (empty), W4 (empty), W5 (empty); loose: 11 storage/backup/tape, 1 server. Loose devices packed in 11 box(es) (1 box = 1×2U or 2×1U); Truck load 44.75/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 11:00 | 11:30 |  |  |  | Open | B3-12 | [8 empty] | TR-3 |  | 2026-10-25 11:00 | 2026-10-25 11:30
232 | 3 | B3-14 | Transit | Transport TR-3 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 11:30 | 13:30 |  |  |  | Open | B3-13 | [8 empty] | TR-3 | Notify command centre on departure & arrival | 2026-10-25 11:30 | 2026-10-25 13:30
233 | 3 | B3-15 | Target | TR-3: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 13:30 | 13:45 |  |  |  | Open | B3-14 | [8 empty] | TR-3 |  | 2026-10-25 13:30 | 2026-10-25 13:45
234 | 3 | B3-16 | Target | TR-3: position and fix racks at target (W3→G-05, W4→G-04, W5→G-03); connect PDUs. Empty racks first so loose devices can be re-racked. | Royal / STT / Power-IT | 60 | 2026-10-25 | 2026-10-25 | 13:45 | 14:45 |  |  |  | Open | B3-15 | [8 empty] | TR-3 |  | 2026-10-25 13:45 | 2026-10-25 14:45
235 | 3 | B3-17 | Target | TR-3: unpack and mount 12 loose device(s) in mapped target rack-U (target racks: D-14, G-04, G-05, NA). | Royal / Power-IT / Kyndryl Migration | 90 | 2026-10-25 | 2026-10-25 | 14:45 | 16:15 |  |  |  | Open | B3-16 | [8 empty] | TR-3 |  | 2026-10-25 14:45 | 2026-10-25 16:15
236 | 3 | B3-18 | Source | Load & seal TR-3.1 – No racks; loose: 21 storage/backup/tape, 4 server, 12 network/security. Loose devices packed in 45 box(es) (1 box = 1×2U or 2×1U); Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 11:30 | 12:00 |  |  |  | Open | B3-12 | [8 empty] | TR-3.1 |  | 2026-10-25 11:30 | 2026-10-25 12:00
237 | 3 | B3-19 | Transit | Transport TR-3.1 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 12:00 | 14:00 |  |  |  | Open | B3-18 | [8 empty] | TR-3.1 | Notify command centre on departure & arrival | 2026-10-25 12:00 | 2026-10-25 14:00
238 | 3 | B3-20 | Target | TR-3.1: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 14:00 | 14:15 |  |  |  | Open | B3-19 | [8 empty] | TR-3.1 |  | 2026-10-25 14:00 | 2026-10-25 14:15
239 | 3 | B3-21 | Target | TR-3.1: unpack and mount 37 loose device(s) in mapped target rack-U (target racks: D-10, E-07, E-08, F-07, F-08, F-09, G-03, G-04, H-05, I-06, K-08, OOS …). Wait for target rack(s) on TR-3. | Royal / Power-IT / Kyndryl Migration | 180 | 2026-10-25 | 2026-10-25 | 14:45 | 17:45 |  |  |  | Open | B3-20, B3-16 | [8 empty] | TR-3.1 |  | 2026-10-25 14:45 | 2026-10-25 17:45
240 | 3 | B3-22 | Source | Load & seal TR-3.2 – No racks; loose: 27 network/security. Loose devices packed in 45 box(es) (1 box = 1×2U or 2×1U); Truck load 45/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 12:00 | 12:30 |  |  |  | Open | B3-12 | [8 empty] | TR-3.2 |  | 2026-10-25 12:00 | 2026-10-25 12:30
241 | 3 | B3-23 | Transit | Transport TR-3.2 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 12:30 | 14:30 |  |  |  | Open | B3-22 | [8 empty] | TR-3.2 | Notify command centre on departure & arrival | 2026-10-25 12:30 | 2026-10-25 14:30
242 | 3 | B3-24 | Target | TR-3.2: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 14:30 | 14:45 |  |  |  | Open | B3-23 | [8 empty] | TR-3.2 |  | 2026-10-25 14:30 | 2026-10-25 14:45
243 | 3 | B3-25 | Target | TR-3.2: unpack and mount 27 loose device(s) in mapped target rack-U (target racks: E-06, E-07, E-08, E-09, E-11, F-05, F-07, F-09, F-11, F-12, TBD). | Royal / Power-IT / Kyndryl Migration | 165 | 2026-10-25 | 2026-10-25 | 14:45 | 17:30 |  |  |  | Open | B3-24 | [8 empty] | TR-3.2 |  | 2026-10-25 14:45 | 2026-10-25 17:30
244 | 3 | B3-26 | Source | Load & seal TR-3.3 – No racks; loose: 41 network/security. Loose devices packed in 27 box(es) (1 box = 1×2U or 2×1U); Truck load 27/45 boxes. Verify against Truck_Load_Plan. | Royal International / Bank / Kyndryl | 30 | 2026-10-25 | 2026-10-25 | 12:30 | 13:00 |  |  |  | Open | B3-12 | [8 empty] | TR-3.3 |  | 2026-10-25 12:30 | 2026-10-25 13:00
245 | 3 | B3-27 | Transit | Transport TR-3.3 from ITI to STT (gate pass / e-way bill / seal no. in Truck_Tracker). | Royal International | 120 | 2026-10-25 | 2026-10-25 | 13:00 | 15:00 |  |  |  | Open | B3-26 | [8 empty] | TR-3.3 | Notify command centre on departure & arrival | 2026-10-25 13:00 | 2026-10-25 15:00
246 | 3 | B3-28 | Target | TR-3.3: inward gate pass, unloading, security verification and physical check against packing list. | Royal / STT / Bank / Kyndryl | 15 | 2026-10-25 | 2026-10-25 | 15:00 | 15:15 |  |  |  | Open | B3-27 | [8 empty] | TR-3.3 |  | 2026-10-25 15:00 | 2026-10-25 15:15
247 | 3 | B3-29 | Target | TR-3.3: unpack and mount 41 loose device(s) in mapped target rack-U (target racks: E-11, E-12, F-11, G-03, G-04, G-05, H-05, H-06, H-10, H-11, N/W). Wait for target rack(s) on TR-3. | Royal / Power-IT / Kyndryl Migration | 180 | 2026-10-25 | 2026-10-25 | 15:15 | 18:15 |  |  |  | Open | B3-28, B3-16 | [8 empty] | TR-3.3 |  | 2026-10-25 15:15 | 2026-10-25 18:15
▸ Target – installation, power-on & validation
248 | 3 | B3-30 | Target | Connect power, network cabling; validate labels and paths. | Power-IT / Network | 120 | 2026-10-25 | 2026-10-25 | 18:15 | 20:15 |  |  |  | Open | B3-17, B3-21, B3-25, B3-29 | [10 empty] | 2026-10-25 18:15 | 2026-10-25 20:15
249 | 3 | B3-31 | Target | Power on network & security (core, DMZ, firewalls, routers); verify routing, HA pairs and policies. | Network / Bank | 90 | 2026-10-25 | 2026-10-25 | 20:15 | 21:45 |  |  |  | Open | B3-30 | [10 empty] | 2026-10-25 20:15 | 2026-10-25 21:45
250 | 3 | B3-32 | Target | Power on standalone servers and object / storage servers; verify OS, network and services. | Windows / Linux / Storage | 60 | 2026-10-25 | 2026-10-25 | 21:45 | 22:45 |  |  |  | Open | B3-31 | [10 empty] | 2026-10-25 21:45 | 2026-10-25 22:45
251 | 3 | B3-33 | Target | Start and validate services – Data Center Operations Section (ITI); obtain SPOC sign-off. | Application / Network / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 22:45 | 10:45 |  |  |  | Open | B3-32 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Data Center Operations Section (ITI) | DCO | [7 empty] | 2026-10-25 22:45 | 2026-10-26 10:45
252 | 3 | B3-34 | Target | Start and validate services – Service Unit Section; obtain SPOC sign-off. | Application / Network / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 22:45 | 10:45 |  |  |  | Open | B3-32 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Service Unit Section | [8 empty] | 2026-10-25 22:45 | 2026-10-26 10:45
253 | 3 | B3-35 | Target | Start and validate services – Data Warehouse Section; obtain SPOC sign-off. | Application / Network / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 22:45 | 10:45 |  |  |  | Open | B3-32 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Data Warehouse Section | Data Warehouse | [7 empty] | 2026-10-25 22:45 | 2026-10-26 10:45
254 | 3 | B3-36 | Target | Start and validate services – Online Banking Technology Net banking Section; obtain SPOC sign-off. | Application / Network / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 22:45 | 10:45 |  |  |  | Open | B3-32 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | Online Banking Technology Net banking Section | WEB-OTP |  |  |  | To Be Confirmed |  |  |  | 2026-10-25 22:45 | 2026-10-26 10:45
255 | 3 | B3-37 | Target | Start and validate services – TM Section Integrated Treasury Wing; obtain SPOC sign-off. | Application / Network / Vendor Teams | 720 | 2026-10-25 | 2026-10-26 | 22:45 | 10:45 |  |  |  | Open | B3-32 | Scope: 1 device(s): 1 physical, 0 LPAR, 0 VM | TM Section Integrated Treasury Wing | Swift | Gambhirya Lokhande ¦ 7558713822 ¦ gambhiryatejrao@canarabank.com | [6 empty] | 2026-10-25 22:45 | 2026-10-26 10:45
256 | 3 | B3-38 | Target | Restore monitoring, complete batch validation and hand over to BAU / DCM. | Migration / BAU / Bank | 30 | 2026-10-26 | 2026-10-26 | 10:45 | 11:15 |  |  |  | Open | B3-33, B3-34, B3-35, B3-36, B3-37 | [9 empty] | Notify: Batch 3 complete | 2026-10-26 10:45 | 2026-10-26 11:15
POST-MIGRATION
257 | Post | PM-01 | Target | Hypercare – monitor all migrated workloads; track issues in Issue Log. | Kyndryl Migration / BAU | 2880 | 2026-10-27 | 2026-10-29 | 21:15 | 21:15 |  |  |  | Open | B1-60, B2-155, B3-38 | [10 empty] | 2026-10-27 21:15 | 2026-10-29 21:15
258 | Post | PM-02 | Target | Update CMDB / inventory with target rack-U positions; close change records. | Kyndryl Migration / Bank | 120 | 2026-10-27 | 2026-10-27 | 21:15 | 23:15 |  |  |  | Open | B1-60, B2-155, B3-38 | [10 empty] | 2026-10-27 21:15 | 2026-10-27 23:15
259 | Post | PM-03 | Source/Target | Lessons-learnt session and runbook closure. | Kyndryl Migration / Bank | 60 | 2026-10-29 | 2026-10-29 | 21:15 | 22:15 |  |  |  | Open | PM-01 | [10 empty] | 2026-10-29 21:15 | 2026-10-29 22:15
Formulas:
Planned End Date = INT(ROUND(([Planned Start Date]+[Planned Start Time]+[Planned Duration (Minutes)]/1440)*1440,0)/1440)
Planned Start (Date-Time) = [Planned Start Date]+[Planned Start Time]
Planned Start Date = [Planned Start Date, row above]
Planned Start Date = INT(ROUND(MAX([Planned End Date, row above]+[Planned End Time, row above])*1440,0)/1440)
Planned End (Date-Time) = [Planned End Date]+[Planned End Time]
Note on H4: Anchor tasks hold fixed dates (bold blue). Others = MAX(end of Dependencies).

## Scope_Devices
SN | Record Type | HW Type | Hostname | Physical Host (Base Machine) | Movement Batch | Truck No | Transport Mode | Shutdown Date | Shutdown Time | Migration Date | Royal Handover Time | Truck Movement Time | Device Primary Serial Number | Device Sub Serial Number | CBS/Non-CBS | Environment | App Owner Group | Application Name | Application Bank SPOC | Application Vendor Name | Application Vendor Contact | Criticality | Device Type | Device Role | OEM Make | Device Model | x86 / IBM Power | OS Type | OS Version | Internal IP | Management IP (ILO) | VLAN Name | NW Zone | DC Location | Floor | Source Rack | Source U Position | Device U Size | Source Rack Moving (Y/N) | Target Row | Target Rack | Target U Position | Equivalent Source Rack | SAN Connected | SAN Switches (Batch) | Fabric Coverage | OEM (Yes/No) | OEMs | OEM Contacts | HW Vendor | W2W Power Status | Device Status | Inscope | Scrap / OOS Flag | Movement Reason | Shutdown Status | Migration Status | Remarks
1 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | 3BD40HH | CBS | UAT | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 and 1 | IBM Power | AIX | 7.3 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C2 | 16-12 | 5 | Y | G | G-15 | 14-18 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
2 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | 3BDT40HL | CBS | UAT | Data Center Operations Section (ITI) | SFMS |  |  |  | High | SERVER | To Be Confirmed | IBM | FC ENZO | X86 | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | DC1 | 1 | C2 | 26-22 | 5 | Y | G | G-15 | 4-8 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
3 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | 3BDT40HJ | CBS | UAT | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C2 | 21-17 | 5 | Y | G | G-15 | 9-13 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
4 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | WZS03B6 | CBS | UAT | Data Center Operations Section (ITI) | SFMS |  |  |  | High | IO Expansion Drawer | To Be Confirmed | IBM | FC ENZO | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C2 | 38-35 | 4 | Y | G | G-15 | 24-27 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
5 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | WZS039H | CBS | UAT | Data Center Operations Section (ITI) | SFMS |  |  |  | High | IO Expansion Drawer | To Be Confirmed | IBM | FC ENZO | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C2 | 34-31 | 4 | Y | G | G-15 | 28-31 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
6 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | WZS03B9 | CBS | UAT | Data Center Operations Section (ITI) | SFMS |  |  |  | High | IO Expansion Drawer | To Be Confirmed | IBM | FC ENZO | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C2 | 30-27 | 4 | Y | G | G-15 | 32-35 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
7 | Physical | Physical | Not Applicable |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 7:30 | FLM29290C0T | FLM29290C0T | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | C2 | 41 | 1 | Y | G | Spare | Spare | IBM rack (C2) | No |  |  | Yes | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
8 | Physical | Physical | Not Applicable |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 7:30 | FLM29290BRN | FLM29290BRN | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | C2 | 39 | 1 | Y | G | Spare | Spare | IBM rack (C2) | No |  |  | Yes | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
9 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | 78C7868 | CBS | UAT | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | High | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.3 | 10.32.209.164 | NA | HMC1_ATM_SWITCH | Internal | DC1 | 1 | C2 | 05-04U | 2 | Y | G | G-15 | 36-37 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | Not in production | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
10 | Physical | Physical | C2-9080-HEX-SN78C7868-UAT |  | 2 | TR-2.3 | Loaded in OEM rack C2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | 3BDT40HF | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C2 | 11-06 | 5 | Y | G | G-15 | 19-23 | IBM rack (C2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
11 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 00WZSO39F | CBS | UAT | Data Center Operations Section (ITI) | SFMS |  |  |  | High | IO Expansion Drawer | DB | IBM | FC ENZO | NA | NA | NA | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | D1 | 38-35 | 4 | Y | H | H-15 | 24-27 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
12 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 00WZSO3CY and 00WZSC2V1 | CBS | UAT | Data Center Operations Section (ITI) | SFMS |  |  |  | High | IO Expansion Drawer | DB | IBM | FC ENZO and 1 | NA | NA | NA | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | D1 | 34-31 | 4 | Y | H | H-15 | 28-31 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
13 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 00WZSC2V1 | CBS | UAT | Data Center Operations Section (ITI) | SFMS |  |  |  | High | IO Expansion Drawer | DB | IBM | FC ENZO | NA | NA | NA | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | D1 | 30-27 | 4 | Y | H | H-15 | 32-35 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
14 | Physical | Physical | Not Applicable |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 8:30 | FLM29290BVR | FLM29290BVR | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Network-Switch | DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | D1 | 41 | 1 | Y | H | H-10 | U18 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
15 | Physical | Physical | Not Applicable |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 8:30 | FLM29290GES | FLM29290GES | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Network-Switch | DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | D1 | 39 | 1 | Y | H | H-11 | U17 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
16 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 78C7848 | CBS | UAT | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | High | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.3 | 10.32.201.166 | NA | CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | D1 | 05-04 | 2 | Y | H | H-15 | 36-37 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | Not in production | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
17 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 00000FGD06FK | CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.3 | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | D1 | 26-22 | 5 | Y | H | H-15 | 4-8 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
18 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 00000FGD06DC | CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.3 | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | D1 | 21-17 | 5 | Y | H | H-15 | 9-13 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
19 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 00000FGD06AY | CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.3 | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | D1 | 16-12 | 5 | Y | H | H-15 | 14-18 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
20 | Physical | Physical | D1-9080-HEX-SN78C7848-UAT |  | 2 | TR-2.5 | Loaded in OEM rack D1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | 00000FGD06EC | CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.3 | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | D1 | 11-07 | 5 | Y | H | H-15 | 19-23 | IBM rack (D1) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
21 | Physical | Physical | BLR128B-G7-SW1 |  | 2 | TR-2.5 | Loaded in OEM rack D2 | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 8:30 | 787413W | 787413W | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Switch 64G | Storage | IBM | Brocade G730 | NA | Not Applicable | Not Applicable | 10.32.202.126 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | D2 | 39-40 | 2 | Y | C | C-11 | 23-24 | IBM Rack (D2) | Yes | BLR512B-G7-SW1 (B2) | switch | Yes | Lailesh to verify |  | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
22 | Physical | Physical | Not Applicable |  | 2 | TR-2.5 | Loaded in OEM rack D2 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 8:30 | 7813TC8 | 7813TC8 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | D2 | 17-18 | 2 | Y | C | C-11 | 9-10 | IBM Rack (D2) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
23 | Physical | Physical | Not Applicable |  | 2 | TR-2.5 | Loaded in OEM rack D2 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 8:30 | 7813TC5 | 7813TC5 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | D2 | 13-14 | 2 | Y | C | C-11 | 13-14 | IBM Rack (D2) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
24 | Physical | Physical | Not Applicable |  | 2 | TR-2.5 | Loaded in OEM rack D2 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 8:30 | 78E4Z5Z | 78E4Z5Z | CBS | UAT | Data Center Operations Section (ITI) | UATP10 Storage Boxes |  |  |  | High | Storage Controller | Storage | IBM | Flash System 9500 | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | D2 | 05-09 | 5 | Y | C | C-11 | 4-8 | IBM Rack (D2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
25 | Physical | Physical | Not Applicable |  | 2 | TR-2.5 | Loaded in OEM rack D2 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 8:30 | 78E3NYR | 78E3NYR | CBS | UAT | Data Center Operations Section (ITI) | UATP10 Storage Boxes |  |  |  | High | Storage Controller | Storage | IBM | FLASH SYSTEM 7300 | NA | Not Applicable | Not Applicable | 10.32.202.123 | 10.32.202.123 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | D2 | 15-16 | 2 | Y | C | C-11 | 11-12 | IBM Rack (D2) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | Not in production | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
26 | Physical | Physical | Not Applicable |  | 1 | TR-1 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 12:30 | 5ZWGVP3 | 5ZWGVP3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) |  |  |  |  | To Be Confirmed | Tape Library | To Be Confirmed | Dell | EMC ML3E | NA | Not Applicable | Not Applicable | 10.32.204.42 | NA | Non-CBS_STORAGE_MGMT | Internal | DC1 | 1 | D5 | 08-10 | 3 | Y | D | D-04 | 9-11 | WQ Rack (D5) | No |  |  | Yes | Non-OEMs |  | CITO INFOTECH PVT LTD | ON | ON | Yes |  | Tape libraries | Pending | Pending
27 | Physical | Physical | Not Applicable |  | 1 | TR-1 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 12:30 | H4XGVP3 | H4XGVP3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) |  |  |  |  | To Be Confirmed | Tape Library | To Be Confirmed | Dell | EMC ML3E | NA | Not Applicable | Not Applicable | 10.32.204.42 | NA | Non-CBS_STORAGE_MGMT | Internal | DC1 | 1 | D5 | 05-07 | 3 | Y | D | D-04 | 12-14 | WQ Rack (D5) | No |  |  | Yes | Non-OEMs |  | CITO INFOTECH PVT LTD | ON | ON | Yes |  | Tape libraries | Pending | Pending
28 | Physical | Physical | TAPEINV22 |  | 1 | TR-1.1 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 13:00 | 6G0HVP3 | 6G0HVP3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) |  |  |  |  | To Be Confirmed | Tape Library | To Be Confirmed | Dell | EMC ML3 | NA | Not Applicable | Not Applicable | 10.32.204.42 | NA | Non-CBS_STORAGE_MGMT | Internal | DC1 | 1 | D5 | 02-04 | 3 | Y | D | D-04 | 15-17 | WQ Rack (D5) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | Non-OEMs |  | CITO INFOTECH PVT LTD | ON | ON | Yes |  | Tape libraries | Pending | Pending
29 | Physical | Physical | Not Applicable |  | 1 | TR-1.1 | Loaded in OEM rack L1 | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 13:00 | 78BB816 | 78BB816 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Tape Library | Backup BaseBox | IBM | TS4500 | NA | Not Applicable | Not Applicable | 10.32.202.26 | NA | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | L1 | NA | NA | Y | C | C-01 |  | IBM LTO8 tape library (L1) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Not Applicable | Yes |  | Tape libraries | Pending | Pending
30 | Physical | Physical | Not Applicable |  | 1 | TR-1.2 | Loaded in OEM rack L2 | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 13:30 | 78DB196 | 78DB196 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Tape Library | Backup Expansion | IBM | TS4500 | NA | Not Applicable | Not Applicable | 10.32.202.26 | NA | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | L2 | NA | NA | Y | C | C-02 |  | IBM LTO8 tape library (L2) | No |  |  | Yes | Lailesh to verify |  | IBM INDIA PVT LTD | ON | Not Applicable | Yes |  | Tape libraries | Pending | Pending
31 | Physical | Physical | BLR512B-G7-SW2 |  | 1 | TR-1 | Unracked (loose) | 2026-10-24 | 6:00 | 2026-10-24 | 6:00 | 12:30 | 755231F | 755231F | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Director | Storage | IBM | SAN Director- 64G - F78 | NA | Not Applicable | Not Applicable | 10.32.202.106 | 10.32.202.106 10.32.202.107 10.32.202.108 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A4 | 3-16 | 14 | N | F | F-01 | 4-17 | New rack | Yes | BLR128B-G7-SW2 (B2), DCX-BLR512B-2 (B2) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | CBS one Director, To reduce downtime of CBS, less than 24hours | Pending | Pending
32 | Physical | Physical | BLR128B-G7-SW2 |  | 2 | TR-2 | Unracked (loose) | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 6:00 | 787414D | 787414D | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Switch 64G | Storage | IBM | Brocade G730 | NA | Not Applicable | Not Applicable | 10.32.202.127 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | D3 | 39 | 1 | Y | D | D-09 | 23 | IBM Rack (D3) | Yes | BLR512B-G7-SW2 (B1) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
33 | Physical | Physical | CR1130RH6A |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 14:30 | 130RH6A | 130RH6A | Non-CBS | Production | Data Center Operations Section (ITI) | NDR HMC |  |  |  | Medium | SERVER | To Be Confirmed | IBM | POwerE950/7063CR1-130RH6A | IBM Power | AIX | 7.2 TL5 SP7 | 172.27.97.79 | NA | EFRM_Mgmt | NON DMZ | NDC-GR | Ground | GR-A1 | 21 | 1 |  | N | N-03 | 21 | GR-A3 | No |  |  | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | NDC devices | Pending | Pending
34 | Physical | Physical | SANINV379 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 14:30 | 78E4Y9C | 78E4Y9C | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | MT:2145-SV3 | NA | Not Applicable | Not Applicable | 10.32.206.19, 10.32.206.17 | NA | NDR-MGMT-NEW | Internal | NDC-GR | Ground | GR-A1 | 17-16 | 2 |  | N | N-03 | 17-16 | GR-A3 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
35 | Physical | Physical | SANINV378 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 14:30 | 78E4Y8T | 78E4Y8T | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | MT:2145-SV3 | NA | Not Applicable | Not Applicable | 10.32.206.18, 10.32.206.17 | NA | NDR-MGMT-NEW | Internal | NDC-GR | Ground | GR-A1 | 15-14 | 2 |  | N | N-03 | 15-14 | GR-A3 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
36 | Physical | Physical | BLRNDC_64BG7_SW1 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:00 | 2026-10-24 | 6:00 | 14:30 | 786731M | 7867J1M | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Switch 64G | Storage | IBM | Brocade G720 | NA | Not Applicable | Not Applicable | 172.27.97.114 | NA | Disconnected NO VLAN | To Be Confirmed | NDC-GR | Ground | GR-A1 | 38 | 1 |  | N | N-03 | 38 | GR-A3 | Yes | BLRDCREP_64BG7_SW1 (B2) | switch | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | NDC devices | Pending | Pending
37 | Physical | Physical | BLRNDC_64BG7_SW2 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:00 | 2026-10-24 | 6:00 | 14:30 | 786729Z | 786729Z | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Switch 64G | Storage | IBM | Brocade G720 | NA | Not Applicable | Not Applicable | 172.27.97.115 | NA | EFRM_Mgmt | Internal | NDC-GR | Ground | GR-A2 | 35 | 1 |  | N | N-04 | 35 | GR-A4 | Yes | BLRDCREP_64BG7_SW2 (B2) | switch | No | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | NDC devices | Pending | Pending
38 | Physical | Physical | Not Applicable |  | 1 | TR-1.2 | Loaded in OEM rack L3 | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 13:30 | 78DB197 | 78DB197 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Tape Library | Backup Expansion | IBM | TS4500 | NA | Not Applicable | Not Applicable | 10.32.202.26 | NA | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | L3 | NA | NA | Y | C | C-03 |  | IBM LTO8 tape library (L3) | No |  |  | Yes | Lailesh to verify |  | IBM INDIA PVT LTD | ON | Not Applicable | Yes |  | Tape libraries | Pending | Pending
39 | Physical | Physical | Not Applicable |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 14:30 | 3185702 | 3185702 | CBS | To Be Confirmed | Service Unit Section | SFMS |  |  |  | To Be Confirmed | Monitor | To Be Confirmed | IBM | HMC | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | NDC-GR | Ground | GR-A1 | 23 | 1 |  | N | N-03 | 23 | GR-A3 | No |  |  | No | Non-OEMs | Not Applicable | To Be Confirmed | Not Applicable | Not Applicable | Yes |  | NDC devices | Pending | Pending
40 | Physical | Physical | Not Applicable |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 14:30 | 78E3NKE2 | 78E3NKE2 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SAN Volume Controller | Storage | IBM | FLASH SYSTEM 7300 | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | NDC-GR | Ground | GR-A1 | 13-12 | 2 |  | N | N-03 | 13-12 | GR-A3 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | NDC devices | Pending | Pending
41 | Physical | Physical | ndrfccdb |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 14:30 | 78DA08X | 78DA08X | NON-CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 172.27.97.98 | 172.27.97.98 | EFRM_Mgmt | NON DMZ | NDC-GR | Ground | GR-A2 | 6-3 | 4 |  | N | N-04 | 6-3 | GR-A4 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | NDC devices | Pending | Pending
42 | Physical | Physical | Not Applicable |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 14:30 | 78DA08X | 00000FZHZ226 | CBS | To Be Confirmed | Service Unit Section | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | To Be Confirmed | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | To Be Confirmed | NDC-GR | Ground | GR-A2 | 10-7 | 4 |  | N | N-04 | 10-7 | GR-A4 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
43 | Physical | Physical | SANINV382 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 14:30 | 78E4Z1B | 78E4Z1B | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | MT:2145-SV3 | NA | Not Applicable | Not Applicable | 10.32.206.21, 10.32.206.17 | NA | NDR-MGMT-NEW | Internal | NDC-GR | Ground | GR-A2 | 17-16 | 2 |  | N | N-04 | 17-16 | GR-A4 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
44 | Physical | Physical | SANINV380 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 14:30 | 78E4Z1E | 78E4Z1E | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | MT:2145-SV3 | NA | Not Applicable | Not Applicable | 10.32.206.20, 10.32.206.17 | NA | NDR-MGMT-NEW | Internal | NDC-GR | Ground | GR-A2 | 15-14 | 2 |  | N | N-04 | 15-14 | GR-A4 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
45 | Physical | Physical | SANINV381 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:30 | 2026-10-24 | 6:00 | 14:30 | 78E3NPL | 78E3NPL | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | FLASH SYSTEM 7300 | NA | Not Applicable | Not Applicable | 10.32.206.22, 10.32.206.23, 10.32.206.24 | NA | NDR-MGMT-NEW | Internal | NDC-GR | Ground | GR-A2 | 13-12 | 2 |  | N | N-04 | 13-12 | GR-A4 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
46 | Physical | Physical | CB-NDR-P2P-SW |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FDO28050YP1 | FDO28050YP1 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | C9500 -24Y4C | NA | Not Applicable | Not Applicable | 10.32.255.35 | 10.32.255.35 | NDR-OUTSIDE-1 | NA | NDC-GR | Ground | GR-A3 | 39 | 1 |  | N | N-02 | 39 | GR-A2 | No |  |  | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | NDC devices | Pending | Pending
47 | Physical | Physical | CB-NDR-P2P-SW |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FDO28050YP4 | FDO28050YP4 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | C9500 -24Y4C | NA | Not Applicable | Not Applicable | 10.32.255.35 | 10.32.255.35 | NDR-OUTSIDE-1 | NA | NDC-GR | Ground | GR-A3 | 37 | 1 |  | N | N-02 | 37 | GR-A2 | No |  |  | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | NDC devices | Pending | Pending
48 | Physical | Physical | NDR-Cisco-Nexus-SW1 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FDO28160D18 | FDO28160D18 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108TC-FX3P | NA | Not Applicable | Not Applicable | 172.27.97.74 | 172.27.97.74 | NDR-MGMT-OLD | NA | NDC-GR | Ground | GR-A3 | 31 | 1 |  | L | L-10 | U4 |  | No |  |  | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | NDC devices | Pending | Pending
49 | Physical | Physical | NDR-Cisco-Nexus-SW2 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FDO28160237 | FDO28160237 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108TC-FX3P | NA | Not Applicable | Not Applicable | 172.27.97.75 | 172.27.97.75 | NDR-MGMT-OLD | NA | NDC-GR | Ground | GR-A3 | 29 | 1 | N | L | L-11 | U4 | New rack | No |  |  | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | NDC devices | Pending | Pending
50 | Physical | Physical | Not Applicable |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | 2161392000161 | 2161392000161 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Modem | To Be Confirmed | TP-Link | MC220L | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | NDC-GR | Ground | GR-A3 | Not Mounted | 0 |  | N | N-02 | Not Mounted | GR-A2 | No |  |  | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
51 | Physical | Physical | Not Applicable |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | SY2511A-131200531 / SY2304-131203010 | SY2511A-131200531 / SY2304-131203010 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Modem | To Be Confirmed | Syrotech | Firbre ethernet Media converter | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | NDC-GR | Ground | GR-A3 | Not Mounted | 0 |  | N | N-02 | Not Mounted | GR-A2 | No |  |  | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
52 | Physical | Physical | Not Applicable |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | CAEZ2226 | CAEZ2226 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Router | To Be Confirmed | Juniper | Mx104 | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | NDC-GR | Ground | GR-A3 | 4-2 | 3 |  | N | N-02 | 4-2 | GR-A2 | No |  |  | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | NDC devices | Pending | Pending
53 | Physical | Physical | CAN-NDR-FORTINET-FW2 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FG3K2D3Z16800247 | FG3K2D3Z16800247 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Security Appliance | To Be Confirmed | Fortinet | Fortigate 3200D | NA | Not Applicable | Not Applicable | 172.27.97.245/10.32.255.40 | 172.27.97.245/10.32.255.40 | NDR-MGMT-OLD | NA | NDC-GR | Ground | GR-A4 | 36-35 | 2 |  | N | N-01 | 36-35 | GR-A1 | No |  |  | No | Non-OEMs | Not Applicable | Tech Mahindra Ltd. | ON | ON | Yes |  | NDC devices | Pending | Pending
54 | Physical | Physical | CAN-NDR-FORTINET-FW1 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FG3K2D3Z16800269 | FG3K2D3Z16800269 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Security Appliance | To Be Confirmed | Fortinet | Fortigate 3200D | NA | Not Applicable | Not Applicable | 172.27.97.245/10.32.255.40 | 172.27.97.245/10.32.255.40 | NDR-MGMT-OLD | NA | NDC-GR | Ground | GR-A4 | 34-33 | 2 |  | N | N-01 | 34-33 | GR-A1 | No |  |  | No | Non-OEMs | Not Applicable | Tech Mahindra Ltd. | ON | ON | Yes |  | NDC devices | Pending | Pending
55 | Physical | Physical | NDR-DMZ-SW-01 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FDO281513F3 | FDO281513F3 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108TC-FX3 | NA | Not Applicable | Not Applicable | 10.33.200.25 | 10.33.200.25 | DMZ_NETWORK_MGMT | DMZ | NDC-GR | Ground | GR-A4 | 31 | 1 | N | H | H-10 | U4 | New rack | No |  |  | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | NDC devices | Pending | Pending
56 | Physical | Physical | NDR_DMZ_SW_02 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 14:30 | FDO28160CZT | FDO28160CZT | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108TC-FX3 | NA | Not Applicable | Not Applicable | 10.33.200.26 | 10.33.200.26 | DMZ_NETWORK_MGMT | DMZ | NDC-GR | Ground | GR-A4 | 29 | 1 |  | H | H-11 | U4 | New rack | No |  |  | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | NDC devices | Pending | Pending
57 | Physical | Physical | NDC-BASENDC-APP |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | C8SSN24 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | Dell Poweredge R760 | X86 | WINDOWS | Microsoft Windows Server 2025 | 10.32.216.5 | 10.32.206.14 | NDR_BASE_ESXI | NON DMZ | NDC-GR | Ground | GR-A4 | 6-5 | 2 |  | N | N-01 | 6-5 | GR-A1 | Yes | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | No | Non-OEMs | Not Applicable | Dynacons Systems and Solutions Limited | ON | Live | Yes |  | NDC devices | Pending | Pending
58 | Physical | Physical | DCC0GRN24 |  | 1 | TR-1.4 | Unracked (loose) | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 14:30 | C0GRN24 | C0GRN24 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | Database Server - NDC - ASBA n Dpsecure |  |  | 47206 | Dynacons Systems and Solutions Limited | SERVER | 10.32.206.198 | Dell | Dell Poweredge R760 | Pending | 45657 | CPVMW-TPS-ORD-558-2024-25 |  | Capex | No | No | NDC-GR | Ground | GR-A4 | 8-7 | 2 |  | N | N-01 | 8-7 | GR-A1 | No | [5 empty] | Not Applicable | ON | Shutdown | Yes |  | NDC devices | Pending | Pending
59 | Physical | Physical | DC-K6-N9K-TOR-SW1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 12:30 | FDO24130M76 | FDO24130M76 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.12 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K6 | 41 | 1 | Y | I | I-10 | Spare | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
60 | Physical | Physical | SANINV191 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 78E071K | 78E071K | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | Storage Array | Storage | IBM | IBM Flashsystem 9100 MTM: 9848-AF8 | NA | Not Applicable | Not Applicable | 10.32.202.9 | 10.32.202.9 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | K6 | 15-16 | 2 | Y | G | G-20 | 4-5 | IBM rack (K6) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
61 | Physical | Physical | SANINV179 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 78E072T | 78E072T | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Array | Storage | IBM | Flash system 9100 | NA | Not Applicable | Not Applicable | 10.32.202.12 | Mgmt IP N1P1 Serive IP N2P1 Serive IP | CBS_STORAGE_MGMT | Internal | DC1 | 1 | L5 | 13-14 | 2 | Y | H | H-19 | 4-5 | IBM rack (L5) | Yes | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Batch 2 – UAT switch BLR128B-G7-SW1/SW2 (787413W/787414D) and all connected devices (batch-reason: 78C7868 & 78C7848 also connected to DCX-BLR512B-1/2) | Pending | Pending
62 | Physical | Physical | E980-2-9080-M9S-SN78415A8 |  | 2 | TR-2.8 | Loaded in OEM rack K2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | 78415A8 | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.21, 10.32.207.22 | 10.32.207.21 | HMC_CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | K2 | 9-10 | 2 | Y | G | G-09 | 28-29 | IBM rack (K2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
63 | Physical | Physical | E980-2-9080-M9S-SN78415A8 |  | 2 | TR-2.8 | Loaded in OEM rack K2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | CSS3426 | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K2 | 26-30 | 5 | Y | G | G-09 | 4-8 | IBM rack (K2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
64 | Physical | Physical | E980-2-9080-M9S-SN78415A8 |  | 2 | TR-2.8 | Loaded in OEM rack K2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | CSS322E | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K2 | 21-25 | 5 | Y | G | G-09 | 9-13 | IBM rack (K2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
65 | Physical | Physical | E980-2-9080-M9S-SN78415A8 |  | 2 | TR-2.8 | Loaded in OEM rack K2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | CSS2CAD | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K2 | 16-20 | 5 | Y | G | G-09 | 14-18 | IBM rack (K2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
66 | Physical | Physical | E980-2-9080-M9S-SN78415A8 |  | 2 | TR-2.8 | Loaded in OEM rack K2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | CSS33C2 | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K2 | 11-15 | 5 | Y | G | G-09 | 19-23 | IBM rack (K2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
67 | Physical | Physical | E980-2-9080-M9S-SN78415A8 |  | 2 | TR-2.8 | Loaded in OEM rack K2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | SN00000FZHFY97 | CBS | Notinuse | Data Center Operations Section (ITI) | SFMS |  |  |  | Medium | IO Expansion Drawer | To Be Confirmed | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | K2 | 31-34 | 4 | Y | G | G-09 | 24-27 | IBM rack (K2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
68 | Physical | Physical | DC-K2-N9K-TOR-SW1 |  | 2 | TR-2.8 | Loaded in OEM rack K2 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 10:00 | FDO24120F48 | FDO24120F48 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.5 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K2 | 42 | 1 | Y | A | A-09 | 0 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
69 | Physical | Physical | E950-3-9040-MR9-SN78DE94X |  | 2 | TR-2.8 | Loaded in OEM rack K3 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78DE94X | 78DE94X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.12 | 10.32.201.30 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K3 | 11-14 | 4 | Y | H | H-09 | 8-11 | IBM rack (K1) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
70 | Physical | Physical | E950-1-9040-MR9-SN78DE92X |  | 2 | TR-2.8 | Loaded in OEM rack K3 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78DE92X | 78DE92X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.10 | 10.32.201.31 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K3 | 7-10 | 4 | Y | H | H-09 | 12-15 | IBM rack (K1) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
71 | Physical | Physical | E950-2-9040-MR9-SN78DE93X |  | 2 | TR-2.8 | Loaded in OEM rack K3 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | 78DE93X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.11 | 10.32.201.29 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K3 | 15-18 | 4 | Y | H | H-09 | 4-7 | IBM rack (K1) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
72 | Physical | Physical | Not Applicable |  | 2 | TR-2.8 | Loaded in OEM rack K3 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 106525Z | 106525Z | CBS | Notinuse | Data Center Operations Section (ITI) | SFMS |  |  |  | Medium | Monitor | To Be Confirmed | IBM | Console Monitor | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | DC1 | 1 | K3 | 22 | 1 | Y | H | H-09 | 16 | IBM rack (K1) | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
73 | Physical | Physical | DC-K3-N9K-TOR-SW1 |  | 2 | TR-2.8 | Loaded in OEM rack K3 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 10:00 | FDO24120F3W | FDO24120F3W | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.6 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K3 | 41 | 1 | Y | H | H-14 | 0 | IBM rack (C3) | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
74 | Physical | Physical | DC-K3-N9K-TOR-SW2 |  | 2 | TR-2.8 | Loaded in OEM rack K3 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 10:00 | FDO24120EVL | FDO24120EVL | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.7 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K3 | 40 | 1 | Y | G | G-10 | 0 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
75 | Physical | Physical | DC130WA8A |  | 2 | TR-2.8 | Loaded in OEM rack K3 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:00 | 130WA8A | 130WA8A | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | HMC Console | To Be Confirmed | IBM | MTM: 7063-CR1 | NA | NA | NA | 10.32.201.3 | 10.32.201.3 | CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | K3 | 21 | 1 | Y | H | H-09 | 17 | IBM rack (K1) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
76 | Physical | Physical | E950-6-9040-MR9-SN78DE97X |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | 78DE97X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.15 | 10.32.201.32 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K4 | 15-18 | 4 | Y | G | G-08 | 4-7 | IBM rack (K4) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
77 | Physical | Physical | E950-4-9040-MR9-SN78DE95X |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | 78DE95X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.13 | 10.32.201.36 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K4 | 11-14 | 4 | Y | G | G-08 | 8-11 | IBM rack (K4) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
78 | Physical | Physical | E950-5-9040-MR9-SN78DE96X |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | 78DE96X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.14 | 10.32.201.34 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K4 | 7-10 | 4 | Y | G | G-08 | 12-15 | IBM rack (K4) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
79 | Physical | Physical | Not Applicable |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 130897A | 130897A | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SERVER | To Be Confirmed | IBM | MTM: 7063-CR1 | X86 | NA | NA | 172.16.38.49 | 172.16.38.49 | Database | NON DMZ | DC1 | 1 | K4 | 24 | 1 | Y | G | G-08 | 25 | IBM rack (K4) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
80 | Physical | Physical | DC-K4-N9K-TOR-SW1 |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 10:30 | FDO24120F13 | FDO24120F13 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.8 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K4 | 41 | 1 | Y | H | H-08 | 0 | IBM rack (K3) | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
81 | Physical | Physical | DC-K4-N9K-TOR-SW2 |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 10:30 | FDO241208LK | FDO241208LK | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.9 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K4 | 40 | 1 | Y | G | G-11 | Spare | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
82 | Physical | Physical | DC-K4-N9K-TOR-SW3 |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 10:30 | FDO24120F8J | FDO24120F8J | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.10 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K4 | 39 | 1 | Y | G | G-10 | Spare | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
83 | Physical | Physical | Not Applicable |  | 2 | TR-2.9 | Loaded in OEM rack K4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 102656Y | 102656Y | CBS | To Be Confirmed | Data Center Operations Section (ITI) | SFMS |  |  |  | To Be Confirmed | Monitor | To Be Confirmed | IBM | Console Monitor | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | DC1 | 1 | K4 | 25 | 1 | Y | G | G-08 | 24 | IBM rack (K4) | No |  |  | Yes | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
84 | Physical | Physical | E950-9-9040-MR9-SN78DE99X |  | 2 | TR-2.9 | Loaded in OEM rack K5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 78DE99X | 78DE99X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.18 | 10.32.201.35 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K5 | 15-18 | 4 | Y | H | H-08 | 28-31 | IBM rack (K3) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
85 | Physical | Physical | E950-7-9040-MR9-SN78DE9AX |  | 2 | TR-2.9 | Loaded in OEM rack K5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | 78DE9AX | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.16 | 10.32.201.33 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K5 | 11-14 | 4 | Y | G | G-08 | 16-19 | IBM rack (K4) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
86 | Physical | Physical | E950-8-9040-MR9-SN78DE98X |  | 2 | TR-2.9 | Loaded in OEM rack K5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | 78DE98X | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E950 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.17 | 10.32.201.37 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | K5 | 7-10 | 4 | Y | G | G-08 | 20-23 | IBM rack (K4) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
87 | Physical | Physical | DC-K5-N9K-TOR-SW1 |  | 2 | TR-2.9 | Loaded in OEM rack K5 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 10:30 | FDO241208W2 | FDO241208W2 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.11 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K5 | 41 | 1 | Y | G | G-11 | Spare | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
88 | Physical | Physical | SANINV195 |  | 2 | TR-2.10 | Loaded in OEM rack K6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E306M | 78E306M | CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Volume Controller | Storage | IBM | IBM SAN Volume Controller MTM: 2145-SV2 | NA | Not Applicable | Not Applicable | 10.32.202.25 | 10.32.202.25 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | K6 | 11-12 | 2 | Y | G | G-20 | 6-7 | IBM rack (K6) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
89 | Physical | Physical | SANINV193 |  | 2 | TR-2.10 | Loaded in OEM rack K6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E3078 | 78E3078 | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Volume Controller | Storage | IBM | IBM SAN Volume Controller MTM: 2145-SV2 | NA | Not Applicable | Not Applicable | 10.32.202.23 | 10.32.202.23 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | K6 | 9-10 | 2 | Y | G | G-20 | 8-9 | IBM rack (K6) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
90 | Physical | Physical | SANINV192 |  | 2 | TR-2.10 | Loaded in OEM rack K6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E3071 | 78E3071 | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Volume Controller | Storage | IBM | IBM SAN Volume Controller MTM: 2145-SV2 | NA | Not Applicable | Not Applicable | 10.32.202.21 | 10.32.202.21 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | K6 | 7-8 | 2 | Y | G | G-20 | 10-11 | IBM rack (K6) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
91 | Physical | Physical | SANINV194 |  | 2 | TR-2.10 | Loaded in OEM rack K6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E306K | 78E306K | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Volume Controller | Storage | IBM | IBM SAN Volume Controller MTM: 2145-SV2 | NA | Not Applicable | Not Applicable | 10.32.202.19 | 10.32.202.19 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | K6 | 5-6 | 2 | Y | G | G-20 | 12-13 | IBM rack (K6) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
92 | Physical | Physical | SANINV196 |  | 2 | TR-2.10 | Loaded in OEM rack K6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E3063 | 78E3063 | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Volume Controller | Storage | IBM | IBM SAN Volume Controller MTM: 2145-SV2 | NA | Not Applicable | Not Applicable | 10.32.202.17 | 10.32.202.17 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | K6 | 3-4 | 2 | Y | G | G-20 | 14-15 | IBM rack (K6) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
93 | Physical | Physical | SANINV181 |  | 2 | TR-2.10 | Loaded in OEM rack L5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E3079 | 78E3079 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.24 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | L5 | 9-10 | 2 | Y | H | H-19 | 6-7 | IBM rack (L5) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
94 | Physical | Physical | SANINV182 |  | 2 | TR-2.10 | Loaded in OEM rack L5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E3072 | 78E3072 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.22 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | L5 | 7-8 | 2 | Y | H | H-19 | 8-9 | IBM rack (L5) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
95 | Physical | Physical | SANINV183 |  | 2 | TR-2.10 | Loaded in OEM rack L5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E306L | 78E306L | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.20 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | L5 | 5-6 | 2 | Y | H | H-19 | 10-11 | IBM rack (L5) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
96 | Physical | Physical | SANINV180 |  | 2 | TR-2.10 | Loaded in OEM rack L5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:00 | 78E306B | 78E306B | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Volume Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.18 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | L5 | 3-4 | 2 | Y | H | H-19 | 12-13 | IBM rack (L5) | Yes | BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
97 | Physical | Physical | BLR512B-G7-SW1 |  | 2 | TR-2 | Unracked (loose) | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 6:00 | 787100G | 787100G | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Director | Storage | IBM | SAN Director- 64G - F78 | NA | Not Applicable | Not Applicable | 10.32.202.103,10.32.202.104,10.32.202.105 | 10.32.202.103 10.32.202.104 10.32.202.105 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A3 | 3-16 | 14 | N | E | E-16 | 4-17 | New rack | Yes | BLR128B-G7-SW1 (B2), DCX-BLR512B-1 (B2) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | SAN switch BLR512B-G7-SW1 – merged SAN batch | Pending | Pending
98 | Physical | Physical | SANINV90 |  | 2 | TR-2 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 6:00 | 7821YYX | 7821YYX | CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | High | SAN Storage | Storage | IBM | Storewize-V7000 | NA | Not Applicable | Not Applicable | 172.16.34.200, 172.16.34.201 | NA | DC_Storage | Internal | DC1 | 1 | B2 | 21-22 | 2 | Y | C | C-08 | 4-5 | IBM Rack (C1) | No |  |  | No | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
99 | Physical | Physical | SANINV88 |  | 2 | TR-2 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 6:00 | 782206V | 782206V | CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | High | SAN Storage | Storage | IBM | Storewize-V7000 | NA | Not Applicable | Not Applicable | 172.16.34.199 | 172.16.34.199 | DC_Storage | NON DMZ | DC1 | 1 | B2 | 19-20 | 2 | Y | C | C-08 | 6-7 | IBM Rack (C1) | No |  |  | No | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
100 | Physical | Physical | SANINV68 |  | 2 | TR-2 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 6:00 | 7823KXE | 7823KXE | CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Storage | Storage | IBM | Storewize-V7000 | NA | Not Applicable | Not Applicable | 172.16.34.220, 172.16.34.221 | NA | DC_Storage | Internal | DC1 | 1 | B2 | 17-18 | 2 | Y | C | C-08 | 8-9 | IBM Rack (C1) | No |  |  | No | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
101 | Physical | Physical | SANINV66 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 7823KWF | 7823KWF | CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Storage | Storage | IBM | Storewize-V7000 | NA | Not Applicable | Not Applicable | 172.16.34.220, 172.16.34.221 | NA | DC_Storage | Internal | DC1 | 1 | B2 | 15-16 | 2 | Y | C | C-08 | 10-11 | IBM Rack (C1) | No |  |  | No | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
102 | Physical | Physical | candcnwsn01 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | CX4SMZ3 | CX4SMZ3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Server | Storage | Dell | DELL EMC PowerEdge R650 | NA | Not Applicable | Not Applicable | 10.32.24.61 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W6 | 34 | 1 | Y | H | H-06 | 35 | Dell Rack (W6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | To Be Confirmed | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
103 | Physical | Physical | candcnwsn02 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | BJDXMZ3 | BJDXMZ3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Server | Storage | Dell | DELL EMC PowerEdge R650 | NA | Not Applicable | Not Applicable | 10.32.24.62 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W6 | 33 | 1 | Y | H | H-06 | 36 | Dell Rack (W6) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
104 | Physical | Physical | candcdd.aranac.com |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | DZRH504 | DZRH504 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Backup Appliance | Storage | Dell | Power Protect DD9900 | NA | Not Applicable | Not Applicable | 10.32.24.14,10.32.24.15,10.32.24.16,10.32.24.17,172.16.3.99,172.16.11.158,172.16.38.7,10.32.24.47 | 10.32.24.72 | Tapeless Backup Solutions,Database,NON-CBS DB2,NON-CBS DB | To Be Confirmed | DC2 | 2 | W6 | 28-26 | 3 | Y | H | H-06 | 24-26 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
105 | Physical | Physical | candcdd.aranac.com |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | GZRH504 | GZRH504 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Backup Appliance | Storage | Dell | Power Protect DD9900 | NA | Not Applicable | Not Applicable | 10.32.24.14,10.32.24.15,10.32.24.16,10.32.24.17,172.16.3.99,172.16.11.158,172.16.38.7,10.32.24.47 | 10.32.24.73 | Tapeless Backup Solutions,Database,NON-CBS DB2,NON-CBS DB | To Be Confirmed | DC2 | 2 | W6 | 25-23 | 3 | Y | H | H-06 | 27-29 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
106 | Physical | Physical | Not Applicable |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | 296Z9W3 | 296Z9W3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage extension | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W6 | 22-21 | 3 | Y | H | H-06 | 30-32 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
107 | Physical | Physical | Not Applicable |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | 496Z9W3 | 496Z9W3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage extension | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W6 | 20-16 | 5 | Y | H | H-06 | 4-8 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
108 | Physical | Physical | Not Applicable |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | 696Z9W3 | 696Z9W3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage extension | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W6 | 15-11 | 5 | Y | H | H-06 | 9-13 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
109 | Physical | Physical | Not Applicable |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | 396Z9W3 | 396Z9W3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage extension | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W6 | 10-6 | 5 | Y | H | H-06 | 14-18 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
110 | Physical | Physical | Not Applicable |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | 5C4Z9W3 | 5C4Z9W3 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage extension | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W6 | 5-1 | 5 | Y | H | H-06 | 19-23 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
111 | Physical | Physical | Not Applicable |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 781V1N9 | 781V1N9 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | B2 | 11-12 | 2 | Y | C | C-08 | 14-15 | IBM Rack (C1) | No |  |  | No | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
112 | Physical | Physical | SANINV221 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 781V1M7 | 781V1M7 | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | High | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | 10.32.202.3 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | B2 | 09-10 | 2 | Y | C | C-08 | 16-17 | IBM Rack (C1) | No |  |  | No | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
113 | Physical | Physical | SANINV220 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 781V1N4 | 781V1N4 | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | High | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | 10.32.202.3 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | B2 | 07-08 | 2 | Y | C | C-08 | 18-19 | IBM Rack (C1) | No |  |  | No | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
114 | Physical | Physical | Not Applicable |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 78E06F7 | 78E06F7 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Storage | Storage | IBM | Storewize-V7000 | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | B2 | 13-14 | 2 | Y | C | C-08 | 12-13 | IBM Rack (C1) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
115 | Physical | Physical | DCPLCSWDO02RTGS |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | WZP22260A84 | WZP22260A84 | Non-CBS | Production | Service Unit Section | RTGS | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com | IFTAS | IFTAS (RBI SUBSIDIARY ) ¦ 914047524085 ¦ sfms.team@iftas.in | High | SERVER | APP | Cisco | UCS C220 M5 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 172.16.32.119 | 172.16.32.119 | SFMS-NEFT | NON DMZ | DC1 | 1 | E2 | 13 | 1 | Y | C | C-14 | 15 | WQ Rack (AB2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
116 | Physical | Physical | SANINV170 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 8JW4L83 | 8JW4L83 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | Storage Array | Storage | Dell | EMC Unity 380F | NA | Not Applicable | Not Applicable | 172.16.34.171 | 172.16.34.171 | DC_Storage | NON DMZ | DC1 | 1 | F3 | 14-15 | 2 | Y | D | D-06 | 34-35 | WQ Rack (AC6) | No |  |  | No | Dell Support | Harsha.Vardhan5@Dell.com | CITO INFOTECH PVT LTD | ON | Shutdown | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
117 | Physical | Physical | SANINV170 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | G5KVNT3 | G5KVNT3 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | Storage Array | Storage | Dell | EMC Unity 380F | NA | Not Applicable | Not Applicable | 172.16.34.171 | NA | DC_Storage | Internal | DC1 | 1 | F3 | 12-13 | 2 | Y | D | D-06 | 32-33 | WQ Rack (AC6) | No |  |  | No | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
118 | Physical | Physical | SANINV170 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | D5KVNT3 | D5KVNT3 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | Storage Array | Storage | Dell | EMC Unity 380F | NA | Not Applicable | Not Applicable | 172.16.34.171 | NA | DC_Storage | Internal | DC1 | 1 | F3 | 10-11 | 2 | Y | D | D-06 | 30-31 | WQ Rack (AC6) | No |  |  | No | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
119 | Physical | Physical | SANINV170 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | CKM00194301481/22W9MX2 | CKM00194301481/22W9MX2 | CBS | Notinuse | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | Storage Array | Storage | Dell | Dell EMC Unity XT | NA | Not Applicable | Not Applicable | 172.16.34.171 | NA | DC_Storage | Internal | DC1 | 1 | F3 | 05-04 | 2 | Y | D | D-06 | 28-29 | WQ Rack (AC6) | No |  |  | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
120 | Physical | Physical | DCX-BLR512B-1 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 11:30 | 781403F | 781403F | CBS | Production | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | SAN Director | Storage | IBM | IBM SAN512B-6 | NA | Not Applicable | Not Applicable | 10.32.202.27 | 10.32.202.27 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | K7 | 17-04 | 14 | N | F | F-16 | 4-17 | New rack | Yes | BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | SAN switch DCX-BLR512B-1 – merged SAN batch | Pending | Pending
121 | Physical | Physical | DCX-BLR512B-2 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 11:30 | 781405Z | 781405Z | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Director | Storage | IBM | IBM SAN512B-6-SAN Director 32G | NA | Not Applicable | Not Applicable | 10.32.202.30,10.32.202.31,10.32.202.32 | Mgmt IP CP0 Service IP CP1 Service IP | CBS_STORAGE_MGMT | Internal | DC1 | 1 | L6 | 17-04 | 14 | N | E | E-01 | 4-17 | New rack | Yes | BLR512B-G7-SW2 (B1), DCX-BLR3SSWPC2112 (B2) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | SAN switch DCX-BLR512B-2 – merged SAN batch | Pending | Pending
122 | Physical | Physical | OAVS2 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | WZP222808BJ | WZP222808BJ | Non-CBS | Production | Data Center Operations Section (ITI) | Audit Vault Database Firewall |  |  |  | Medium | SERVER | APP | Cisco | UCS C220 M5 | X86 | OEL | OEL 7.90 | 172.16.32.180 | 172.16.32.180 | Oracle_ULA_AV | NON DMZ | DC1 | 1 | E2 | 02 | 1 | Y | C | C-14 | 23 | WQ Rack (AB2) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
123 | Physical | Physical | DCPLCSWQI01RTGS |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | WZP22260A7Z | WZP22260A7Z | Non-CBS | Production | Service Unit Section | RTGS |  |  |  | High | SERVER | APP | Cisco | UCS C220 M5 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 172.16.32.118 | 172.16.32.118 | SFMS-NEFT | NON DMZ | DC1 | 1 | E3 | 13 | 1 | Y | D | D-14 | 8 | WQ Rack (AD2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
124 | Physical | Physical | avs00451d69b946 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | WZP22270KUZ | WZP22270KUZ | Non-CBS | Production | Data Center Operations Section (ITI) | Audit Vault Database Firewall |  |  |  | Medium | SERVER | APP | Cisco | UCS C220 M5 | X86 | OEL | OEL 7.90 | 172.16.32.179 | 172.16.32.179 | Oracle_ULA_AV | NON DMZ | DC1 | 1 | E3 | 02 | 1 | Y | D | D-14 | 16 | WQ Rack (AD2) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
125 | Physical | Physical | UATAPP-OTP |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | WZP22190GDB | WZP22190GDB | CBS | UAT | Online Banking Technology Net banking Section | OFFLINE OTP | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com | MANIPAL TECHNOLOGY | SUBRAMANIYAM ¦ 9741797150 ¦ offlineotp@canarabank.com | Low | SERVER | APP | Cisco | UCS C220 M5 | X86 | WINDOWS | Microsoft Windows Server 2016 Standard | 172.16.11.4 | 172.16.11.4 | NON-CBS_APP_2 | NON DMZ | DC1 | 1 | E3 | 17 | 1 | Y | D | D-14 | 5 | WQ Rack (AD2) | No |  |  | No | Non-OEMs | Not Applicable | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
126 | Physical | Physical | DCDLLDB1RAC5NODE2 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 8XX5G33 | 8XX5G33 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | DB | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 10.32.12.13 | 10.32.12.13 | NCBS_DB | NON DMZ | DC1 | 1 | F2 | 29 | 1 | N | A | A-10 | 27 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
127 | Physical | Physical | dcdlldb1rac5node1 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 6XX5G33 | 6XX5G33 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | DB | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 10.32.12.12 | 10.32.12.12 | NCBS_DB | NON DMZ | DC1 | 1 | F2 | 28 | 1 | N | B | B-10 | 29 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
128 | Physical | Physical | DCDLLDB1RAC1NODE1 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | FCJXJ03 | FCJXJ03 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | NCBS RAC |  |  |  | Medium | SERVER | DB | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 172.16.121.4 | 172.16.6.41 | NON-CBS_Oracle_RAC | NON DMZ | DC1 | 1 | F3 | 09 | 1 | Y | H | H-02 | 30 | WQ Rack (AE4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | OFF | Decommissioned | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
129 | Physical | Physical | DCDLLDB1RAC2NODE1 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 3DCYM03 | 3DCYM03 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | NCBS RAC |  |  |  | Medium | SERVER | DB | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 172.16.121.6 | 172.16.6.42 | NON-CBS_Oracle_RAC | NON DMZ | DC1 | 1 | F3 | 08 | 1 | Y | H | H-02 | 31 | WQ Rack (AE4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | OFF | Decommissioned | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
130 | Physical | Physical | DCDLLDB1RAC3NODE1 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 5DCYM03 | 5DCYM03 | Non-CBS | Production | Data Center Operations Section (ITI) | RAC DB |  |  |  | Low | SERVER | DB | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 172.16.121.8 | 172.16.121.8 | NON-CBS_Oracle_RAC | NON DMZ | DC1 | 1 | F3 | 07 | 1 | N | A | A-10 | 26 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
131 | Physical | Physical | DCDLLDB1RAC3NODE2 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 5ZHXJ03 | 5ZHXJ03 | Non-CBS | Production | FCR Deposits Section | RAC DB |  |  |  | Low | SERVER | DB | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 172.16.121.9 | 172.16.121.9 | NON-CBS_Oracle_RAC | NON DMZ | DC1 | 1 | F4 | 16 | 1 | N | B | B-10 | 28 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
132 | Physical | Physical | DCUATDBN4 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | D2SXMZ3 | D2SXMZ3 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | Middleware Hyper V Cluster |  |  |  | Medium | SERVER | SERVER | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | 9.4 | 10.32.203.113 | 10.32.203.113 | NON-CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | J2 | 8-9 | 2 | Y | L | L-01 | 6-7 | WQ rack (N5) | Yes | DCX-BLR3SSWPC2112 (B2) | B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
133 | Physical | Physical | DCUATDBN5 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | D3SXMZ3 | D3SXMZ3 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | Middleware Hyper V Cluster |  |  |  | Medium | SERVER | SERVER | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | 9.4 | 10.32.203.112 | 10.32.210.162 | NON-CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | J2 | 4-5 | 2 | Y | L | L-02 | 6-7 | WQ rack (AA6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
134 | Physical | Physical | DCUATDBN2 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 73SXMZ3 | 73SXMZ3 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | Tracs UAT DB |  |  |  | Medium | SERVER | SERVER | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | 9.4 | 10.32.203.212 | 10.32.203.208 | NON-CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | J2 | 20-21 | 2 | Y | L | L-01 | 14-15 | WQ rack (N5) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
135 | Physical | Physical | DCHVCLSTRN10 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 93SXMZ3 | 93SXMZ3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | SERVER | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.51.37 | 10.32.51.37 | NCBS_APP_NEW | NON DMZ | DC1 | 1 | J2 | 16-17 | 2 | Y | H | H-01 | 6-7 | WQ Rack (AE3) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
136 | Physical | Physical | DCHVCLSTRN09 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | 83SXMZ3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.51.38 | 10.32.51.38 | NCBS_APP_NEW | NON DMZ | DC1 | 1 | J2 | 14-15 | 2 | Y | H | H-01 | 8-9 | WQ Rack (AE3) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
137 | Physical | Physical | DCHVCLSTRN08 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | H3SXMZ3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.51.39 | 10.32.51.39 | NCBS_APP_NEW | NON DMZ | DC1 | 1 | J2 | 12-13 | 2 | Y | H | H-01 | 10-11 | WQ Rack (AE3) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
138 | Physical | Physical | DCHVCLSTRN07 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | G3SXMZ3 | G3SXMZ3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | High | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | RHEL 8.10 | 10.32.51.40 | 10.32.210.165 | NCBS_APP_NEW | NON DMZ | DC1 | 1 | J2 | 10-11 | 2 | Y | H | H-01 | 23-24 | WQ Rack (AE3) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
139 | Physical | Physical | DCUATDBN6 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | J3SXMZ3 | J3SXMZ3 | Non-CBS | UAT | Data Center Operations Section (ITI) | Tracs UAT DB |  |  |  | High | SERVER | SERVER | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | 9.4 | 10.32.203.111 | 10.32.210.161 | Non-CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | J2 | 2-3 | 2 | Y | L | L-02 | 8-9 | WQ rack (AA6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
140 | Physical | Physical | DC-SFTP-SRV |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 183M6C2 | 183M6C2 | Non-CBS | Notinuse | Application Development Section (In House) (ADM) | ADM | Debarun, Yogesh ¦ 9398989380 ¦ yogeshsai@canarabank.com |  |  | High | SERVER | APP | Dell | Dell EMC Power Edge R630 | X86 | WINDOWS | 6.5 | 172.16.41.193 | 192.168.0.120 | NewDMZ | DMZ | DC1 | 1 | M5 | 26 | 1 | Y | I | I-06 | 32 | Net Rack (AA5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
141 | Physical | Physical | Not Applicable |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | FSC1940004 | C3EC8EC034 / C3EC8EC040 / C3EC8EC048 | CBS | To Be Confirmed | NCBS Appication Support | SFMS |  |  |  | To Be Confirmed | Tape Storage | To Be Confirmed | Quantum | Quantum Scalar I6 Drive IBM LTO8 FH FS | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | DC-Gr | Ground | S6 | 14-9 | 6 | Y | C | C-05 | 16-21 | WQ Rack (AA2) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
142 | Physical | Physical | Not Applicable |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | FSC1940004 | C3EC8EC114 / C3EC8EC000 / C3EC8EC008 | CBS | To Be Confirmed | NCBS Appication Support | SFMS |  |  |  | To Be Confirmed | Tape Storage | To Be Confirmed | Quantum | Quantum Scalar I6 Drive IBM LTO8 FH FS | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | DC-Gr | Ground | S6 | 26-21 | 6 | Y | C | C-05 | 4-9 | WQ Rack (AA2) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
143 | Physical | Physical | Not Applicable |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 12:00 | FSC1940004 | C3EC8EC014 / C3EC8EC020 / C3EC8EC028 | CBS | To Be Confirmed | NCBS Appication Support | SFMS |  |  |  | To Be Confirmed | Tape Storage | To Be Confirmed | Quantum | Quantum Scalar I6 Drive IBM LTO8 FH FS | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | DC-Gr | Ground | S6 | 20-15 | 6 | Y | C | C-05 | 10-15 | WQ Rack (AA2) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
144 | Physical | Physical | TRAC Setup |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | C3SXMZ3 | C3SXMZ3 | Non-CBS | Production | Data Center Operations Section (ITI) | PeopleSoft HRMS |  |  |  | High | SERVER | DB | Dell | Dell EMC PowerEdge R750 | X86 | ORACLE LINUX | RHEL 8.10 | 10.32.203.110 | 10.32.11.155 | NON-CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | J2 | 18-19 | 2 |  | H | H-01 | 4-5 | WQ Rack (AE3) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs |  |  | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
145 | Physical | Physical | DCCANCRKPSM03 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 21KHMY3 | 21KHMY3 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | PIM |  |  |  | Medium | SERVER | SERVER | Dell | PowerEdge 750 | X86 | RHEL | 9.4 | 172.16.40.57 | 172.16.40.57 | SOC_PIM_AD_SERVER | NON DMZ | DC1 | 1 | M1 | 17-16 | 2 | Y | J | J-07 | 16-17 | Net Rack (X5) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | Decommissioned | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
146 | Physical | Physical | DCHYPRVBASE2 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 81KHMY3 | 81KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | PowerEdge 750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.33.131.160 | 10.33.131.160 | UAT_NCBS_APP | NON DMZ | DC1 | 1 | M1 | 23-22 | 2 | Y | J | J-07 | 10-11 | Net Rack (X5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
147 | Physical | Physical | cluster1-Node1 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | B1KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | PowerEdge 750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.13.80 | 10.32.13.80 | NCBS_WEB | NON DMZ | DC1 | 1 | M1 | 21-20 | 2 | Y | J | J-07 | 12-13 | Net Rack (X5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
148 | Physical | Physical | cluster1-Node3 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | 10KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | WEB | Dell | PowerEdge 750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.13.44 | 10.32.13.44 | NCBS_WEB | NON DMZ | DC1 | 1 | M1 | 15-14 | 2 | Y | J | J-07 | 18-19 | Net Rack (X5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
149 | Physical | Physical | cluster1-Node4 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | 61KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | PowerEdge 750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.13.45 | 10.32.13.45 | NCBS_WEB | NON DMZ | DC1 | 1 | M1 | 13-12 | 2 | Y | J | J-07 | 20-21 | Net Rack (X5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
150 | Physical | Physical | DCDLLDB1RAC7NODE2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 41KHMY3 | 41KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | SERVER | SERVER | Dell | PowerEdge 750 | X86 | RHEL | RHEL 8.10 | 10.32.22.197 | 10.32.22.197 | RAC7_NCBS | NON DMZ | DC1 | 1 | M1 | 11-10 | 2 | N | A | A-10 | 28-29 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
151 | Physical | Physical | DCDLLDB1RAC7NODE1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | D1KHMY3 | D1KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | SERVER | APP | Dell | PowerEdge 750 | X86 | RHEL | RHEL 8.10 | 10.32.22.196 | 10.32.22.196 | RAC7_NCBS | NON DMZ | DC1 | 1 | M1 | 9-8 | 2 | N | B | B-10 | 22-23 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
152 | Physical | Physical | DCDLLDB1RAC6NODE2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 20KHMY3 | 20KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | APP | Dell | PowerEdge 750 | X86 | RHEL | RHEL 8.10 | 10.32.18.207 | 10.32.18.207 | INTERNET_BANKING_OBDX_DB | NON DMZ | DC1 | 1 | M1 | 7-6 | 2 | N | B | B-10 | 30-31 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
153 | Physical | Physical | DCDLLDB1RAC6NODE1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 71KHMY3 | 71KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | APP | Dell | PowerEdge 750 | X86 | RHEL | RHEL 8.10 | 10.32.18.206 | 10.32.18.206 | INTERNET_BANKING_OBDX_DB | NON DMZ | DC1 | 1 | M1 | 5-4 | 2 | N | A | A-10 | 20-21 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
154 | Physical | Physical | WIN-4JIKE60P6JV |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 90KHMY3 | 90KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | SFTP | Dell | PowerEdge 750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.13.49 | 10.32.13.49 | NCBS_WEB | NON DMZ | DC1 | 1 | M1 | 29-28 | 2 | Y | J | J-07 | 4-5 | Net Rack (X5) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
155 | Physical | Physical | DC-MB-APP11 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | JZJHMY3 | JZJHMY3 | Non-CBS | Production | Online Banking Technology Mobile Banking | MOBILE BANKING |  |  |  | High | SERVER | SERVER | Dell | PowerEdge 750 | X86 | RHEL | 9.4 | 10.32.18.21, fe80::9053:f862:81cb:40b4 | 10.32.203.207 | MB_UPI_APPLICATION | NON DMZ | DC1 | 1 | M1 | 27-26 | 2 | Y | J | J-07 | 6-7 | Net Rack (X5) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
156 | Physical | Physical | dc-dmz-host2.vmcandomain.com |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 3QGL6C2 | 3QGL6C2 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | SERVER | APP | Dell | Dell Power Edge R430 | X86 | WINDOWS | Microsoft Windows Server 2016 | 172.16.38.46 | 172.16.38.46 | Database | NON DMZ | DC1 | 1 | M5 | 27 | 1 | Y | J | J-08 | 20 | Net Rack (X7) | Yes | DCX-BLR512B-2 (B2) | B | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | Live | No |  | Server on SAN fabric – merged SAN batch | Pending | Pending
157 | Physical | Physical | DCNCBSDMZBASE2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | C0KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Low | SERVER | WEB | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.33.201.79 | 172.16.14.140 | DMZ_SERVER_MGMT | NON DMZ | DC1 | 1 | M7 | 05-06 | 2 | Y | L | L-01 | 12-13 | WQ rack (N5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
158 | Physical | Physical | DCNCBSDMZBASE1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | 40KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | WEB | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.33.201.80 | To Be Confirmed | DMZ_SERVER_MGMT | NON DMZ | DC1 | 1 | M7 | 03-04 | 2 | Y | J | J-05 | 12-13 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
159 | Physical | Physical | DCNCBSINTBASE2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | D0KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | To Be Confirmed | To Be Confirmed | 10.32.210.80 | To Be Confirmed | NCBS_SRV_MGMT_2 | NON DMZ | DC1 | 1 | M7 | 01-02 | 2 | Y | J | J-05 | 14-15 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
160 | Physical | Physical | WIN-STLAAFKA5J2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | BKJHMY3 | BKJHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.32.210.70 | 10.32.210.70 | NCBS_SRV_MGMT_2 | NON DMZ | DC1 | 1 | M7 | 28-29 | 2 | Y | J | J-08 | 18-19 | Net Rack (X7) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
161 | Physical | Physical | DCHYPRVBASE1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | 9MJHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | WEB | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.33.192.14 | 10.33.192.14 | DMZ_UAT | NON DMZ | DC1 | 1 | M7 | 11-12 | 2 | Y | J | J-05 | 8-9 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
162 | Physical | Physical | DCHVCLSTRN02 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | B0KHMY3 | B0KHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Rajeev ¦ rajeevkumar.j@canarabank.com |  |  | Medium | SERVER | WEB | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2022 | 10.33.201.71 | 10.33.201.71 | DMZ_SERVER_MGMT | NON DMZ | DC1 | 1 | M7 | 07-08 | 2 | Y | J | J-05 | 10-11 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
163 | Physical | Physical | dwgaipoc |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 60KHMY3 | 60KHMY3 | Non-CBS | Production | Data Warehouse Section | Data Warehouse |  |  |  | High | SERVER | SERVER | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | 9.4 | 10.32.26.244 | 172.16.43.16 | DWH_Sandbox_POC | NON DMZ | DC1 | 1 | M7 | 15-16 | 2 | Y | J | J-05 | 6-7 | Net Rack (U2) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | No | Digital Devices Management Section | amiya@canarabank.com,saurabhsharma4@canarabank.com | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
164 | Physical | Physical | DCNCBSINTBASE1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | CKJHMY3 | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | To Be Confirmed | To Be Confirmed | 10.32.210.79 | 10.32.210.94 | NCBS_SRV_MGMT_2 | NON DMZ | DC1 | 1 | N5 | 28-29 | 2 | Y | I | I-08 | 4-5 | Net Rack (AB4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | To Be Confirmed | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
165 | Physical | Physical | DCIRMSBASE11 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 70KHMY3 | 70KHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.150 | 10.32.210.93 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 26-27 | 2 | Y | I | I-08 | 6-7 | Net Rack (AB4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
166 | Physical | Physical | DCIRMSBASE9 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | G0KHMY3 | G0KHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.148 | 10.32.210.91 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 22-23 | 2 | Y | J | J-05 | 18-19 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
167 | Physical | Physical | DC-B2-N9K-DMZ-TOR-SW |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 12:30 | FLM261608D0 | FLM261608D0 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.33.200.20 | Not Applicable | DMZ_NETWORK_MGMT | DMZ | DC1 | 1 | B2 | 40 | 1 |  | G | G-11 | U19 | New rack | No |  |  | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
168 | Physical | Physical | DC-C1-N9K-ToR-SW-1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 12:30 | FDO22273YZS | FDO22273YZS | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108TC-EX | NA | Not Applicable | Not Applicable | 172.16.39.92 | Not Applicable | Mangement | Internal | DC1 | 1 | C1 | 40 | 1 |  | L | L-11 | U6 | New rack | No |  |  | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
169 | Physical | Physical | DC-C1-N9K-TOR-SW2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 12:30 | FDO2614150K | FDO2614150K | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108TC-EX | NA | Not Applicable | Not Applicable | 10.32.200.79 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C1 | 38 | 1 |  | D | D-10 | U6 | New rack | No |  |  | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
170 | Physical | Physical | DCIRMSBASE8 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 91KHMY3 | 91KHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.147 | 10.32.210.90 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 20-21 | 2 | Y | J | J-05 | 20-21 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
171 | Physical | Physical | DCIRMSBASE7 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | DKJHMY3 | DKJHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.146 | 10.32.210.89 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 18-19 | 2 | Y | I | I-08 | 8-9 | Net Rack (AB4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
172 | Physical | Physical | DCIRMSBASE4 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 50KHMY3 | 50KHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.143 | 10.32.210.86 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 12-13 | 2 | Y | I | I-08 | 14-15 | Net Rack (AB4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
173 | Physical | Physical | DCIRMSBASE2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 7MJHMY3 | 7MJHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.141 | 10.32.210.84 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 08-09 | 2 | Y | J | J-05 | 22-23 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
174 | Physical | Physical | DCIRMSBASE1 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 8KJHMY3 | 8KJHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.140 | 10.32.210.83 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 06-07U | 2 | Y | J | J-05 | 24-25 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
175 | Physical | Physical | DCIRMSBASE10 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 8MJHMY3 | 8MJHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.149 | 10.32.210.92 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 24-25 | 2 | Y | J | J-05 | 16-17 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
176 | Physical | Physical | DCIRMSBASE6 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 74LHMY3 | 74LHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.145 | 10.32.210.88 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 16-17 | 2 | Y | I | I-08 | 10-11 | Net Rack (AB4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
177 | Physical | Physical | DCIRMSBASE5 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 30KHMY3 | 30KHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.144 | 10.32.210.87 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 14-15 | 2 | Y | I | I-08 | 12-13 | Net Rack (AB4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
178 | Physical | Physical | DCIRMSBASE3 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | HZJHMY3 | HZJHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Manash Pathak ¦ 9482460349 ¦ manash.pathak@kyndryl.com | Low | SERVER | APP | Dell | Dell EMC PowerEdge R750 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.32.35.142 | 10.32.210.85 | IRMS_APP | NON DMZ | DC1 | 1 | N5 | 10-11 | 2 | Y | I | I-08 | 16-17 | Net Rack (AB4) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
179 | Physical | Physical | DCPIRMSDB02 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 31KHMY3 | 31KHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Naga Sai ¦ 8074105412 ¦ puttanagasaikumar@kyndryl.com | Low | SERVER | DB | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | RHEL 8.10 | 10.32.34.141 | 10.32.210.82 | IRMS_DB | NON DMZ | DC1 | 1 | N5 | 04-05 | 2 | Y | J | J-05 | 26-27 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
180 | Physical | Physical | DCPIRMSDB01 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 84LHMY3 | 84LHMY3 | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s Kyndryl | Naga Sai ¦ 8074105412 ¦ puttanagasaikumar@kyndryl.com | Low | SERVER | DB | Dell | Dell EMC PowerEdge R750 | X86 | RHEL | RHEL 8.10 | 10.32.34.140 | 10.32.210.81 | IRMS_DB | NON DMZ | DC1 | 1 | N5 | 02-03 | 2 | Y | J | J-05 | 28-29 | Net Rack (U2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
181 | Physical | Physical | localhost |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 3131AG435894 | 3131AG435894 | Non-CBS | Notinuse | Government Business and Financial Inclusion Section | Aadhaar seeding through web |  |  |  | Low | SERVER | APP | HCL | Infinitty global Line 2700CP | X86 | WINDOWS | Microsoft Windows Server 2012 R2 | 172.16.44.71 | 172.16.44.71 | Financial-Inclusion | NON DMZ | DC1 | 1 | O5 | 29-28 | 2 |  |  | Scrap |  |  | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | KARVY INNOTECH LIMITED | ON | Decommissioned | No | Target Rack = Scrap | Server on SAN fabric – merged SAN batch [SCRAP/OOS] | Pending | Pending
182 | Physical | Physical | DCBLR7PRXDV2 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 7PRXDV2 | 7PRXDV2 | Non-CBS | Production | Network Administration Section | NCCM | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com | Inspira | Inspira ¦ Inspira ¦ nmssupport@canarabank.com | High | SERVER | APP | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 10.32.23.156 | 10.32.23.156 | NMS_NCCM_DB | NON DMZ | DC1 | 1 | P1 | 20 | 1 | N | E | E-05 | 21 | New rack | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | No | Non-OEMs | Not Applicable | DELL INTERNATIONAL SERVICES INDIA PVT LTD | On | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
183 | Physical | Physical | DCNCCMDB01 |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 7PRRDV2 | 7PRRDV2 | Non-CBS | Production | Network Administration Section | NCCM | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com | Inspira | Inspira ¦ Inspira ¦ nmssupport@canarabank.com | High | SERVER | APP | Dell | DELL EMC PowerEdge R640 | X86 | RHEL | RHEL 8.10 | 10.32.23.153 | 10.32.23.153 | NMS_NCCM_DB | NON DMZ | DC1 | 1 | P1 | 21 | 1 | N | E | E-05 | 20 | New rack | Yes | DCX-BLR3SSWPC2111 (B2) | A | No | Non-OEMs | Not Applicable | FRONTIER BUSINESS SYSTEMS PVT LTD | On | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
184 | Physical | Physical | EWIRMUATAPPBASE |  | 2 | TR-2.13 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:30 | 7V1N0V3 | 7V1N0V3 | Non-CBS | UAT | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | SERVER | APP | Dell | DELL EMC PowerEdge R650 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 10.33.134.72 | 10.33.134.72 | IRMS_UAT_App | NON DMZ | DC2 | 2 | X2 | 26 | 1 | N | F | F-03 | 24 | New rack | Yes | DCX-BLR512B-1 (B2) | A | No | Non-OEMs | Not Applicable | CITO INFOTECH PVT LTD | On | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
185 | Physical | Physical | DC-A1-N9K-TOR-SW1 |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 6:30 | FDO26141GLU | FDO26141GLU | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108TC-FX | NA | Not Applicable | Not Applicable | 10.32.200.130 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | A1 | 41 | 1 | Y | I | I-11 | U6 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
186 | Physical | Physical | A1-9080-HEX-SN78A1DD8-MIG-1 |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | 78A1DD8 | CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | SERVER | DB | IBM | Power E1080 9080-HEX | IBM Power | AIX | 7.3 TL2 SP2 | 10.32.209.133,10.32.209.134 | 10.32.18.197 | NCBS_DB_NEW | Internal | DC1 | 1 | A1 | 5-6 | 2 | Y | G | G-13 | 27-28 | IBM rack (A1) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
187 | Physical | Physical | A1-9080-HEX-SN78A1DD8-MIG-1 |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | 00000FGD03QK | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | A1 | 17-21 | 5 | Y | G | G-13 | 4-8 | IBM rack (A1) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
188 | Physical | Physical | A1-9080-HEX-SN78A1DD8-MIG-1 |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | 00000FGD03PI | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | A1 | 12-16 | 5 | Y | G | G-13 | 9-13 | IBM rack (A1) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
189 | Physical | Physical | DC78A47CD |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A47CD | 78A47CD | CBS | Production | Data Center Operations Section (ITI) | HMC (NA) |  |  |  | Medium | SERVER | SERVER | IBM | Power HMC | IBM Power | Not Applicable | Not Applicable | 10.32.201.95 | NA | CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | A1 | 23 | 1 | Y | G | G-13 | 30 | IBM rack (A1) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
190 | Physical | Physical | A1-9080-HEX-SN78A1DD8-MIG-1 |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | 00000FGD03PU | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | A1 | 7-11 | 5 | Y | G | G-13 | 14-18 | IBM rack (A1) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
191 | Physical | Physical | DC-A1-N9K-TOR-SW2 |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 6:30 | FDO28130VWK | FDO28130VWK | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.32.200.122 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | A1 | 39 | 1 | Y | G | G-10 | U19 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
192 | Physical | Physical | Not Applicable |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | FZHFY04 | FZHFY04 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | To Be Confirmed | IBM | EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | A1 | 31-34 | 4 | Y | G | G-13 | 19-22 | IBM rack (A1) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
193 | Physical | Physical | Not Applicable |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | FZHFY10 | FZHFY10 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | To Be Confirmed | IBM | EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | A1 | 27-30 | 4 | Y | G | G-13 | 23-26 | IBM rack (A1) | No |  |  | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
194 | Physical | Physical | Not Applicable |  | 2 | TR-2.1 | Loaded in OEM rack A1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | CNB1110959 | CNB1110959 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | SFMS |  |  |  | To Be Confirmed | Monitor | To Be Confirmed | IBM | Console | NA | Not Applicable | Not Applicable | Not Applicable | NA | To Be Confirmed | NON DMZ | DC1 | 1 | A1 | 24 | 1 | Y | G | G-13 | 29 | IBM rack (A1) | No |  |  | Yes | Non-OEMs | Not Applicable | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
195 | Physical | Physical | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DC8 | 78A1DC8 | CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | 10.32.209.135,10.32.2.66,10.32.2.68,10.32.2.12,10.32.2.13,10.32.33.100,10.32.2.20,10.32.205.225 | 10.32.2.68 | HMC1_ATM_SWITCH | Internal | DC1 | 1 | A2 | 5-6 | 2 | Y | G | G-14 | 24-25 | IBM rack (A2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
196 | Physical | Physical | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DC8 | FGD03OO | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | CBS_DB | Internal | DC1 | 1 | A2 | 22-26 | 5 | Y | G | G-14 | 4-8 | IBM rack (A2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
197 | Physical | Physical | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DC8 | FGD03QN | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | CBS_DB | Internal | DC1 | 1 | A2 | 17-21 | 5 | Y | G | G-14 | 9-13 | IBM rack (A2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
198 | Physical | Physical | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DC8 | FGD03QI | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | CBS_DB | Internal | DC1 | 1 | A2 | 12-16 | 5 | Y | G | G-14 | 14-18 | IBM rack (A2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
199 | Physical | Physical | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DC8 | FGD03MS | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | To Be Confirmed | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | CBS_DB | Internal | DC1 | 1 | A2 | 7-11 | 5 | Y | G | G-14 | 19-23 | IBM rack (A2) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
200 | Physical | Physical | DC-A2-N9K-TOR-SW2 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 6:30 | FDO2813133P | FDO2813133P | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-93180YC-FXC | NA | Not Applicable | Not Applicable | 10.32.200.124 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | A2 | 41 | 1 | Y | G | G-10 | U18 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
201 | Physical | Physical | DC-A2-N9K-TOR-SW1 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 6:30 | FDO28140BV3 | FDO28140BV3 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-93180YC-FXC | NA | Not Applicable | Not Applicable | 10.32.200.123 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | A2 | 39 | 1 | Y | G | G-10 | U17 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
202 | Physical | Physical | DC-A2-N9K-RAC-SW3 |  | 2 | TR-2.1 | Loaded in OEM rack A2 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 6:30 | FDO28140BNG | FDO28140BNG | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-93180YC-FXC | NA | Not Applicable | Not Applicable | 10.32.200.128 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | A2 | 37 | 1 | Y | G | Spare | Spare | IBM rack (A2) | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
203 | Physical | Physical | SANINV368 |  | 2 | TR-2.2 | Loaded in OEM rack A5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4G8P | 78E4G8P | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.79 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A5 | 27-28 | 2 | Y | D | D-13 | 8-9 | IBM Rack (A5) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
204 | Physical | Physical | SANINV369 |  | 2 | TR-2.2 | Loaded in OEM rack A5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4B4D | 78E4B4D | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.80 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A5 | 24-25 | 2 | Y | D | D-13 | 10-11 | IBM Rack (A5) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
205 | Physical | Physical | SANINV370 |  | 2 | TR-2.2 | Loaded in OEM rack A5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4N36 | 78E4N36 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.81 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A5 | 21-22 | 2 | Y | D | D-13 | 12-13 | IBM Rack (A5) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
206 | Physical | Physical | SANINV371 |  | 2 | TR-2.2 | Loaded in OEM rack A5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4T96 | 78E4T96 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.82 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A5 | 18-19 | 2 | Y | D | D-13 | 14-15 | IBM Rack (A5) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
207 | Physical | Physical | BLRDCREP_64BG7_SW1 |  | 2 | TR-2.2 | Loaded in OEM rack A5 | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 7:00 | 786711P | 786711P | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Switch 32G | Storage | Brocade | G720 | NA | Not Applicable | Not Applicable | 10.32.202.109 | 10.32.202.109 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A5 | 40 | 1 | Y | D | D-13 | 23 | IBM Rack (A5) | Yes | BLRNDC_64BG7_SW1 (B1) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | SAN switch BLRDCREP_64BG7_SW1 – merged SAN batch | Pending | Pending
208 | Physical | Physical | SANINV376 |  | 2 | TR-2.2 | Loaded in OEM rack A5 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4E54 | 78E4E54 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | Flash System 9500 | NA | Not Applicable | Not Applicable | 10.32.202.88 | 10.32.202.88 10.32.202.89 10.32.202.90 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A5 | 7-10 | 4 | Y | D | D-13 | 4-7 | IBM Rack (A5) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
209 | Physical | Physical | SANINV372 |  | 2 | TR-2.2 | Loaded in OEM rack A6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4T04 | 78E4T04 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.83 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A6 | 27-28 | 2 | Y | C | C-12 | 8-9 | IBM Rack (A6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
210 | Physical | Physical | SANINV373 |  | 2 | TR-2.2 | Loaded in OEM rack A6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4X74 | 78E4X74 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.84 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A6 | 24-25 | 2 | Y | C | C-12 | 10-11 | IBM Rack (A6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
211 | Physical | Physical | SANINV374 |  | 2 | TR-2.2 | Loaded in OEM rack A6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4W21 | 78E4W21 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.85 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A6 | 21-22 | 2 | Y | C | C-12 | 12-13 | IBM Rack (A6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
212 | Physical | Physical | SANINV375 |  | 2 | TR-2.2 | Loaded in OEM rack A6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4B1H | 78E4B1H | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.86 | 10.32.202.15 10.32.202.16 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A6 | 18-19 | 2 | Y | C | C-12 | 14-15 | IBM Rack (A6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
213 | Physical | Physical | Not Applicable |  | 2 | TR-2.2 | Loaded in OEM rack A6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4F19 | 78E4F19 | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | Storage Controller | Storage | IBM | SAN Volume Controller | NA | Not Applicable | Not Applicable | 10.32.202.87 | 10.32.202.87 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | A6 | 15-16 | 2 | Y | C | C-12 | 16-17 | IBM Rack (A6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
214 | Physical | Physical | BLRDCREP_64BG7_SW2 |  | 2 | TR-2.2 | Loaded in OEM rack A6 | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 7:00 | 786711C | 786711C | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Switch 32G | Storage | Brocade | G720 | NA | Not Applicable | Not Applicable | 10.32.202.110 | 10.32.202.110 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A6 | 40 | 1 | Y | C | C-12 | 23 | IBM Rack (A6) | Yes | BLRNDC_64BG7_SW2 (B1) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | SAN switch BLRDCREP_64BG7_SW2 – merged SAN batch | Pending | Pending
215 | Physical | Physical | SANINV377 |  | 2 | TR-2.2 | Loaded in OEM rack A6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 7:00 | 78E4V30 | 78E4V30 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | Flash System 9500 | NA | Not Applicable | Not Applicable | 10.32.202.91 | 10.32.202.91 10.32.202.92 10.32.202.93 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | A6 | 7-10 | 4 | Y | C | C-12 | 4-7 | IBM Rack (A6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
216 | Physical | Physical | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 12:30 | 78A1DE8 | 78A1DE8 | Non-CBS | Production | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | SERVER | Core DB | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | 10.32.209.137 | 10.32.2.69 | HMC1_ATM_SWITCH | Internal | DC1 | 1 | C3 | 5-6 | 2 | Y | H | H-14 | 24-25 | IBM rack (C3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
217 | Physical | Physical | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 12:30 | 78A1DE8 | 00000FGD03PV | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | Core DB | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C3 | 22-26 | 5 | Y | H | H-14 | 4-8 | IBM rack (C3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
218 | Physical | Physical | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 12:30 | 78A1DE8 | 00000FGD03R7 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | Core DB | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C3 | 12-16 | 5 | Y | H | H-14 | 14-18 | IBM rack (C3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
219 | Physical | Physical | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 12:30 | 78A1DE8 | 00000FGD03R5 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | Core DB | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C3 | 17-21 | 5 | Y | H | H-14 | 9-13 | IBM rack (C3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
220 | Physical | Physical | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 5:00 | 2026-10-24 | 6:00 | 12:30 | 78A1DE8 | 00000FGD03QE | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | Core DB | IBM | Power E1080 | IBM Power | AIX | 7.3 TL2 SP2 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C3 | 7-11 | 5 | Y | H | H-14 | 19-23 | IBM rack (C3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
221 | Physical | Physical | DC-C3-N9K-TOR-SW2 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 12:30 | FDO28140BUK | FDO28140BUK | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | Core DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.32.200.126 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C3 | 41 | 1 | Y | H | H-10 | U18 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
222 | Physical | Physical | DC-C3-N9K-TOR-SW1 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 12:30 | FDO28130JMK | FDO28130JMK | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | Core DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.32.200.125 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C3 | 39 | 1 | Y | G | G-11 | U17 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
223 | Physical | Physical | DC-C3-N9K-RAC-SW3 |  | 1 | TR-1 | Loaded in OEM rack C3 | 2026-10-24 | 6:30 | 2026-10-24 | 6:00 | 12:30 | FDO2813130Y | FDO2813130Y | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | Core DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.32.200.129 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C3 | 37 | 1 | Y | H | H-10 | U19 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Batch 1 – AIX P10 frame 78A1DE8 (rack C3) moved to Batch 1 as requested; rack C3 travels loaded with all its devices | Pending | Pending
224 | Physical | Physical | C4-9080-HEX-SN78A1DF8-MIG-2 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | 78A1DF8 | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.2 TL5 SP8 | 10.32.209.139 | NA | HMC1_ATM_SWITCH | Internal | DC1 | 1 | C4 | 5-6 | 2 | Y | H | H-13 | 27-28 | IBM rack (C4) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
225 | Physical | Physical | C4-9080-HEX-SN78A1DF8-MIG-2 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | 00000FGD047E | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.2 TL5 SP8 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C4 | 17-21 | 5 | Y | H | H-13 | 4-8 | IBM rack (C4) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
226 | Physical | Physical | C4-9080-HEX-SN78A1DF8-MIG-2 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | 00000FGD049K | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.2 TL5 SP8 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C4 | 12-16 | 5 | Y | H | H-13 | 9-13 | IBM rack (C4) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
227 | Physical | Physical | C4-9080-HEX-SN78A1DF8-MIG-2 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | 00000FGD048Z | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | DB | IBM | Power E1080 | IBM Power | AIX | 7.2 TL5 SP8 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C4 | 7-11 | 5 | Y | H | H-13 | 14-18 | IBM rack (C4) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
228 | Physical | Physical | C4-9080-HEX-SN78A1DF8-MIG-2 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | 00000FZHFU04 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C4 | 31-34 | 4 | Y | H | H-13 | 19-22 | IBM rack (C4) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
229 | Physical | Physical | C4-9080-HEX-SN78A1DF8-MIG-2 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | 00000FZHFU03 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C4 | 27-30 | 4 | Y | H | H-13 | 23-26 | IBM rack (C4) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
230 | Physical | Physical | DC-C4-N9K-TOR-SW1 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 7:30 | FDO261414G3 | FDO261414G3 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | DB | Cisco | N9K-C93108TC-EX | NA | Not Applicable | Not Applicable | 10.32.200.131 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C4 | 41 | 1 | Y | D | D-11 | U6 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
231 | Physical | Physical | DC-C4-N9K-TOR-SW2 |  | 2 | TR-2.3 | Loaded in OEM rack C4 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 7:30 | FDO28140BNC | FDO28140BNC | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.32.200.127 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C4 | 39 | 1 | Y | H | H-11 | U18 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
232 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 00000CSS553C | Non-CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C5 | 22-26 | 5 | Y | G | G-17 | 4-8 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
233 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 00000CSS554A | Non-CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C5 | 17-21 | 5 | Y | G | G-17 | 9-13 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
234 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 00000CSS30DF | Non-CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C5 | 12-16 | 5 | Y | G | G-17 | 14-18 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
235 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 00000CSS2EDE | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C5 | 07-11 | 5 | Y | G | G-17 | 19-23 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
236 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 00000FZHZ764 | CBS | Notinuse | Data Center Operations Section (ITI) | SFMS |  |  |  | Medium | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C5 | 35-38 | 4 | Y | G | G-17 | 24-27 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
237 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 00000FZHZ016 | CBS | Notinuse | Data Center Operations Section (ITI) | SFMS |  |  |  | Medium | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C5 | 31-34 | 4 | Y | G | G-17 | 28-31 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
238 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 00000FZHZ022 | CBS | Notinuse | Data Center Operations Section (ITI) | SFMS |  |  |  | Medium | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C5 | 27-30 | 4 | Y | G | G-17 | 32-35 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
239 | Physical | Physical | Server2-9080-M9S-SN783BFC8 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | 783BFC8 | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | High | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.26,10.32.207.25 | 172.16.11.132 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | C5 | 05-06 | 2 | Y | G | G-17 | 36-37 | IBM rack (C5) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
240 | Physical | Physical | DC-C5-N9K-TOR-SW N9K-C93180YC-FX3 |  | 2 | TR-2.4 | Loaded in OEM rack C5 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 8:00 | FDO281313BE | FDO281313BE | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.32.200.141 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C5 | 40 | 1 | Y | H | H-10 | U17 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
241 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 783BFE8 | CBS | Production | Government Business and Financial Inclusion Section | Not Applicable | Not Applicable |  |  | High | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.28 | 172.16.11.131 | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | C6 | 5-6 | 2 | Y | H | H-17 | 36-37 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
242 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 00000CSS5503 | CBS | To Be Confirmed | Government Business and Financial Inclusion Section | Not Applicable | arundhatikatolkar@canarabank.com |  |  | To Be Confirmed | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C6 | 17-21 | 5 | Y | H | H-17 | 9-13 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
243 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 00000FZHY908 | CBS | To Be Confirmed | Government Business and Financial Inclusion Section | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C6 | 35-38 | 4 | Y | H | H-17 | 24-27 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
244 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 00000FZHY979 | CBS | To Be Confirmed | Government Business and Financial Inclusion Section | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C6 | 31-34 | 4 | Y | H | H-17 | 28-31 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
245 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 00000FZHY985 | CBS | To Be Confirmed | Government Business and Financial Inclusion Section | SFMS |  |  |  | To Be Confirmed | IO Expansion Drawer | DB | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | C6 | 27-30 | 4 | Y | H | H-17 | 32-35 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
246 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 00000CSS554F | CBS | To Be Confirmed | Government Business and Financial Inclusion Section | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C6 | 22-26 | 5 | Y | H | H-17 | 4-8 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
247 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 00000CSS310A | CBS | To Be Confirmed | Government Business and Financial Inclusion Section | Not Applicable | Not Applicable |  |  | To Be Confirmed | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C6 | 12-16 | 5 | Y | H | H-17 | 14-18 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
248 | Physical | Physical | Server1-9080-M9S-SN783BFE8 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | 00000CSS2D7C | CBS | To Be Confirmed | Government Business and Financial Inclusion Section | Not Applicable | LEEMA ROSELIN K 9741644668 |  |  | To Be Confirmed | SERVER | DB | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | C6 | 7-11 | 5 | Y | H | H-17 | 19-23 | IBM rack (C6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
249 | Physical | Physical | Not Applicable |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 8:00 | AJ29019530 | AJ29019530 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Network-Switch | DB | Juniper | OFX5200-48Y | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | C6 | 42 | 1 | Y | H | Spare | Spare | IBM rack (C6) | No |  |  | Yes | Non-OEMs | Not Applicable | To Be Confirmed | OFF | OFF | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
250 | Physical | Physical | DC-C6-N9K-TOR-SW N9K-C93180YC-FX3 |  | 2 | TR-2.4 | Loaded in OEM rack C6 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 8:00 | FDO28140BQT | FDO28140BQT | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | DB | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.32.200.142 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | C6 | 40 | 1 | Y | H | H-11 | U19 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
251 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D3 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 78E4Z6R | 78E4Z6R | CBS | UAT | Data Center Operations Section (ITI) | UATP10 Storage Boxes |  |  |  | High | Storage Controller | Storage | IBM | Flash System 9500 | NA | Not Applicable | Not Applicable | 10.32.202.117 | 10.32.202.117 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | D3 | 16-13 | 4 | Y | D | D-09 | 4-7 | IBM Rack (D3) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | Not in production | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
252 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D3 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 78E4Z6F | 78E4Z6F | CBS | UAT | Data Center Operations Section (ITI) | UATP10 Storage Boxes |  |  |  | High | Storage Controller | Storage | IBM | Flash System 9500 | NA | Not Applicable | Not Applicable | 10.32.202.120 | 10.32.202.120 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | D3 | 07-04 | 4 | Y | D | D-09 | 8-11 | IBM Rack (D3) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | M/s Pentagon System and Services Pvt. Ltd. | ON | Not in production | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
253 | Physical | Physical | SANINV361 |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 78E3KFT | 78E3KFT | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | FLASH SYSTEM 7300 | NA | Not Applicable | Not Applicable | 10.32.202.94 | 10.32.202.94 10.32.202.95 10.32.202.96 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | D6 | 05-06 | 2 | Y | C | C-07 | 16-17 | IBM Rack (D6) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
254 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 7810KX3 | 7810KX3 | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | High | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | 10.32.202.100 | 10.32.202.100 10.32.202.101 10.32.202.102 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | D6 | 21-22 | 2 | Y | C | C-07 | 4-5 | IBM Rack (D6) | No |  |  | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
255 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 7810KT2 | 7810KT2 | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | High | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | 10.32.202.100 | 10.32.202.100 10.32.202.101 10.32.202.102 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | D6 | 17-18 | 2 | Y | C | C-07 | 8-9 | IBM Rack (D6) | No |  |  | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
256 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 7810KT4 | 7810KT4 | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | High | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | 10.32.202.97 | 10.32.202.94 10.32.202.95 10.32.202.96 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | D6 | 11-12 | 2 | Y | C | C-07 | 12-13 | IBM Rack (D6) | No |  |  | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
257 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 7810KR5 | 7810KR5 | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | High | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | 10.32.202.94 | 10.32.202.94 10.32.202.95 10.32.202.96 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | D6 | 07-08 | 2 | Y | C | C-07 | 14-15 | IBM Rack (D6) | No |  |  | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
258 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 7810KX7 | 7810KX7 | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | High | Storage Controller | Storage | IBM | Flash System 7000 | NA | Not Applicable | Not Applicable | 10.32.202.94 | 10.32.202.94 10.32.202.95 10.32.202.96 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | D6 | 03-04 | 2 | Y | C | C-07 | 18-19 | IBM Rack (D6) | No |  |  | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
259 | Physical | Physical | Not Applicable |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 78E3K6H | 78E3K6H | CBS | Production | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | High | Storage Controller | Storage | IBM | FLASH SYSTEM 7300 | NA | Not Applicable | Not Applicable | 10.32.202.100 | 10.32.202.100 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | D6 | 19-20 | 2 | Y | C | C-07 | 6-7 | IBM Rack (D6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Live | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
260 | Physical | Physical | SANINV362 |  | 2 | TR-2.6 | Loaded in OEM rack D6 | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 9:00 | 78E3KDF | 78E3KDF | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Controller | Storage | IBM | FLASH SYSTEM 7300 | NA | Not Applicable | Not Applicable | 10.32.202.97 | 10.32.202.97 10.32.202.98 10.32.202.99 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | D6 | 13-14 | 2 | Y | C | C-07 | 10-11 | IBM Rack (D6) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM Support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
261 | Physical | Physical | SANINV172 |  | 2 | TR-2 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 6:00 | 483313 | 483313 | Non-CBS | UAT | Data Center Operations Section (ITI) | No application installed |  |  |  | Medium | Storage Management Server | Storage | Hitachi | SFRSVP | NA | Not Applicable | Not Applicable | 10.32.202.44 | 10.32.202.44 | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | F5 | 42 | 1 | Y | D | D-06 | 25 | WQ Rack (AC6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Hitachi support | siva.nallamothu@hitachivantara.com | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
262 | Physical | Physical | DCHNAS5200-N2 |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | C1A1KW2304376 | C1A1KW2304376 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) |  |  |  |  | To Be Confirmed | SERVER | To Be Confirmed | Hitachi | CFB1100 | X86 | To Be Confirmed | To Be Confirmed | 10.32.202.55,10.32.202.56 | 10.32.202.57 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | F5 | 31-33 | 3 | Y | D | D-06 | 18-20 | WQ Rack (AC6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Hitachi support | siva.nallamothu@hitachivantara.com | To Be Confirmed | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
263 | Physical | Physical | DCHNAS5200-N1 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | C1A1KW2304258 | C1A1KW2304258 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage | To Be Confirmed | Hitachi | MDKC810I-SBX | X86 | To Be Confirmed | To Be Confirmed | 10.32.202.53,10.32.202.54 | 10.32.202.57 | CBS_STORAGE_MGMT | Internal | DC1 | 1 | F5 | 28-30 | 3 | Y | D | D-06 | 21-23 | WQ Rack (AC6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Hitachi support | siva.nallamothu@hitachivantara.com | To Be Confirmed | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
264 | Physical | Physical | Not Applicable |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 483313 | F077103H8LE19380132 | Non-CBS | UAT | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | Storage Array | Storage | Hitachi | Virtual Storage Plateform G350 | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | F5 | 40-41 | 2 | Y | D | D-06 | 16-17 | WQ Rack (AC6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Hitachi support | siva.nallamothu@hitachivantara.com | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
265 | Physical | Physical | Not Applicable |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 483313 | F077103H8LE19380209 | Non-CBS | UAT | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | Storage Array | Storage | Hitachi | Virtual Storage Plateform G350 | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | F5 | 38-39 | 2 | Y | D | D-06 | 14-15 | WQ Rack (AC6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Hitachi support | siva.nallamothu@hitachivantara.com | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
266 | Physical | Physical | SANINV383 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 612909 | 612909 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Array | Storage | Hitachi | Virtual Storage E790 | NA | Not Applicable | Not Applicable | 10.32.202.71 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | F6 | 07-08 | 2 | Y | D | D-06 | 4-6 | WQ Rack (AC6) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Hitachi support | siva.nallamothu@hitachivantara.com | To Be Confirmed | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
267 | Physical | Physical | DCCSW02SFMSNEFT |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | WZP23050K70 | WZP23050K70 | Non-CBS | Production | Service Unit Section | SFMS | DEBJOY ROY ¦ 9874753518 ¦ AAQ_CanaraBank_NEFT_RTGS.xlsx | IFTAS | IFTAS (RBI SUBSIDIARY ) ¦ 914047524085 ¦ sfms.team@iftas.in | High | SERVER | APP | Cisco | UCS C220 M5 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 172.16.32.121 | 172.16.32.121 | SFMS-NEFT | NON DMZ | DC1 | 1 | F6 | 27 | 1 | Y | D | D-14 | 26 | WQ Rack (AD2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Non-OEMs | Not Applicable | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
268 | Physical | Physical | SANINV383 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | F077103H8LE22120246 | F077103H8LE22120246 | Non-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage Array | Storage | Hitachi | VSP E790 | NA | Not Applicable | Not Applicable | 10.32.202.71 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | F6 | 09-10 | 2 | Y | D | D-06 | 7-9 | WQ Rack (AC6) | No |  |  | Yes | Lailesh to verify |  | To Be Confirmed | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
269 | Physical | Physical | SANINV383 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 22:00 | 2026-10-25 | 0:30 | 11:30 | 810675 | 810675 | NON-CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | Storage | Storage | Hitachi | Lumada Ready | NA | Not Applicable | Not Applicable | 10.32.202.71 | NA | CBS_STORAGE_MGMT | Internal | DC1 | 1 | F6 | 30-29 | 2 | Y | D | D-06 | 10-11 | WQ Rack (AC6) | Yes | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | Hitachi support | siva.nallamothu@hitachivantara.com | To Be Confirmed | ON | ON | Yes |  | Storage on SAN fabric – merged SAN batch | Pending | Pending
270 | Physical | Physical | DCCSW01SFMSNEFT |  | 2 | TR-2.12 | Unracked (loose) | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 12:00 | WZP23050K8T | WZP23050K8T | NON-CBS | Production | Service Unit Section | SFMS |  |  |  | High | SERVER | APP | Cisco | UCS C220 M5 | X86 | WINDOWS | Microsoft Windows Server 2019 Standard | 172.16.32.120 | 172.16.32.120 | SFMS-NEFT | NON DMZ | DC1 | 1 | F6 | 28 | 1 | Y | D | D-14 | 17 | WQ Rack (AD2) | Yes | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | Yes | Non-OEMs | Not Applicable | HITACHI SYSTEMS MICRO CLINIC PVT LTD | ON | Live | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
271 | Physical | Physical | DCX-BLR3SSWPC2111 |  | 2 | TR-2.7 | Loaded in OEM rack F7 | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 9:30 | 10194GB | 10194GB | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Director | Storage | IBM | DCX-8510-8-IBM- SAN Director 16G | NA | Not Applicable | Not Applicable | 172.16.38.233 | NA | Database | Internal | DC1 | 1 | F7 | 34-21 | 14 | Y | F | F-15 | 4-17 | IBM Rack (A4) | Yes | DCX-BLR512B-1 (B2) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | SAN switch DCX-BLR3SSWPC2111 – merged SAN batch | Pending | Pending
272 | Physical | Physical | DCX-BLR3SSWPC2112 |  | 2 | TR-2.11 | Unracked (loose) | 2026-10-24 | 23:30 | 2026-10-25 | 0:30 | 11:30 | 10194DD | 10194DD | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | To Be Confirmed | SAN Director | Storage | IBM | DCX-8510-8-IBM -SAN Diretcor 16G | NA | Not Applicable | Not Applicable | 172.16.38.236 | NA | Database | Internal | DC1 | 1 | G7 | 34-21 | 14 | Y | E | E-02 | 4-17 | New rack | Yes | DCX-BLR512B-2 (B2) | switch | Yes | IBM support | chandramohan.k@in.ibm.com | To Be Confirmed | ON | ON | Yes |  | SAN switch DCX-BLR3SSWPC2112 – merged SAN batch | Pending | Pending
273 | Physical | Physical | E980-1-9080-M9S-SN78414F8 |  | 2 | TR-2.7 | Loaded in OEM rack K1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | 78414F8 | CBS | Notinuse | Data Center Operations Section (ITI) | CBS Allied Application |  |  |  | Medium | SERVER | APP | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.19 | 10.32.207.19 | HMC_CBS_SERVER_MGMT | NON DMZ | DC1 | 1 | K1 | 9-10 | 2 | Y | H | H-08 | 32-33 | IBM rack (K3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | Shutdown | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
274 | Physical | Physical | E980-1-9080-M9S-SN78414F8 |  | 2 | TR-2.7 | Loaded in OEM rack K1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | SN00000FZHFX84 | CBS | Notinuse | Data Center Operations Section (ITI) | SFMS |  |  |  | Medium | IO Expansion Drawer | To Be Confirmed | IBM | FC EMX0 | NA | Not Applicable | Not Applicable | Not Applicable | NA | NA | NON DMZ | DC1 | 1 | K1 | 31-34 | 4 | Y | H | H-08 | 24-27 | IBM rack (K3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
275 | Physical | Physical | E980-1-9080-M9S-SN78414F8 |  | 2 | TR-2.7 | Loaded in OEM rack K1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | SN00000CSS32BF | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K1 | 26-30 | 5 | Y | H | H-08 | 4-8 | IBM rack (K3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
276 | Physical | Physical | E980-1-9080-M9S-SN78414F8 |  | 2 | TR-2.7 | Loaded in OEM rack K1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | CSS2FAD | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K1 | 21-25 | 5 | Y | H | H-08 | 9-13 | IBM rack (K3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
277 | Physical | Physical | E980-1-9080-M9S-SN78414F8 |  | 2 | TR-2.7 | Loaded in OEM rack K1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | CSS32F7 | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K1 | 16-20 | 5 | Y | H | H-08 | 14-18 | IBM rack (K3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
278 | Physical | Physical | E980-1-9080-M9S-SN78414F8 |  | 2 | TR-2.7 | Loaded in OEM rack K1 | 2026-10-24 | 21:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | CSS340A | CBS | Notinuse | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | Medium | SERVER | To Be Confirmed | IBM | Power E980 | IBM Power | AIX | 7.2 TL5 SP7 | Not Applicable | NA | To Be Confirmed | To Be Confirmed | DC1 | 1 | K1 | 11-15 | 5 | Y | H | H-08 | 19-23 | IBM rack (K3) | Yes | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | Yes | IBM support | chandramohan.k@in.ibm.com | IBM INDIA PVT LTD | ON | ON | Yes |  | Server on SAN fabric – merged SAN batch | Pending | Pending
279 | Physical | Physical | DC-K1-N9K-TOR-SW1 |  | 2 | TR-2.7 | Loaded in OEM rack K1 | 2026-10-25 | 0:00 | 2026-10-25 | 0:30 | 9:30 | FDO241208W1 | FDO241208W1 | CBS | To Be Confirmed | Data Center Operations Section (ITI) | Not Applicable | Not Applicable |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93108YC-FX | NA | Not Applicable | Not Applicable | 10.32.200.4 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | K1 | 42 | 1 | Y | A | A-08 | U4 | New rack | No |  |  | Yes | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | ON | Yes |  | Rack/ToR group of SAN devices – merged SAN batch | Pending | Pending
280 | Physical | Physical | CAN-DC-CELL7 |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 22:15 | 2026-10-25 | 9:30 | 12:00 | FNHTN24 | FNHTN24 | Non-CBS | Notinuse | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | SERVER | APP | Dell | Dell Poweredge R760 | X86 | NA | NA | 172.16.3.234 | 10.32.212.118 | D2D_DATA | NON DMZ | DC1 | 1 | G3 | 12-13 | 2 | Y | I | I-06 | 22-23 | Net Rack (AA5) | No |  |  | No | Non-OEMs | Harsha.Vardhan5@Dell.com | Dynacons Systems and Solutions Limited | ON | Staging | Yes |  | Standalone – no SAN connectivity | Pending | Pending
281 | Physical | Physical | Not Applicable |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | 697640 | 697640 | CBS | Production | Online Banking Technology Mobile Banking | HSM |  |  |  | High | Security Appliance | To Be Confirmed | Thales | Luna HSM | NA | Not Applicable | Not Applicable | 10.32.18.69 | 10.32.18.69 | OMNI_APP | Internal | DC1 | 1 | G3 | 27 | 1 | N | D | D-10 |  | New rack | No |  |  | No | Online Banking Technology Mobile Banking | kirankumard@kyndryl.com | INTEGRA MICRO SYSTEMS PVT LTD | ON | Live | Yes |  | Standalone – no SAN connectivity | Pending | Pending
282 | Physical | Physical | Server-8284-22A-SN84B6FAW |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 22:15 | 2026-10-25 | 9:30 | 12:00 | 84B6FAW | 84B6FAW | Non-CBS | Production | Service Unit Section | Not Applicable | Not Applicable |  |  | Low | SERVER | To Be Confirmed | IBM | Power S822 | IBM Power | AIX | 7.2 TL5 SP7 | 10.32.207.37 | NA | HMC_CBS_SERVER_MGMT | Internal | DC1 | 1 | G3 | 16-17 | 2 |  |  | OOS |  |  | No |  |  | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | Live | No | Target Rack = OOS | Standalone – no SAN connectivity [SCRAP/OOS] | Pending | Pending
283 | Physical | Physical | DCDBSYNFRS |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 22:15 | 2026-10-25 | 9:30 | 12:00 | 1PG5MP2 | 1PG5MP2 | Non-CBS | Production | Data Warehouse Section | Data Warehouse |  |  |  | Medium | SERVER | APP | Dell | DELL EMC POWER EDGE R740 | X86 | RHEL | RHEL 8.10 | 10.32.25.5 | 10.32.210.114 | NCBS_ARCHIVAL_DB | NON DMZ | DC1 | 1 | G6 | 26-27 | 2 | Y | K | K-08 | 8-9 | WQ rack (M1) | No |  |  | No | Non-OEMs | Not Applicable | DELL INTERNATIONAL SERVICES INDIA PVT LTD | ON | Live | Yes |  | Standalone – no SAN connectivity | Pending | Pending
284 | Physical | Physical | DC-H2-P2 CLOUDSTATION |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | CS801400000012 | CS801400000012 | Non-CBS | Production | Network Administration Section | SDWAN |  |  |  | High | NW-Server | To Be Confirmed | LAVELLE NETWORKS | H-CS-XL-4E-R4A2U | To Be Confirmed | To Be Confirmed | To Be Confirmed | 10.37.0.6 | To Be Confirmed | SD WAN | Cloud | DC1 | 1 | H2 | 09-10 | 2 | N | F | F-07 | 4-5 | New rack | No |  |  | No | Non-OEMs |  | BHARTI AIRTEL | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
285 | Physical | Physical | UATWEB-OTP |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 22:15 | 2026-10-25 | 9:30 | 11:30 | WZP22190GCS | WZP22190GCS | CBS | UAT | Online Banking Technology Net banking Section | WEB-OTP |  |  | To Be Confirmed | HITACHI SYSTEMS MICRO CLINIC PVT LTD | SERVER | 172.16.14.170 | Cisco | UCS C220 M5 | Pending | 43291 | DIT-AP and M-ORD-57-2018-19 dated 10.07.2018 |  | Capex | 47056 | Yes | DC1 | 1 | M4 | 29 | 1 | Y | D | D-14 | 20 | WQ Rack (AD2) | No |  |  |  | VIVEK 919786261374 vivek.r@canarabank.com | MANIPAL TECHNOLOGY SUBRAMANIYAM 9741797150 offlineotp@canarabank.com | Not Applicable | ON | Live | Yes |  | Standalone – no SAN connectivity | Pending | Pending
286 | Physical | Physical | canamluat |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | 12DGGQ00100002 | 12DGGQ00100002 | CBS | UAT | FCUBS | OmniEnterprises AML Solution | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | MADHAVI GEDELA | 6304027118 ¦ madhavi.gedela@kiya.ai | Low | Power-Backup system | APP | Wipro | netpower datacentre system |  | WINDOWS | Microsoft Windows Server 2016 Standard | 172.16.45.215 | 172.16.45.215 | NON-CBS | NON DMZ | DC-Gr | Ground | V3 | 20 | 1 |  |  | NA |  |  | No |  |  | No | Non-OEMs | Not Applicable | KARVY INNOTECH LIMITED | ON | Live | Yes | Comments mention scrap | Standalone – no SAN connectivity [SCRAP/OOS] | Pending | Pending
287 | Physical | Physical | candcex300ecs1d1.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | C6DBTZ3 | C6DBTZ3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.104 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W3 | 13-12 | 2 | Y | G | G-05 | 4-5 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
288 | Physical | Physical | candcex300ecs1d10.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | D6DBTZ3 | D6DBTZ3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.113 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W3 | 11-10 | 2 | Y | G | G-05 | 6-7 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
289 | Physical | Physical | candcex300ecs1d11.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | F6DBTZ3 | F6DBTZ3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.114 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W3 | 9-8 | 2 | Y | G | G-05 | 8-9 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
290 | Physical | Physical | candcex300ecs1d2.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | J5DBTZ3 | J5DBTZ3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.105 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W3 | 7-6 | 2 | Y | G | G-05 | 10-11 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
291 | Physical | Physical | candcex300ecs1d3.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | B6DBTZ3 | B6DBTZ3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.106 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W3 | 5-4 | 2 | Y | G | G-05 | 12-13 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
292 | Physical | Physical | candcex300ecs1d4.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | 96DBTZ3 | 96DBTZ3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.107 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W3 | 3-2 | 2 | Y | G | G-05 | 14-15 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | Kyndryl Solutions Private Limited | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
293 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 8RM4SR3 | 8RM4SR3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5248F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W3 | 22 | 1 | Y | G | G-05 | 23 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
294 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 8RF8SR3 | 8RF8SR3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5248F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W3 | 20 | 1 | Y | G | G-05 | 24 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
295 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 8RF6SR3 | 8RF6SR3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5248F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W3 | 18 | 1 | Y | G | G-05 | 25 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
296 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 8RD6SR3 | 8RD6SR3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5248F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W3 | 16 | 1 | Y | G | G-05 | 26 | Dell Rack (W3) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
297 | Physical | Physical | candcex300ecs1d5.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | 10QLV03 | 10QLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.108 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 30-29 | 2 | Y | G | G-04 | 4-5 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
298 | Physical | Physical | candcex300ecs1d6.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | JZPLV03 | JZPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.109 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 28-27 | 2 | Y | G | G-04 | 6-7 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
299 | Physical | Physical | candcex300ecs1d7.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | HZPLV03 | HZPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.110 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 26-25 | 2 | Y | G | G-04 | 8-9 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
300 | Physical | Physical | candcex300ecs1d8.aranac.com |  | 3 | TR-3 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 11:30 | 30QLV03 | 30QLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.111 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 24-23 | 2 | Y | G | G-04 | 10-11 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
301 | Physical | Physical | candcex300ecs1d9.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | FZPLV03 | FZPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.112 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 15-14 | 2 | Y | G | G-04 | 12-13 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
302 | Physical | Physical | candcex300ecs2d1.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 20QLV03 | 20QLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.115 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 13-12 | 2 | Y | G | G-04 | 14-15 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
303 | Physical | Physical | candcex300ecs2d10.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | GZPLV03 | GZPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.124 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 11-10 | 2 | Y | G | G-04 | 16-17 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
304 | Physical | Physical | candcex300ecs2d2.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | DZPLV03 | DZPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.116 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 9-8 | 2 | Y | G | G-04 | 18-19 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
305 | Physical | Physical | candcex300ecs2d3.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | BWTLV03 | BWTLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.117 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 7-6 | 2 | Y | G | G-04 | 20-21 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
306 | Physical | Physical | candcex300ecs2d4.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 7HLLV03 | 7HLLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.118 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 5-4 | 2 | Y | G | G-04 | 22-23 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
307 | Physical | Physical | candcex300ecs2d5.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 9WTLV03 | 9WTLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.119 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W4 | 3-2 | 2 | Y | G | G-04 | 24-25 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
308 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 9435SR3 | 9435SR3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5248F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W4 | 36 | 1 | Y | G | G-04 | 26 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
309 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 9434SR3 | 9434SR3 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5248F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W4 | 34 | 1 | Y | G | G-04 | 27 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
310 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 30YB9Z2 | 30YB9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W4 | 22 | 1 | Y | G | G-04 | 28 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
311 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 30XD9Z2 | 30XD9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W4 | 20 | 1 | Y | G | G-04 | 29 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
312 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 30YC9Z2 | 30YC9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W4 | 18 | 1 | Y | G | G-04 | 30 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
313 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 310C9Z2 | 310C9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W4 | 16 | 1 | Y | G | G-04 | 31 | Dell Rack (W4) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
314 | Physical | Physical | candcex300ecs2d6.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | B0QLV03 | B0QLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.120 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 28-27 | 2 | Y | G | G-03 | 4-5 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
315 | Physical | Physical | candcex300ecs2d7.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 8XPLV03 | 8XPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.121 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 26-25 | 2 | Y | G | G-03 | 6-7 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
316 | Physical | Physical | candcex300ecs2d8.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 3ZPLV03 | 3ZPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.122 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 24-23 | 2 | Y | G | G-03 | 8-9 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
317 | Physical | Physical | candcex300ecs2d9.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | DYPLV03 | DYPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.123 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 15-14 | 2 | Y | G | G-03 | 10-11 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
318 | Physical | Physical | candcex500ecs3d1.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | JYPLV03 | JYPLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.75 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 13-12 | 2 | Y | G | G-03 | 12-13 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
319 | Physical | Physical | candcex500ecs3d2.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 5WTLV03 | 5WTLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.76 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 11-10 | 2 | Y | G | G-03 | 14-15 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
320 | Physical | Physical | candcex500ecs3d3.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 3WTLV03 | 3WTLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.77 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 9-8U | 2 | Y | G | G-03 | 16-17 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
321 | Physical | Physical | candcex500ecs3d4.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 7WTLV03 | 7WTLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.78 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 7-6 | 2 | Y | G | G-03 | 18-19 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
322 | Physical | Physical | candcex500ecs3d5.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | 4WTLV03 | 4WTLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.79 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 5-4 | 2 | Y | G | G-03 | 20-21 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
323 | Physical | Physical | candcex500ecs3d6.aranac.com |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | HJLLV03 | HJLLV03 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | ECS PowerEdge R740xd2 | NA | Not Applicable | Not Applicable | 10.32.24.80 | NA | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W5 | 3-2 | 2 | Y | G | G-03 | 22-23 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
324 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 25JD9Z2 | 25JD9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W5 | 22 | 1 | Y | G | G-03 | 24 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
325 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 25CD9Z2 | 25CD9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W5 | 20 | 1 | Y | G | G-03 | 25 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
326 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 25GC9Z2 | 25GC9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W5 | 18 | 1 | Y | G | G-03 | 26 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
327 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 25KD9Z2 | 25KD9Z2 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Network-Switch | To Be Confirmed | Dell | S5148F-ON | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC2 | 2 | W5 | 16 | 1 | Y | G | G-03 | 27 | Dell Rack (W5) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
328 | Physical | Physical | Not Applicable |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | FCNCA191702270 | FCNCA191702270 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W7 | 21-18 | 4 | Y | H | H-05 | 8-11 | WQ Rack (AF2) | No |  |  | Yes | Lailesh to verify | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
329 | Physical | Physical | Not Applicable |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | FCNCA191800100 | FCNCA191800100 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W7 | 16-13 | 4 | Y | H | H-05 | 12-15 | WQ Rack (AF2) | No |  |  | Yes | Lailesh to verify | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
330 | Physical | Physical | Not Applicable |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | FCNCA191800042 | FCNCA191800042 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W7 | 11-8 | 4 | Y | H | H-05 | 16-19 | WQ Rack (AF2) | No |  |  | Yes | Lailesh to verify | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
331 | Physical | Physical | Not Applicable |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:00 | 2026-10-25 | 9:30 | 12:00 | FCNCA191800014 | FCNCA191800014 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Storage Server | Storage | Dell | Dell Server | NA | Not Applicable | Not Applicable | To Be Confirmed | NA | To Be Confirmed | To Be Confirmed | DC2 | 2 | W7 | 6-3 | 4 | Y | H | H-05 | 20-23 | WQ Rack (AF2) | No |  |  | Yes | Lailesh to verify | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
332 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | TSBJC2003784 | TSBJC2003784 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Security Appliance | To Be Confirmed | KEMP | LOADMASTER X15 | NA | Not Applicable | Not Applicable | 10.32.24.41,10.32.24.42,10.32.24.95,10.32.24.96,10.32.24.97 | 10.32.24.39 | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W7 | 39 | 1 | Y | H | H-06 | 37 | Dell Rack (W6) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
333 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | TSBJ52004985 | TSBJ52004985 | Non-CBS | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Security Appliance | To Be Confirmed | KEMP | LOADMASTER X15 | NA | Not Applicable | Not Applicable | 10.32.24.41,10.32.24.42,10.32.24.95,10.32.24.96,10.32.24.97 | 10.32.24.40 | TAPELESS_BACKUP_SOLUTION | Internal | DC2 | 2 | W7 | 38 | 1 | Y | H | H-05 | 35 | WQ Rack (AF2) | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
334 | Physical | Physical | DC-H2-P2 INSIGHTS |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | IN801400000014 | IN801400000014 | Non-CBS | Production | Network Administration Section | SDWAN |  |  |  | High | NW-Server | To Be Confirmed | LAVELLE NETWORKS | H-CS-XL-4E-R4A2U | To Be Confirmed | To Be Confirmed | To Be Confirmed | 10.37.0.7 | To Be Confirmed | SD WAN | Cloud | DC1 | 1 | H2 | 06-07 | 2 | N | E | E-07 | 4-5 | New rack | No |  |  | No | Non-OEMs |  | BHARTI AIRTEL | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
335 | Physical | Physical | DC-H3-H4-WAN-L2-SW |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | WS3719420161 | WS3719420161 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Juniper | QFX 5110-48S | NA | Not Applicable | Not Applicable | 10.32.200.23 | 10.32.200.23 | NETWORK_MGMT | Internal | DC1 | 1 | H3 | 38 | 1 | N | E | E-08 | 27 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
336 | Physical | Physical | DC-H3-KS-RTR-2 |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | FOX1740GAHU | FOX1740GAHU | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | ASR 1002 X | NA | Not Applicable | Not Applicable | 172.27.98.134 | 172.27.98.134 | To Be Confirmed | To Be Confirmed | DC1 | 1 | H3 | 36-35 | 2 | N | F | F-08 | 19-20 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
337 | Physical | Physical | DC-L3-WAN-AGG |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | VF3715360067 | VF3715360067 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Juniper | QFX 5100-48S | NA | Not Applicable | Not Applicable | 10.32.10.130 | 10.32.10.130 | L3_SW_FW | L3_SW_FW | DC1 | 1 | H3 | 33 | 1 | N | E | E-08 | 28 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
338 | Physical | Physical | DC-H3-GM-RTR-2 |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | FXS1741Q27Z | FXS1741Q27Z | To Be Confirmed | To Be Confirmed | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | ASR 1006 | NA | Not Applicable | Not Applicable | 172.27.98.132 | 172.27.98.132 | To Be Confirmed | To Be Confirmed | DC1 | 1 | H3 | 24-29 | 6 | N | F | F-08 | 13-18 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
339 | Physical | Physical | DCINTADC02.aranac.com F5-BIG-LTM-15800 |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | f5-pyrs-qtdq | f5-pyrs-qtdq | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | F5 | Big IP i5000 | NA | Not Applicable | Not Applicable | 10.32.200.214 | 10.32.200.214 | NETWORK_MGMT | Internal | DC1 | 1 | H3 | 22 | 1 | N | F | F-09 | 24 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
340 | Physical | Physical | DC-H3-CORE-RTR-2 |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | FXS2436Q0R1 | FXS2436Q0R1 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | ASR 1000 X | NA | Not Applicable | Not Applicable | 172.27.100.202 | 172.27.100.202 | To Be Confirmed | To Be Confirmed | DC1 | 1 | H3 | 04-12 | 9 | N | F | F-08 | 4-12 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
341 | Physical | Physical | DC-H3-P2 CLOUDPORT GATEWAY 2 |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | 801400000008 | 801400000008 | Non-CBS | Production | Network Administration Section | SDWAN |  |  |  | High | NW-Server | To Be Confirmed | LAVELLE NETWORKS | H-CPG-10000-4E-R4A2U | To Be Confirmed | To Be Confirmed | To Be Confirmed | 172.16.226.153 | To Be Confirmed | VPNInside | Internal | DC1 | 1 | H3 | 19-20 | 2 | N | F | F-07 | 6-7 | New rack | No |  |  | No | Non-OEMs |  | BHARTI AIRTEL | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
342 | Physical | Physical | DC-H3-H4-WAN-L2-SW |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | WS3719420123 | WS3719420123 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Juniper | QFX 5110-48S | NA | Not Applicable | Not Applicable | 10.32.200.23 | 10.32.200.23 | NETWORK_MGMT | Internal | DC1 | 1 | H4 | 38 | 1 | N | F | F-08 | 23 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
343 | Physical | Physical | DC-H4-KS-RTR-1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FOX1740GAHX | FOX1740GAHX | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | ASR 1002 X | NA | Not Applicable | Not Applicable | 172.27.98.133 | 172.27.98.133 | To Be Confirmed | To Be Confirmed | DC1 | 1 | H4 | 35-36 | 2 | N | E | E-08 | 22-23 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
344 | Physical | Physical | DC-L3-WAN-AGG |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:00 | VF3715360265 | VF3715360265 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Juniper | QFX 5100-48S | NA | Not Applicable | Not Applicable | 10.32.10.130 | 10.32.10.130 | L3_SW_FW | L3_SW_FW | DC1 | 1 | H4 | 33 | 1 | N | F | F-08 | 24 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
345 | Physical | Physical | DC-H4-GM-RTR-1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FXS1739Q2UK | FXS1739Q2UK | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | ASR 1006 | NA | Not Applicable | Not Applicable | 172.27.98.131 | 172.27.98.131 | To Be Confirmed | To Be Confirmed | DC1 | 1 | H4 | 24-29 | 9 | N | E | E-08 | 13-21 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
346 | Physical | Physical | DCINTADC01.aranac.com F5-BIG-LTM-15800 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | F5-RBYB-IWXP | F5-RBYB-IWXP | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | F5 | Big IP i5000 | NA | Not Applicable | Not Applicable | 10.32.200.213 | 10.32.200.213 | NETWORK_MGMT | Internal | DC1 | 1 | H4 | 22 | 1 | N | E | E-09 | 24 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
347 | Physical | Physical | DC-H4-P2 CLOUDPORT GATEWAY 1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | 801400000007 | 801400000007 | Non-CBS | Production | Network Administration Section | SDWAN |  |  |  | High | NW-Server | To Be Confirmed | LAVELLE NETWORKS | H-CPG-10000-4E-R4A2U | To Be Confirmed | To Be Confirmed | To Be Confirmed | 172.16.226.152 | To Be Confirmed | VPNInside | Internal | DC1 | 1 | H4 | 21-20 | 2 | N | E | E-08 | 24-25 | New rack | No |  |  | No | Non-OEMs |  | BHARTI AIRTEL | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
348 | Physical | Physical | DC-I1-P1 CLOUDPORT GATEWAY 2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | 501400000011 | 501400000011 | Non-CBS | Production | Network Administration Section | SDWAN | nitish kumar ¦ 9964841777 ¦ nitishkumarv@canarabank.com | Inspira | Inspira ¦ 9489414920 ¦ sdwansupport@canarabank.com | High | NW-Server | To Be Confirmed | LAVELLE NETWORKS | Lavelle LN-CP-10G | NA | Not Applicable | Not Applicable | 172.16.226.142 | Not Applicable | VPNInside | Internal | DC1 | 1 | I1 | 9 | 1 | N | F | F-07 | 8 | New rack | No |  |  | No | Non-OEMs | Not Applicable | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
349 | Physical | Physical | drswift02 |  | 3 | TR-3.1 | Unracked (loose) | 2026-10-24 | 22:15 | 2026-10-25 | 9:30 | 12:00 | 847C10W | 847C10W | CBS | Production | TM Section Integrated Treasury Wing | Swift | Gambhirya Lokhande ¦ 7558713822 ¦ gambhiryatejrao@canarabank.com |  |  | High | SERVER | To Be Confirmed | IBM | Power S814 | IBM Power | AIX | 7.2 TL5 SP9 | 172.16.41.197 | 172.16.41.200 | NewDMZ | NON DMZ | DC1 | 1 | N1 | 21-24 | 4 |  |  | Scrap |  |  | No |  |  | No | Non-OEMs | Not Applicable | IBM INDIA PVT LTD | ON | Decommissioned | No | Target Rack = Scrap | Standalone – no SAN connectivity [SCRAP/OOS] | Pending | Pending
350 | Physical | Physical | DC-H4-CORE-RTR-1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FXS2545Q0Z1 | FXS2545Q0Z1 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | ASR 1000 X | NA | Not Applicable | Not Applicable | 172.27.100.201 | 172.27.100.201 | To Be Confirmed | To Be Confirmed | DC1 | 1 | H4 | 04-12 | 9 | N | E | E-08 | 4-12 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
351 | Physical | Physical | DC-FORTI-FW-1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FG3K2D3Z16800261 | FG3K2D3Z16800261 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Fortinet | Fortigate 3200D | NA | Not Applicable | Not Applicable | 10.32.32.33 | 10.32.32.33 | FORTI-WAN | Internal | DC1 | 1 | I2 | 41-42 | 2 | N | E | E-09 | 22-23 | New rack | No |  |  | No | Non-OEMs |  | Tech Mahindra Ltd. | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
352 | Physical | Physical | DC-I2-FTD-CHASSIS-1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | JMX2302L035 | JMX2302L035 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Cisco | FPR - C9300 | NA | Not Applicable | Not Applicable | 10.32.10.5 | 10.32.10.5 | FMC_FTD_INTERNAL | Internal | DC1 | 1 | I2 | 21-23 | 3 | N | E | E-09 | 18-20 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
353 | Physical | Physical | DC-I2-N9508-CORE-SW1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FGE22334V45 | FGE22334V45 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | Nexus 9508 | NA | Not Applicable | Not Applicable | 172.27.98.36 | 172.27.98.36 | NEXUS-TO-ASA | Internal | DC1 | 1 | I2 | 4-16 | 13 | N | E | E-09 | 4-16 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
354 | Physical | Physical | DC-FORTI-FW-2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FG3K2D3Z16800276 | FG3K2D3Z16800276 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Fortinet | Fortigate 3200D | NA | Not Applicable | Not Applicable | 10.32.32.33 | 10.32.32.33 | FORTI-WAN | Internal | DC1 | 1 | I3 | 41-42 | 2 | N | F | F-09 | 22-23 | New rack | No |  |  | No | Non-OEMs |  | Tech Mahindra Ltd. | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
355 | Physical | Physical | DC-I3-FMC-PRIMARY |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | WMP2411007K | WMP2411007K | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Cisco | Cisco FMC 4600 | NA | Not Applicable | Not Applicable | 10.32.10.4 | 10.32.10.4 | FMC_FTD_INTERNAL | Internal | DC1 | 1 | I3 | 25 | 1 | N | E | E-06 | 13 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
356 | Physical | Physical | DC-I2-FTD-CHASSIS-2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | JMX2417L00R | JMX2417L00R | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Cisco | FPR - C9300 | NA | Not Applicable | Not Applicable | 10.32.10.6 | 10.32.10.6 | FMC_FTD_INTERNAL | Internal | DC1 | 1 | I3 | 21-23 | 3 | N | F | F-09 | 18-20 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
357 | Physical | Physical | DC-J6-P1 CLOUDSTATION |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | CS401300000002 | CS401300000002 | Non-CBS | Production | Network Administration Section | SDWAN |  |  |  | High | NW-Server | To Be Confirmed | LAVELLE NETWORKS | LAVELLE Network CSE813MTQ3-R407CB | NA | Not Applicable | Not Applicable | 10.37.0.10 | Not Applicable | SD WAN | Cloud | DC1 | 1 | J6 | 38 | 1 | N | E | E-07 | 6 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
358 | Physical | Physical | DC-J6-P1 INSIGHTS |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | IN401300000002 | IN401300000002 | Non-CBS | Production | Network Administration Section | SDWAN |  |  |  | High | NW-Server | To Be Confirmed | LAVELLE NETWORKS | LAVELLE Network | NA | Not Applicable | Not Applicable | 10.37.0.11 | Not Applicable | SD WAN | Cloud | DC1 | 1 | J6 | 37-36 | 2 | N | F | F-05 | 4-5 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
359 | Physical | Physical | DCDMZADC02 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | f5-ctyi-hccy | f5-ctyi-hccy | Non-CBS | Production | Network Administration Section | ADC |  |  |  | High | Security Appliance | To Be Confirmed | F5 | BIG-IP i11000 series | NA | Not Applicable | Not Applicable | 10.32.200.202 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | N3 | 27 | 1 | N | F | F-11 | 20 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
360 | Physical | Physical | CB-DC-CP-EVENT-SRV |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | HWXRT04 | HWXRT04 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | NW-Server | To Be Confirmed | Check point | smart-1 6000-L | NA | Not Applicable | Not Applicable | 10.32.200.243 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | N3 | 36-37 | 2 | N | E | E-11 | 11-12 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
361 | Physical | Physical | Checkpoint 29100 CB-DC-CP-DMZ-FW2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | LR202312007390 | LR202312007390 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Check point | 29100 | NA | Not Applicable | Not Applicable | 10.32.209.67 | 10.32.209.67 | NA | External | DC1 | 1 | N3 | 36-35 | 2 | N | F | F-11 | 10-11 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
362 | Physical | Physical | CB-DC-CP-INTERNET-PROXY-FW2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | LR202402009851 | LR202402009851 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Check point | RR1-CP-26 | NA | Not Applicable | Not Applicable | 10.32.209.99 | 10.32.209.99 | NA | External | DC1 | 1 | N3 | 11-12 | 2 | N | F | F-12 | 11-12 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
363 | Physical | Physical | DC-N3-AGGEGATION-N9K-SW-2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FDO28130W1X | FDO28130W1X | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 172.16.41.12 | 172.16.41.12 | ZNPER | Internal | DC1 | 1 | N3 |  | 1 | N | F | F-12 | 23 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
364 | Physical | Physical | Cisco Nexus 3548-X DC-N3-DMZ-PXY-WAN-SW-2Y |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FOC2132R03J | FOC2132R03J | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | Nexus 3548-X | NA | Not Applicable | Not Applicable | 10.33.5.150 | 10.33.5.150 | NA | NA | DC1 | 1 | N3 | 20 | 1 | N | F | F-12 | 24 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
365 | Physical | Physical | DC-I3-N9508-CORE-SW2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FGE22334V4X | FGE22334V4X | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | Nexus 9508 | NA | Not Applicable | Not Applicable | 172.27.98.37 | 172.27.98.37 | NEXUS-TO-ASA | Internal | DC1 | 1 | I3 | 4-16 | 13 | N | F | F-09 | 4-16 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
366 | Physical | Physical | DC-N3-INTERNET-PROXY-RTR2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | BJ606 | BJ606 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Juniper | MX104 | NA | Not Applicable | Not Applicable | 10.33.5.166 | 10.33.5.166 | NA | External | DC1 | 1 | N3 | 22-24 | 3 | N | F | F-12 | 4-6 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
367 | Physical | Physical | DC-N4-N9K-PROXY-CORE-SW-1 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FLM26160862 | FLM26160862 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.33.200.146 | 10.33.200.146 | PROXY_NETWORK_MGMT | DMZ | DC1 | 1 | N3 | 17 | 1 |  |  | TBD | 32 |  | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
368 | Physical | Physical | Not Applicable |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FG4H0FT923914098 | FG4H0FT923914098 | To Be Confirmed | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Security Appliance | To Be Confirmed | Fortinet | Fortigate 400F | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | N3 | 15 | 1 | N | E | E-11 | 21 | New rack | No |  |  | No | Non-OEMs |  | To Be Confirmed | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
369 | Physical | Physical | DC-N3-CLOUD-WAN-SW-2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FDO28130VX8 | FDO28130VX8 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.33.5.197 | 10.33.5.197 | Cloud Mgmt | Cloud Mgmt | DC1 | 1 | N3 | 13 | 1 |  |  | TBD | 32 |  | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
370 | Physical | Physical | Not Applicable |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | LR202402009861 | LR202402009861 | To Be Confirmed | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Security Appliance | To Be Confirmed | Check point | RR1-CP-26 | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | N3 | 28-29 | 2 | N | F | F-12 | 9-10 | New rack | No |  |  | No | Lailesh to verify |  | To Be Confirmed | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
371 | Physical | Physical | DC-N3-CLOUD-RTR-2 |  | 3 | TR-3.2 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 12:30 | FGL2139814C | FGL2139814C | To Be Confirmed | To Be Confirmed | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | 4400 | NA | Not Applicable | Not Applicable | 10.33.5.182 | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | N3 | 07-08 | 2 | N | F | F-12 | 13-14 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
372 | Physical | Physical | DCDMZADC01 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | f5-mucx-joiu | f5-mucx-joiu | Non-CBS | Production | Network Administration Section | ADC |  |  |  | High | Network-Switch | To Be Confirmed | F5 | BIG-IP i11000 series | NA | Not Applicable | Not Applicable | 10.32.200.201 | Not Applicable | NETWORK_MGMT | Internal | DC1 | 1 | N4 | 27 | 1 | N | E | E-11 | 33 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
373 | Physical | Physical | CB-DC-CP-MGMT-SRV |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 8xxRT04 | 8xxRT04 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | NW-Server | To Be Confirmed | Check point | Check point | NA | Not Applicable | Not Applicable | 10.32.200.242 | 10.32.200.242 | NETWORK_MGMT | Internal | DC1 | 1 | N4 | 36-37 | 2 | N | F | F-11 | 12-13 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
374 | Physical | Physical | Checkpoint 29100 CB-DC-CP-DMZ-FW1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | LR202401010219 | LR202401010219 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Check point | 29100 | NA | Not Applicable | Not Applicable | 10.32.209.66 | 10.32.209.66 | NA | External | DC1 | 1 | N4 | 34-35 | 2 | N | E | E-11 | 13-14 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
375 | Physical | Physical | CB-DC-CP-INTERNET-PROXY-FW1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | LR202402009885 | LR202402009885 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Check point | RR1-CP-26 | NA | Not Applicable | Not Applicable | 10.32.209.98 | 10.32.209.98 | NA | External | DC1 | 1 | N4 | 28-29 | 2 | N | E | E-12 | 10-11 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
376 | Physical | Physical | DC-N4-CLOUD-WAN-SW-1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FDO28140BUE | FDO28140BUE | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 10.33.5.196 | 10.33.5.196 | Cloud Mgmt | Cloud Mgmt | DC1 | 1 | N4 | 26 | 1 | N | H | H-11 | 23 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
377 | Physical | Physical | DC-N4-INTERNET-PROXY-RTR1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | CG094 | CG094 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Juniper | MX104 | NA | Not Applicable | Not Applicable | 10.33.5.165 | 10.33.5.165 | NA | External | DC1 | 1 | N4 | 21-24 | 4 | N | E | E-12 | 4-7 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
378 | Physical | Physical | Cisco Nexus 3548-X DC-N4-DMZ-PXY-WAN-SW-1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FOC2132R03L | FOC2132R03L | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | Nexus 3548-X | NA | Not Applicable | Not Applicable | 10.33.5.149 | 10.33.5.149 | NA | External | DC1 | 1 | N4 | 20 | 1 | N | E | E-12 | 23 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
379 | Physical | Physical | DC-N3-N9K-PROXY-CORE-SW-2 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FLM261600BU | FLM261600BU | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX | NA | Not Applicable | Not Applicable | 10.33.200.147 | 10.33.200.147 | PROXY_NETWORK_MGMT | DMZ | DC1 | 1 | N4 | 17 | 1 | N | H | H-11 | 24 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
380 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FG4H0FT923913688 | FG4H0FT923913688 | To Be Confirmed | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Security Appliance | To Be Confirmed | Fortinet | Fortigate 400F | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | N4 | 15 | 1 | N | F | F-11 | 21 | New rack | No |  |  | No | Non-OEMs |  | To Be Confirmed | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
381 | Physical | Physical | DC-N4-AGGREGATION-N9K-SW-1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FDO281312YJ | FDO281312YJ | To Be Confirmed | To Be Confirmed | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | N9K-C93180YC-FX3 | NA | Not Applicable | Not Applicable | 172.16.41.11 | 172.16.41.11 | ZNPER | Internal | DC1 | 1 | N4 | 13 | 1 | N | H | H-10 | 23 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
382 | Physical | Physical | CB-DC-CP-CLOUD-FW1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | LR202402004472 | LR202402004472 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Security Appliance | To Be Confirmed | Check point | RR1-CP-26 | NA | Not Applicable | Not Applicable | 10.32.209.114 | 10.32.209.114 | NA | External | DC1 | 1 | N4 | 11-12 | 2 | N | E | E-12 | 12-13 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
383 | Physical | Physical | DC-N4-CLOUD-RTR-1 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FGL2139814D | FGL2139814D | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Cisco | 4400 | NA | Not Applicable | Not Applicable | 10.33.5.181 | 10.33.5.181 | NA | External | DC1 | 1 | N4 | 07-08 | 2 | N | E | E-12 | 14-15 | New rack | No |  |  | No | Non-OEMs |  | IBM INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
384 | Physical | Physical | DC-O1-INTERNET-DMZ-RTR-01 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FLM281510M1 | FLM281510M1 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | C8300-1N-1S-6T | NA | Not Applicable | Not Applicable | 10.33.5.2 | 10.33.5.2 | NA | External | DC1 | 1 | O1 | 16 | 1 | N | E | E-11 | 22 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
385 | Physical | Physical | DC-O1-INTERNET-DMZ-RTR-02 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | FLM281510M0 | FLM281510M0 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Router | To Be Confirmed | Cisco | C8300-1N-1S-6T | NA | Not Applicable | Not Applicable | 10.33.5.3 | 10.33.5.3 | NA | External | DC1 | 1 | O1 | 14 | 1 | N | F | F-11 | 22 | New rack | No |  |  | No | Non-OEMs |  | Kyndryl Solutions Private Limited | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
386 | Physical | Physical | DC-O1-INTERNET-JPR-L3 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | VF3715360003 | VF3715360003 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Aruba | QFX 5110-48S | NA | Not Applicable | Not Applicable | 10.33.200.6 | 10.33.200.6 | DMZ_NETWORK_MGMT | DMZ | DC1 | 1 | O1 | 12 | 1 | N | E | E-11 | 34 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
387 | Physical | Physical | DC-O1-INTERNET-JPR-L3 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | VF3715360016 | VF3715360016 | To Be Confirmed | Production | To Be Confirmed |  |  |  |  | High | Network-Switch | To Be Confirmed | Aruba | QFX 5110-48S | NA | Not Applicable | Not Applicable | 10.33.200.6 | 10.33.200.6 | DMZ_NETWORK_MGMT | DMZ | DC1 | 1 | O1 | 10 | 1 | N | F | F-11 | 33 | New rack | No |  |  | No | Non-OEMs |  | INSPIRA ENTERPRISE INDIA PVT LTD | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
388 | Physical | Physical | DCCANARBOR |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | CG24148159LA | CG24148159LA | Non-CBS | Production | Cyber Security Operations Centre (CSOC) Section | Netscout Anti-DDOS(Network Appliance) |  |  |  | High | Security Appliance | To Be Confirmed | NETSCOUT | Arbor Edge Defense | NA | Not Applicable | Not Applicable | 10.33.201.10 | Not Applicable | DMZ_SERVER_MGMT | Internal | DC1 | 1 | O1 | 34-35 | 2 | N | E | E-11 | 15-16 | New rack | No |  |  | No | Non-OEMs |  | To Be Confirmed | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
389 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 1901312380 | 1901312380 | To Be Confirmed | To Be Confirmed | To Be Confirmed |  |  |  |  | To Be Confirmed | Security Appliance | To Be Confirmed | ARRAY | Edge safe | NA | Not Applicable | Not Applicable | Not Applicable | Not Applicable | To Be Confirmed | To Be Confirmed | DC1 | 1 | O6 | 35 | 1 | N | F | F-11 | 23 | New rack | No |  |  | No | Group Project NGSoc | csoc@canarabank.com | To Be Confirmed | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
390 | Physical | Physical | DCCSWPSSL01 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 3377DT33C | 3377DT33C | Non-CBS | Production | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center |  |  |  | High | Security Appliance | To Be Confirmed | ARRAY | ASI9900 | NA | Not Applicable | Not Applicable | 10.33.200.61 | Not Applicable | DMZ_NETWORK_MGMT | Internal | DC1 | 1 | O6 | 24-23 | 2 | N | E | E-11 | 17-18 | New rack | No |  |  | No | Group Project NGSoc | csoc@canarabank.com | To Be Confirmed | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
391 | Physical | Physical | DCCSWPSSL02 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 338BTT3CT | 338BTT3CT | Non-CBS | Production | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center |  |  |  | High | Security Appliance | To Be Confirmed | ARRAY | ASI9900 | NA | Not Applicable | Not Applicable | 10.33.200.62 | Not Applicable | DMZ_NETWORK_MGMT | Internal | DC1 | 1 | O6 | 21-22 | 2 | N | F | F-11 | 16-17 | New rack | No |  |  | No | Group Project NGSoc | csoc@canarabank.com | To Be Confirmed | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
392 | Physical | Physical | DCCSWNTB01 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 23720020148 | 23720020148 | Non-CBS | Production | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center |  |  |  | High | Security Appliance | To Be Confirmed | NTB | NTB T12a-BP2 | NA | Not Applicable | Not Applicable | 10.33.200.63 | Not Applicable | DMZ_NETWORK_MGMT | Internal | DC1 | 1 | O6 | 33 | 1 | N | E | E-11 | 7 | New rack | No |  |  | No | Group Project NGSoc | csoc@canarabank.com | Array Networks | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
393 | Physical | Physical | DCCSWNTB02 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | 23720020149 | 23720020149 | Non-CBS | Production | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center |  |  |  | High | Security Appliance | To Be Confirmed | NTB | NTB T12a-BP2 | NA | Not Applicable | Not Applicable | 10.33.200.64 | Not Applicable | DMZ_NETWORK_MGMT | Internal | DC1 | 1 | O6 | 34 | 1 | N | F | F-11 | 24 | New rack | No |  |  | No | Group Project NGSoc | csoc@canarabank.com | Array Networks | On | On | Yes |  | Standalone – no SAN connectivity | Pending | Pending
394 | Physical | Physical | DCCSWPAPT01 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | SR 025409001255 | SR 025409001255 | Non-CBS | Production | Cyber Security Operations Centre (CSOC) Section | Palo Alto Anti-APT(Firewall) |  |  |  | High | Security Appliance | To Be Confirmed | Palo-Alto | PA5430 | NA | Not Applicable | Not Applicable | 10.33.201.18 | Not Applicable | DMZ_SERVER_MGMT | Internal | DC1 | 1 | O6 | 16-17 | 2 | N | E | E-11 | 19-20 | New rack | No |  |  | No | Group Project NGSoc | csoc@canarabank.com | DELOITTEE TOUCHE TOHMATSU INDIA LLP | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
395 | Physical | Physical | DCCSWPAPT02 |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | SR 025409001274 | SR 025409001274 | Non-CBS | Production | Cyber Security Operations Centre (CSOC) Section | Palo Alto Anti-APT(Firewall) |  |  |  | High | Security Appliance | To Be Confirmed | Palo-Alto | PA5430 | NA | Not Applicable | Not Applicable | 10.33.201.19 | Not Applicable | DMZ_SERVER_MGMT | Internal | DC1 | 1 | O6 | 18-19 | 2 | N | F | F-11 | 18-19 | New rack | No |  |  | No | Group Project NGSoc | csoc@canarabank.com | DELOITTEE TOUCHE TOHMATSU INDIA LLP | ON | ON | Yes |  | Standalone – no SAN connectivity | Pending | Pending
396 | Physical | Physical | Not Applicable |  | 3 | TR-3.3 | Unracked (loose) | 2026-10-24 | 23:45 | 2026-10-25 | 9:30 | 13:00 | W3-KVM Switch | W3-KVM Switch | Not Applicable | To Be Confirmed | NA |  |  |  |  | To Be Confirmed | KVM Switch | To Be Confirmed | Dell | KVM Switch | NA | Not Applicable | Not Applicable | NA | NA | To Be Confirmed | NON DMZ | DC2 | 2 | W3 | 19 | 1 |  |  | N/W |  | TBD | No |  |  | Yes | Dell Support | Harsha.Vardhan5@Dell.com | To Be Confirmed | Not Applicable | Not Applicable | No |  | Standalone – no SAN connectivity | Pending | Pending
397 | Virtual | AIX-Lpar | DCARCHDB2 | C2-9080-HEX-SN78C7868-UAT | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.2.39,10.32.2.37,10.32.33.12 |  | CBS_DB | Internal | DC1 | 1 | C2 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C2-9080-HEX-SN78C7868-UAT | Pending | Pending
398 | Virtual | AIX-Lpar | DCCBSUAT2APP | C2-9080-HEX-SN78C7868-UAT | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.145 |  | CBS_UAT | NON DMZ | DC1 | 1 | C2 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C2-9080-HEX-SN78C7868-UAT | Pending | Pending
399 | Virtual | AIX-Lpar | DCCBSUAT2DB | C2-9080-HEX-SN78C7868-UAT | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.144 |  | CBS_UAT | NON DMZ | DC1 | 1 | C2 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C2-9080-HEX-SN78C7868-UAT | Pending | Pending
400 | Virtual | AIX-Lpar | DCCBSUAT3APP | C2-9080-HEX-SN78C7868-UAT | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.149 |  | CBS_UAT | NON DMZ | DC1 | 1 | C2 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C2-9080-HEX-SN78C7868-UAT | Pending | Pending
401 | Virtual | AIX-Lpar | DCCBSUAT3DB | C2-9080-HEX-SN78C7868-UAT | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78C7868 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.148 |  | CBS_UAT | NON DMZ | DC1 | 1 | C2 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C2-9080-HEX-SN78C7868-UAT | Pending | Pending
402 | Virtual | AIX-Lpar | DCARCHDB1 | D1-9080-HEX-SN78C7848-UAT | 2 | TR-2.5 | Moves with host (Loaded in OEM rack D1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.2.38,10.32.2.36,10.32.33.11 |  | CBS_DB | Internal | DC1 | 1 | D1 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host D1-9080-HEX-SN78C7848-UAT | Pending | Pending
403 | Virtual | AIX-Lpar | DCCBSUAT1APP | D1-9080-HEX-SN78C7848-UAT | 2 | TR-2.5 | Moves with host (Loaded in OEM rack D1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.139 |  | CBS_UAT | NON DMZ | DC1 | 1 | D1 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host D1-9080-HEX-SN78C7848-UAT | Pending | Pending
404 | Virtual | AIX-Lpar | DCCBSUAT1DB1 | D1-9080-HEX-SN78C7848-UAT | 2 | TR-2.5 | Moves with host (Loaded in OEM rack D1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.132 |  | CBS_UAT | NON DMZ | DC1 | 1 | D1 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host D1-9080-HEX-SN78C7848-UAT | Pending | Pending
405 | Virtual | AIX-Lpar | DCCBSUATPREPRODAPP | D1-9080-HEX-SN78C7848-UAT | 2 | TR-2.5 | Moves with host (Loaded in OEM rack D1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.141 |  | CBS_UAT | NON DMZ | DC1 | 1 | D1 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host D1-9080-HEX-SN78C7848-UAT | Pending | Pending
406 | Virtual | AIX-Lpar | DCCBSUATPREPRODDB | D1-9080-HEX-SN78C7848-UAT | 2 | TR-2.5 | Moves with host (Loaded in OEM rack D1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.140 |  | CBS_UAT | NON DMZ | DC1 | 1 | D1 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host D1-9080-HEX-SN78C7848-UAT | Pending | Pending
407 | Virtual | AIX-Lpar | DCCBSUATSTGAPP | D1-9080-HEX-SN78C7848-UAT | 2 | TR-2.5 | Moves with host (Loaded in OEM rack D1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.147 |  | CBS_UAT | NON DMZ | DC1 | 1 | D1 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host D1-9080-HEX-SN78C7848-UAT | Pending | Pending
408 | Virtual | AIX-Lpar | DCCBSUATSTGDB | D1-9080-HEX-SN78C7848-UAT | 2 | TR-2.5 | Moves with host (Loaded in OEM rack D1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:30 | 78C7848 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.146 |  | CBS_UAT | NON DMZ | DC1 | 1 | D1 | [7 empty] | Via host (Yes) | BLR128B-G7-SW1 (B2), BLR128B-G7-SW2 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host D1-9080-HEX-SN78C7848-UAT | Pending | Pending
409 | Virtual | Hyper-V-VM | NDC-ASBAAPP-N01 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | SPMS | ASBA | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.206.132 |  | NDR_NCBS_APP | NON DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
410 | Virtual | Hyper-V-VM | NDC-ASBAWEB-N01 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | SPMS | ASBA | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.9.5 |  | NDR_DMZ_WEB | DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
411 | Virtual | Hyper-V-VM | NDC-ASBAWEB-N02 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | SPMS | ASBA | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.9.6 |  | NDR_DMZ_WEB | DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
412 | Virtual | Hyper-V-VM | NDC-CCIL-APP-1 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.32.230.37 |  | NDR_Treasury_APP |  | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
413 | Virtual | Hyper-V-VM | NDC-DPSECURE-DB | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | Landmark Solutions | Ajikya Hatim ¦ 9768524076 ¦ ajinkya@lsssoftware.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.206.199 |  | NDR_NCBS_DB | NON DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
414 | Virtual | Hyper-V-VM | NDC-DPSecure-APP | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com |  |  | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.206.134 |  | NDR_NCBS_APP | NON DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
415 | Virtual | Hyper-V-VM | RAP-DC-PRB1-DB01 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | IT Assets Management Section | RAP Remote | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | Sonata technology pvt ltd | Dinesh ¦ 9920710330 ¦ dinesh.pratahkal@sonata-software.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.52.201 |  | NCBS_DB_NEW | NON DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
416 | Virtual | Hyper-V-VM | RAP-DC-PRB2-DB01 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | IT Assets Management Section | RAP Remote | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | Sonata technology pvt ltd | Dinesh ¦ 9920710330 ¦ dinesh.pratahkal@sonata-software.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.52.202 |  | NCBS_DB_NEW | NON DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
417 | Virtual | Hyper-V-VM | RAP-DC-SUM-DB01 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | IT Assets Management Section | RAP Remote | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | Sonata technology pvt ltd | Dinesh ¦ 9920710330 ¦ dinesh.pratahkal@sonata-software.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.52.200 |  | NCBS_DB_NEW | NON DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
418 | Virtual | Hyper-V-VM | RAP-DC-UAT-SUM01 | NDC-BASENDC-APP | 1 | TR-1.4 | Moves with host (Unracked (loose)) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 14:30 | C8SSN24 | Virtual Machine | Non-CBS | Production | IT Assets Management Section | RAP Remote | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | Sonata technology pvt ltd | Dinesh ¦ 9920710330 ¦ dinesh.pratahkal@sonata-software.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.161 |  | UAT_NCBS_APP | NON DMZ | NDC-GR | Ground | GR-A4 | [7 empty] | Via host (Yes) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | A+B | [6 empty] | Yes |  | Inherits batch of host NDC-BASENDC-APP | Pending | Pending
419 | Virtual | AIX-Lpar | DCADAPIDDB | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | [7 empty] | LPAR |  |  |  | IBM Power |  |  | 10.32.18.222 |  |  |  | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
420 | Virtual | AIX-Lpar | DCFCUBSPRDDB01 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | Non-CBS | Production | FCUBS | FCUBS |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.68 |  | FCUBS_DB | Internal | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
421 | Virtual | AIX-Lpar | DCFCUBSPRDDB01 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | SUNIL KASHIKAR | 9900139448 ¦ sunilr.kashikar@kyndryl.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.72 |  | FCUBS_DB | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
422 | Virtual | AIX-Lpar | DCGBMPMVIDN1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | Non-CBS | Production | Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | DBA Team |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.52.38 |  | NCBS_DB_NEW | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
423 | Virtual | AIX-Lpar | DCLACBS3GLPRODDB01 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.2.41,10.32.2.42,10.32.2.44,10.32.33.103,10.32.33.102 |  | CBS_DB | Internal | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
424 | Virtual | AIX-Lpar | DCOBDXAPP1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.133 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
425 | Virtual | AIX-Lpar | DCOBDXAPP3 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.135 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
426 | Virtual | AIX-Lpar | DCOBDXAPP5 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.137 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
427 | Virtual | AIX-Lpar | DCOBDXDB1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.199 |  | INTERNET_BANKING_OBDX_DB | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
428 | Virtual | AIX-Lpar | DCOBDXREP1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBT NET Banking Section - Report Server |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.18.139 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
429 | Virtual | AIX-Lpar | DCOBDXWEB1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.44 |  | DMZ_WEB | DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
430 | Virtual | AIX-Lpar | DCOBDXWEB3 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.46 |  | DMZ_WEB | DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
431 | Virtual | AIX-Lpar | DCOBDXWEB5 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.60 |  | DMZ_WEB | DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
432 | Virtual | AIX-Lpar | DCOBDXWEB7 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.13.14 |  | NCBS_WEB | NON DMZ | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
433 | Virtual | AIX-Lpar | DCUPIARCHDB | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | CBS | [7 empty] | LPAR |  |  |  | IBM Power |  |  | 10.32.52.62 |  |  |  | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
434 | Virtual | AIX-Lpar | DCUPIDB02 | A1-9080-HEX-SN78A1DD8-MIG-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DD8 | Lpar | Non-CBS | Production | Online Banking Technology UPI and INFRA Section | UPI DB |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.12.105 |  | NCBS_DB | Internal | DC1 | 1 | A1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A1-9080-HEX-SN78A1DD8-MIG-1 | Pending | Pending
435 | Virtual | AIX-Lpar | DCP10CBSPRDDB01 | A2-9080-HEX-SN78A1DC8-CORE_DB-1 | 2 | TR-2.1 | Moves with host (Loaded in OEM rack A2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 6:30 | 78A1DC8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.2.66 |  | CBS_DB | NON DMZ | DC1 | 1 | A2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host A2-9080-HEX-SN78A1DC8-CORE_DB-1 | Pending | Pending
436 | Virtual | AIX-Lpar | DCP10CBSPRDDB02 | C3-9080-HEX-SN78A1DE8-CORE_DB-2 | 1 | TR-1 | Moves with host (Loaded in OEM rack C3) | 2026-10-24 | 4:30 | 2026-10-24 | 6:00 | 12:30 | 78A1DE8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.2.67 |  | CBS_DB | NON DMZ | DC1 | 1 | C3 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C3-9080-HEX-SN78A1DE8-CORE_DB-2 | Pending | Pending
437 | Virtual | AIX-Lpar | DCFLASH3 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.2.46 |  | CBS_DB | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
438 | Virtual | AIX-Lpar | DCGBMPMVIDN2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | Non-CBS | Production | Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | DBA Team |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.52.39 |  | NCBS_DB_NEW | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
439 | Virtual | AIX-Lpar | DCLACBS3GLPRODDB02 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.2.43 |  | CBS_DB | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
440 | Virtual | AIX-Lpar | DCOBDXAPP2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.134 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
441 | Virtual | AIX-Lpar | DCOBDXAPP4 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.136 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
442 | Virtual | AIX-Lpar | DCOBDXAPP6 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.138 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
443 | Virtual | AIX-Lpar | DCOBDXREP2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBT NET Banking Section - Report Server |  |  |  | Low | LPAR |  |  |  | IBM Power |  |  | 10.32.18.140 |  | INTERNET_BANKING_OBDX_APP | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
444 | Virtual | AIX-Lpar | DCOBDXWEB2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.45 |  | DMZ_WEB | DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
445 | Virtual | AIX-Lpar | DCOBDXWEB4 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.47 |  | DMZ_WEB | DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
446 | Virtual | AIX-Lpar | DCOBDXWEB6 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.61 |  | DMZ_WEB | DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
447 | Virtual | AIX-Lpar | DCOBDXWEB8 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.13.15 |  | NCBS_WEB | NON DMZ | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
448 | Virtual | AIX-Lpar | DCUPIDB01 | C4-9080-HEX-SN78A1DF8-MIG-2 | 2 | TR-2.3 | Moves with host (Loaded in OEM rack C4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 7:30 | 78A1DF8 | Lpar | Non-CBS | Production | Online Banking Technology UPI and INFRA Section | UPI DB |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.12.103 |  | NCBS_DB | Internal | DC1 | 1 | C4 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host C4-9080-HEX-SN78A1DF8-MIG-2 | Pending | Pending
449 | Virtual | Hyper-V-VM | DC-COMP-APP | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | Production | Compliance Department section | Compliance Kartavya | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com | Alphaplus Technologies | Phani Kumar N ¦ 9182989492 ¦ phani@alphaplustech.com,apt.projects@alphaplustech.com, apt.projects-technical@alphaplustech.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.51.14 |  | NCBS_APP_NEW | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
450 | Virtual | Hyper-V-VM | DC-COMP-DB | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | Production | Compliance Department | Compliance Kartavya |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.52.6 |  | NCBS_DB_NEW | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
451 | Virtual | Hyper-V-VM | DC-CRMENCRYPT-APP1 | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | CRM | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | TechMatrix consulting pvt ltd | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com | LOW | Hyper-V VM |  |  |  | X86 |  |  | 10.32.51.15 |  | NCBS_APP_NEW | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
452 | Virtual | Hyper-V-VM | DC-GAURDAI-01 | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | Production | Data Center Operations Section (ITI) | AI Alertlog | Sangeetha ¦ sangeetha_r@canarabank.com |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 172.16.38.77 |  | Database | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
453 | Virtual | Hyper-V-VM | DC-GAURDAI-02 | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | Production | Data Center Operations Section (ITI) | AI Alertlog | Sangeetha ¦ sangeetha_r@canarabank.com |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 172.16.38.75 |  | Database | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
454 | Virtual | Hyper-V-VM | DC-UIPATH-DB1 | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  |  |  |  | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.229 |  | Robot_Process_Auto_DB | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
455 | Virtual | Hyper-V-VM | PUSH-NOTIFICATION-SERVER | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | Production | Online Banking Technology Mobile Banking | MOBILE BANKING | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.18.52 |  | MB_UPI_APP_New | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
456 | Virtual | Hyper-V-VM | UAT-COMP-APP | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | UAT | Compliance Department section | Compliance Kartavya | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com | Alphaplus Technologies | Phani Kumar N ¦ 9182989492 ¦ phani@alphaplustech.com,apt.projects@alphaplustech.com, apt.projects-technical@alphaplustech.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.159 |  | UAT_NCBS_APP | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
457 | Virtual | Hyper-V-VM | UAT-COMP-DB | CLUSTER1-NODE1 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | B1KHMY3 | Virtual Machine | Non-CBS | UAT | Compliance Department | Compliance Kartavya |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.132.21 |  | UAT_Non-CBS_DB | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node1 | Pending | Pending
458 | Virtual | Hyper-V-VM | Circular-Module-App | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | Portal | Gururaj Pamidi ¦ 9535105108 ¦ gururajnaidu.pamidi@kyndryl.com /Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com | OSPYN | Manoj ¦ 9703145556 ¦ manoj.m@ospyn.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.13.87 |  | NCBS_WEB | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
459 | Virtual | Hyper-V-VM | Circular-Module-Web | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | Portal | Gururaj Pamidi ¦ 9535105108 ¦ gururajnaidu.pamidi@kyndryl.com /Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com | OSPYN | Manoj ¦ 9703145556 ¦ manoj.m@ospyn.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.13.88 |  | NCBS_WEB | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
460 | Virtual | Hyper-V-VM | DC-IRCTC-BETA | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | Online Banking Technology Mobile Banking | MOBILE BANKING | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.18.53 |  | MB_UPI_APP_New | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
461 | Virtual | Hyper-V-VM | DC-RPA-HA1 | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.27.244 |  | Robot_Process_Auto_HA | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
462 | Virtual | Hyper-V-VM | DC-RPA-NUG1 | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.27.214, fe80::250:56ff:fe82:9935 |  | Robot_Process_Auto_orchest | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
463 | Virtual | Hyper-V-VM | DC-RPA-ORCH1 | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  | THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.27.212 |  | Robot_Process_Auto_orchest | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
464 | Virtual | Hyper-V-VM | DC-RPA-ORCH12 | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  | Vijey/Ankit ¦ 9487691736/7038831744 ¦ hotoncbs@canarabank.com;vijeyvr@canarabank.com;ankitsr@canarabank.com | Ms Apmosys Technologies Pvt Ltd | Nandiratha ¦ 9938184406 ¦ rpasupport@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.196 |  | Robot_Process_Auto | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
465 | Virtual | Hyper-V-VM | DC-RPA-ORCH13 | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.197 |  | Robot_Process_Auto | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
466 | Virtual | Hyper-V-VM | DC-RPA-ORCH2 | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  | THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.27.213 |  | Robot_Process_Auto_orchest | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
467 | Virtual | Hyper-V-VM | DC-TAPELES-MIG | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.32.24.91 |  | TAPELESS_BACKUP_SOLUTION | MZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
468 | Virtual | Hyper-V-VM | DC-UAT-API | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | Non-CBS | UAT | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | Comportement Software Private Limited | Murali ¦ 9880041498 ¦ murali@comportement.in | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.180 |  | UAT_NCBS_APP | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
469 | Virtual | Hyper-V-VM | DC-UAT-OBDX | CLUSTER1-NODE3 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 10KHMY3 | Virtual Machine | CBS | UAT | Online Banking Technology Net banking Section | OBT NET Banking Server - Jenkins Server | RAGHURAM ¦ 8908226867 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ raghavendra.shivaram@oracle.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.41.8 |  | DIGITAL_LENDING_TOOLS | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node3 | Pending | Pending
470 | Virtual | Hyper-V-VM | DC-ATM-DB | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.43.15 |  | ATMFSS | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
471 | Virtual | Hyper-V-VM | DC-ATM-IBR | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.43.18 |  | ATMFSS | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
472 | Virtual | Hyper-V-VM | DC-ATM-OTP | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.43.29 |  | ATMFSS | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
473 | Virtual | Hyper-V-VM | DC-ATM-Reports | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.3.87 |  | NON-CBS_DB | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
474 | Virtual | Hyper-V-VM | DC-ATM-Reports1 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.26.101 |  | VISA | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
475 | Virtual | Hyper-V-VM | DC-ATM-Reports2 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.42.174 |  | TestAppln | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
476 | Virtual | Hyper-V-VM | DC-ATM-Reports3 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.42.175 |  | TestAppln | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
477 | Virtual | Hyper-V-VM | DC-ATM-WEB | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 172.16.43.24 |  | ATMFSS | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
478 | Virtual | Hyper-V-VM | DC-CANDI-APP2 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | Data Center Operations Section (ITI) |  | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.247 |  | NCBS_APP | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
479 | Virtual | Hyper-V-VM | DC-CRMENCRYPT-APP2 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | CRM | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | TechMatrix consulting pvt ltd | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com | LOW | Hyper-V VM |  |  |  | X86 |  |  | 10.32.51.16 |  | NCBS_APP_NEW | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
480 | Virtual | Hyper-V-VM | DC-CRMENCRYPT-APP3 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  | Saket/Gaurav Baberwal |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.32.51.17 |  | NCBS_APP_NEW | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
481 | Virtual | Hyper-V-VM | DC-CTSDEM-APP3 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | UAT | CTS | DEM | Shakti Narayan Gupta,Bhupesh Piplani,7975142177/9650976622,hoditcts@canarabank.com |  | In-House (ADM),ADM Team, IT Vertical,hoditadm@canarabank.com,NCR,NCR,9535040604,sharathkumar.manvi@ncratleos.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.133.191 |  | UAT_NCBS_APP2 | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
482 | Virtual | Hyper-V-VM | DC-NACH-APP | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | Service Unit Section |  |  |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 172.16.44.78 |  | Financial-Inclusion | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
483 | Virtual | Hyper-V-VM | DC-PROD-APP-OBDX | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | CBS | Production | Online Banking Technology Net banking Section | OBT NET Banking Server - Jenkins Server | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ raghavendra.shivaram@oracle.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.41.9 |  | DIGITAL_LENDING_TOOLS | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
484 | Virtual | Hyper-V-VM | DC-RPA-HA2 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.27.245 |  | Robot_Process_Auto_HA | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
485 | Virtual | Hyper-V-VM | DC-RPA-HA3 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.27.246 |  | Robot_Process_Auto_HA | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
486 | Virtual | Hyper-V-VM | DC-UIPATH-DB2 | CLUSTER1-NODE4 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 61KHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  | Vijey/Ankit |  |  | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.230 |  | Robot_Process_Auto_DB | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host cluster1-Node4 | Pending | Pending
487 | Virtual | Hyper-V-VM | DC-LAPS-CONNWEB1 | DCHVCLSTRN02 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | B0KHMY3 | Virtual Machine | Non-CBS | Production | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.160 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN02 | Pending | Pending
488 | Virtual | Hyper-V-VM | DC-LAPS-CONNWEB2 | DCHVCLSTRN02 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | B0KHMY3 | Virtual Machine | Non-CBS | Production | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.161 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN02 | Pending | Pending
489 | Virtual | Hyper-V-VM | DC-LAPS-LENDWEB1 | DCHVCLSTRN02 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | B0KHMY3 | Virtual Machine | Non-CBS | Production | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.162 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN02 | Pending | Pending
490 | Virtual | Hyper-V-VM | DC-LAPS-LENDWEB2 | DCHVCLSTRN02 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | B0KHMY3 | Virtual Machine | Non-CBS | Production | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.163 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN02 | Pending | Pending
491 | Virtual | Hyper-V-VM | DC-HRMES2.aranac.com | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.12 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
492 | Virtual | Hyper-V-VM | DC-HRMFILE1.aranac.com | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.68 |  | HRMS_NEW_FILE | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
493 | Virtual | Hyper-V-VM | DC-HRMWEB1.aranac.com | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.36 |  | HRMS_NEW_WEB | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
494 | Virtual | Hyper-V-VM | DC-HRMWEB2.aranac.com | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.37 |  | HRMS_NEW_WEB | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
495 | Virtual | Hyper-V-VM | DC-HRMWEB3.aranac.com | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.38 |  | HRMS_NEW_WEB | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
496 | Virtual | Hyper-V-VM | DCHRMAPP2.canarabank.in | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.5 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
497 | Virtual | Hyper-V-VM | DCHRMAPP3.canarabank.in | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.6 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
498 | Virtual | Hyper-V-VM | DCHRMAPP4.canarabank.in | DCHVCLSTRN08 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | H3SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.7 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN08 | Pending | Pending
499 | Virtual | Hyper-V-VM | DC-HRMES1.aranac.com | DCHVCLSTRN09 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.11 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN09 | Pending | Pending
500 | Virtual | Hyper-V-VM | DC-HRMFILE2.aranac.com | DCHVCLSTRN09 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.69 |  | HRMS_NEW_FILE | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN09 | Pending | Pending
501 | Virtual | Hyper-V-VM | DC-HRMWEB4.aranac.com | DCHVCLSTRN09 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.39 |  | HRMS_NEW_WEB | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN09 | Pending | Pending
502 | Virtual | Hyper-V-VM | DC-HRMWEB5.aranac.com | DCHVCLSTRN09 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.40 |  | HRMS_NEW_WEB | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN09 | Pending | Pending
503 | Virtual | Hyper-V-VM | DCHRMAPP5.canarabank.in | DCHVCLSTRN09 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.8 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN09 | Pending | Pending
504 | Virtual | Hyper-V-VM | DCHRMAPP6.canarabank.in | DCHVCLSTRN09 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.9 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN09 | Pending | Pending
505 | Virtual | Hyper-V-VM | DCHRMAPP7.canarabank.in | DCHVCLSTRN09 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 83SXMZ3 | Virtual Machine | Non-CBS | Production | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | Kovaion Consulting India Private Ltd | Matheswaran ¦ 9080713703 ¦ matheshwaran.viswanathan@kovaion.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.45.10 |  | HRMS_NEW_APP | NON DMZ | DC1 | 1 | J2 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN09 | Pending | Pending
506 | Virtual | Hyper-V-VM | DC-IMPS-WEB1 | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | Online Banking Technology Mobile Banking | IMPS | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.80 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
507 | Virtual | Hyper-V-VM | DC-UAT-CRM-WEB1 | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | SPMS | CRM | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | TechMatrix consulting pvt ltd | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com | LOW | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.59 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
508 | Virtual | Hyper-V-VM | UAT-APIBKG-WEB5 | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | Digital API Craft | Sandeep Kenkare Satya Janardhana ¦ 9886236345 ¦ sandeep.k@digitalapi.ai | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.116 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
509 | Virtual | Hyper-V-VM | UAT-APIBKG-WEB6 | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | Digital API Craft | Sandeep Kenkare Satya Janardhana ¦ 9886236345 ¦ sandeep.k@digitalapi.ai | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.117 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
510 | Virtual | Hyper-V-VM | UAT-CBSPIGMYWEB | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.159 |  | DMZ_UAT_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
511 | Virtual | Hyper-V-VM | UAT-CRM-WEB | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | SPMS | CRM | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | TechMatrix consulting pvt ltd | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com | LOW | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.115 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
512 | Virtual | Hyper-V-VM | UAT-DMS-OFFICENOTE | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | SPMS | DOCUMENT MANAGEMENT SYSTEM | Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com | OSPYN | sajeev/manoj ¦ 94892029040/9703145556 ¦ DOCMGMTSYS@GMAIL.COM | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.26 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
513 | Virtual | Hyper-V-VM | UAT-FIG | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | Notinuse | Government Business and Financial Inclusion Section | FI | Kiran B R ¦ 7619453224 ¦ figsupport@canarabank.com & kiranbr@integramicro.co.in & hoditfimb@canarabank.com | Integra Micro Systems Pvt Ltd | Kiran B R ¦ 7619453224 ¦ kiranbr@integramicro.co.in & figsupport@canarabank.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.65 |  | DMZ_WEB | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
514 | Virtual | Hyper-V-VM | UAT-MOBILE-WEB01 | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | Online Banking Technology Mobile Banking | MOBILE BANKING | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.120 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
515 | Virtual | Hyper-V-VM | UAT-QMS-WEB | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | UAT | SPMS | Queue Management System | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | M/s AurionPro | Saroj Kumar Behra ¦ 8144648575 ¦ sarojkumar.behra@aurionpro.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.63 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
516 | Virtual | Hyper-V-VM | WIN-RB3EM3SD28I | DCHYPRVBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 9MJHMY3 | Virtual Machine | Non-CBS | Production | Software Project Management Section |  |  |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.20.45 |  | DMZ_DWH_WEB | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE1 | Pending | Pending
517 | Virtual | Hyper-V-VM | DC-IMPS-APP1 | DCHYPRVBASE2 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 81KHMY3 | Virtual Machine | Non-CBS | UAT | Online Banking Technology Mobile Banking | IMPS | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.168 |  | UAT_NCBS_APP | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE2 | Pending | Pending
518 | Virtual | Hyper-V-VM | DC-UAT-CKYCAPP | DCHYPRVBASE2 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 81KHMY3 | Virtual Machine | Non-CBS | Production | FCR Deposits Section | CKYC | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com | ADROIT | SAKTHIVEL ¦ 9688969398 ¦ sakthiveli' <sakthiveli@adroitcorporate.com> | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.157 |  | UAT_NCBS_APP | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE2 | Pending | Pending
519 | Virtual | Hyper-V-VM | DC-UAT-CKYCIMG | DCHYPRVBASE2 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 81KHMY3 | Virtual Machine | Non-CBS | Production | FCR Deposits Section | CKYC | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com | ADROIT | SAKTHIVEL ¦ 9688969398 ¦ sakthiveli' <sakthiveli@adroitcorporate.com> | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.158 |  | UAT_NCBS_APP | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE2 | Pending | Pending
520 | Virtual | Hyper-V-VM | UAT-APIBKG-APP6 | DCHYPRVBASE2 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 81KHMY3 | Virtual Machine | Non-CBS | UAT | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com |  | DCM ¦ DCM | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.151 |  | UAT_NCBS_APP | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE2 | Pending | Pending
521 | Virtual | Hyper-V-VM | UAT-APIBKG-APP7 | DCHYPRVBASE2 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 81KHMY3 | Virtual Machine | Non-CBS | UAT | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | Digital API Craft | Sandeep Kenkare Satya Janardhana ¦ 9886236345 ¦ sandeep.k@digitalapi.ai | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.152 |  | UAT_NCBS_APP | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE2 | Pending | Pending
522 | Virtual | Hyper-V-VM | UAT-INVOICE-GPU | DCHYPRVBASE2 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | 81KHMY3 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.33.133.208 |  | UAT_NCBS_APP2 | MZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHYPRVBASE2 | Pending | Pending
523 | Virtual | Hyper-V-VM | DCIRMSAPIO1 | DCIRMSBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 8KJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.134 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE1 | Pending | Pending
524 | Virtual | Hyper-V-VM | DCIRMSMETA02.aranac.com | DCIRMSBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 8KJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.154 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE1 | Pending | Pending
525 | Virtual | Hyper-V-VM | DCIRMSVAAR04.aranac.com | DCIRMSBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 8KJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.165 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE1 | Pending | Pending
526 | Virtual | Hyper-V-VM | DCIRMSVAAR08.aranac.com | DCIRMSBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 8KJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.164 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE1 | Pending | Pending
527 | Virtual | Hyper-V-VM | DCIRMSWEB01.aranac.com | DCIRMSBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 8KJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.13.65 |  | NCBS_WEB | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE1 | Pending | Pending
528 | Virtual | Hyper-V-VM | DCIRMSMID02.aranac.com | DCIRMSBASE10 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 8MJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.139 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE10 | Pending | Pending
529 | Virtual | Hyper-V-VM | DCIRMSVAAR11.aranac.com | DCIRMSBASE10 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 8MJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.172 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE10 | Pending | Pending
530 | Virtual | Hyper-V-VM | DCIRMSCOMP02 | DCIRMSBASE11 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 70KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.158 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE11 | Pending | Pending
531 | Virtual | Hyper-V-VM | DCIRMSVA06.aranac.com | DCIRMSBASE11 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 70KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.180 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE11 | Pending | Pending
532 | Virtual | Hyper-V-VM | DCIRMSAPI02 | DCIRMSBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 7MJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.135 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE2 | Pending | Pending
533 | Virtual | Hyper-V-VM | DCIRMSMETA03.aranac.com | DCIRMSBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 7MJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.155 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE2 | Pending | Pending
534 | Virtual | Hyper-V-VM | DCIRMSVAAR02.aranac.com | DCIRMSBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 7MJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.162 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE2 | Pending | Pending
535 | Virtual | Hyper-V-VM | DCIRMSVAAR03.aranac.com | DCIRMSBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 7MJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.163 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE2 | Pending | Pending
536 | Virtual | Hyper-V-VM | DCIRMSWEB02.aranac.com | DCIRMSBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 7MJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.13.66 |  | NCBS_WEB | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE2 | Pending | Pending
537 | Virtual | Hyper-V-VM | DCIRMSMID01.aranac.com | DCIRMSBASE3 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | HZJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.138 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE3 | Pending | Pending
538 | Virtual | Hyper-V-VM | DCIRMSVAAR05.aranac.com | DCIRMSBASE3 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | HZJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.166 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE3 | Pending | Pending
539 | Virtual | Hyper-V-VM | DCIRMSVA01.aranac.com | DCIRMSBASE4 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 50KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.175 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE4 | Pending | Pending
540 | Virtual | Hyper-V-VM | DCIRMSVAAR06.aranac.com | DCIRMSBASE4 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 50KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.167 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE4 | Pending | Pending
541 | Virtual | Hyper-V-VM | DCIRMSCOMP01.aranac.com | DCIRMSBASE5 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 30KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.159 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE5 | Pending | Pending
542 | Virtual | Hyper-V-VM | DCIRMSMETA01.aranac.com | DCIRMSBASE5 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 30KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.152 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE5 | Pending | Pending
543 | Virtual | Hyper-V-VM | DCIRMSVA02.aranac.com | DCIRMSBASE6 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 74LHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.176 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE6 | Pending | Pending
544 | Virtual | Hyper-V-VM | DCIRMSVAAR07.aranac.com | DCIRMSBASE6 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 74LHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.168 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE6 | Pending | Pending
545 | Virtual | Hyper-V-VM | DCIRMSVA03.aranac.com | DCIRMSBASE7 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | DKJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.177 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE7 | Pending | Pending
546 | Virtual | Hyper-V-VM | DCIRMSVAAR01.aranac.com | DCIRMSBASE7 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | DKJHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.169 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE7 | Pending | Pending
547 | Virtual | Hyper-V-VM | DCIRMSVA04.aranac.com | DCIRMSBASE8 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 91KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.178 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE8 | Pending | Pending
548 | Virtual | Hyper-V-VM | DCIRMSVAAR09.aranac.com | DCIRMSBASE8 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 91KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.170 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE8 | Pending | Pending
549 | Virtual | Hyper-V-VM | DCIRMSVA05.aranac.com | DCIRMSBASE9 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | G0KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.179 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE9 | Pending | Pending
550 | Virtual | Hyper-V-VM | DCIRMSVAAR10.aranac.com | DCIRMSBASE9 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | G0KHMY3 | Virtual Machine | Non-CBS | Production | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.35.171 |  | IRMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCIRMSBASE9 | Pending | Pending
551 | Virtual | Hyper-V-VM | DC-BRDPAC-WEB01 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | SPMS | Sudheer Kumar K ¦ 7095444823 ¦ sudheerkumar.k@canarabank.com | M/s BoardPAC | Venkat Sai ¦ 8019699471 ¦ venkatsaiv@boardpac.co | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.140 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
552 | Virtual | Hyper-V-VM | DC-CRMENCRYPT-WEB1 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | CRM | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | TechMatrix consulting pvt ltd | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com | LOW | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.155 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
553 | Virtual | Hyper-V-VM | DC-UATLAPSEXT-WEB2 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | Non-CBS | UAT | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.24 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
554 | Virtual | Hyper-V-VM | DC-UPI-WEB10 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | Non-CBS | Production | Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.2.155 |  | DMZ_MB_UPI | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
555 | Virtual | Hyper-V-VM | DC-UPIFIN-WEB02 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.32.2.143 |  |  |  | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
556 | Virtual | Hyper-V-VM | DC-UPIFIN-WEB03 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.33.2.148 |  |  |  | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
557 | Virtual | Hyper-V-VM | DCCCMSWEB2 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.66 |  | DMZ_WEB | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
558 | Virtual | Hyper-V-VM | DCPKIWEB01 | DCNCBSDMZBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 40KHMY3 | Virtual Machine | CBS | Production | Online Banking Technology Net banking Section | PKI | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com | AROOT TECHNOLOGY | SAI ¦ 9553966570 ¦ saivenkata.sr@emudhra.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.58 |  | DMZ_WEB | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE1 | Pending | Pending
559 | Virtual | Hyper-V-VM | CBDCUAT1-DTSP-WEB1 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | UAT | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | M/S Olive Crypto Systems Pvt Ltd | Sunil Kumar Lokanadam ¦ 917893603440 ¦ sunil.l@olivecrypto.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.193.91 |  | DMZ_UAT_CBDC_DTSP | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
560 | Virtual | Hyper-V-VM | CBDCUAT1-DTSP-WEB2 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | UAT | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | M/S Olive Crypto Systems Pvt Ltd | Sunil Kumar Lokanadam ¦ 917893603440 ¦ sunil.l@olivecrypto.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.193.92 |  | DMZ_UAT_CBDC_DTSP | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
561 | Virtual | Hyper-V-VM | CBDCUAT1-RTSP-WEB1 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | UAT | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | M/S Olive Crypto Systems Pvt Ltd | Sunil Kumar Lokanadam ¦ 917893603440 ¦ sunil.l@olivecrypto.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.193.89 |  | DMZ_UAT_CBDC_DTSP | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
562 | Virtual | Hyper-V-VM | CBDCUAT1-RTSP-WEB2 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | UAT | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | M/S Olive Crypto Systems Pvt Ltd | Sunil Kumar Lokanadam ¦ 917893603440 ¦ sunil.l@olivecrypto.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.193.90 |  | DMZ_UAT_CBDC_DTSP | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
563 | Virtual | Hyper-V-VM | DC-CRMENCRYPT-WEB2 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | CRM | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | TechMatrix consulting pvt ltd | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com | LOW | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.156 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
564 | Virtual | Hyper-V-VM | DC-QMS-WEB | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | Queue Management System | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | M/s AurionPro | Saroj Kumar Behra ¦ 8144648575 ¦ sarojkumar.behra@aurionpro.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.184 |  | DMZ_WEB_SERVERS | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
565 | Virtual | Hyper-V-VM | DC-UATLAPSEXT-WEB1 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | UAT | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.23 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
566 | Virtual | Hyper-V-VM | DCCCMSWEB1 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373/9880283138 ¦ hoccmssection@canarabank.com/hoccpstech@canarabank.com | M/s Aurionpro | Naveen/Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.1.64 |  | DMZ_WEB | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
567 | Virtual | Hyper-V-VM | DCCMSUATWEB1 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | NON-CBS | UAT | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.192.109 |  | DMZ_UAT | DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
568 | Virtual | Hyper-V-VM | DCNCBSQMSAPP2 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | Queue Management System | Saket/Ananda Dharshinee |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.92 |  | NCBS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
569 | Virtual | Hyper-V-VM | uat-capx-web2 | DCNCBSDMZBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | C0KHMY3 | Virtual Machine | Non-CBS | Production | Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | Hyper-V VM |  |  |  | X86 |  |  | 172.16.14.140 |  | TEST-DMZ-UAT-EXT | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSDMZBASE2 | Pending | Pending
570 | Virtual | Hyper-V-VM | DC-BRDPAC-APP01 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | Non-CBS | Production | SPMS | SPMS | Sudheer Kumar K ¦ 7095444823 ¦ sudheerkumar.k@canarabank.com | M/s BoardPAC | Venkat Sai ¦ 8019699471 ¦ venkatsaiv@boardpac.co | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.97 |  | NCBS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
571 | Virtual | Hyper-V-VM | DC-BRDPAC-DB01 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | Non-CBS | Production | SPMS | SPMS | Sudheer Kumar K ¦ 7095444823 ¦ sudheerkumar.k@canarabank.com | M/s BoardPAC | Venkat Sai ¦ 8019699471 ¦ venkatsaiv@boardpac.co | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.32.12.43 |  | NCBS_DB | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
572 | Virtual | Hyper-V-VM | DC-CANDASH-UAT | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | CBS | Production | Data Center Operations Section (ITI) | Treasuary Dashboard | Debjoy - 9874753518 ¦ debjoyroy@canarabank.com |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.198 |  | NCBS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
573 | Virtual | Hyper-V-VM | DC-QMS-APP1 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | Non-CBS | Production | SPMS | Queue Management System | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | M/s AurionPro | Saroj Kumar Behra ¦ 8144648575 ¦ sarojkumar.behra@aurionpro.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.93 |  | NCBS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
574 | Virtual | Hyper-V-VM | DC-QMS-DB1 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | Non-CBS | Production | SPMS | Queue Management System | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | M/s AurionPro | Saroj Kumar Behra ¦ 8144648575 ¦ sarojkumar.behra@aurionpro.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.12.113 |  | NCBS_DB | Internal | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
575 | Virtual | Hyper-V-VM | DC-Vanghee-APP1 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | Non-CBS | Notinuse | New Initiatives-Technology Innovation Section |  |  |  |  | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.248 |  | NCBS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
576 | Virtual | Hyper-V-VM | DCCCMSAPPBACK1 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.36 |  | CCMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
577 | Virtual | Hyper-V-VM | DCCCMSAPPFRONT1 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.38 |  | CCMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
578 | Virtual | Hyper-V-VM | DCCCMSBATCHAPP3 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.45 |  | CCMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
579 | Virtual | Hyper-V-VM | DCCCMSREDISCACHE1 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.40 |  | CCMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
580 | Virtual | Hyper-V-VM | DCCCMSREDISCACHE2 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.41 |  | CCMS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
581 | Virtual | Hyper-V-VM | DCPKIAPP01 | DCNCBSINTBASE1 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | CKJHMY3 | Virtual Machine | CBS | Production | Online Banking Technology Net banking Section | PKI | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com | AROOT TECHNOLOGY | SAI ¦ 9553966570 ¦ saivenkata.sr@emudhra.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.241 |  | NCBS_APP | NON DMZ | DC1 | 1 | N5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE1 | Pending | Pending
582 | Virtual | Hyper-V-VM | DC-ADRESTORE-TEST | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.5 |  | AD_DMS_Bkp_Rest | MZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
583 | Virtual | Hyper-V-VM | DC-GSTSAHY-APP1 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine |  |  | Digital Lending and LAPS Section | GST SAHAY |  |  |  |  | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.191 |  | NCBS_APP | MZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
584 | Virtual | Hyper-V-VM | DC-GSTSAHY-APP2 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine |  |  | Digital Lending and LAPS Section | GST SAHAY |  |  |  |  | Hyper-V VM |  |  |  | X86 |  |  | 10.32.11.192 |  | NCBS_APP | MZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
585 | Virtual | Hyper-V-VM | DCCCMSAPPBACK2 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.37 |  | CCMS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
586 | Virtual | Hyper-V-VM | DCCCMSAPPFRONT2 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.39 |  | CCMS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
587 | Virtual | Hyper-V-VM | DCCCMSBATCHAPP1 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.43 |  | CCMS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
588 | Virtual | Hyper-V-VM | DCCCMSBATCHAPP2 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.44 |  | CCMS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
589 | Virtual | Hyper-V-VM | DCCCMSREDISCACHE3 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine | NON-CBS | Production | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | M/s Aurionpro | Naveen/ ¦ Maheshwari ¦ 8885816400 ¦ CCPSSUPPORT@canarabank.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.38.42 |  | CCMS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
590 | Virtual | Hyper-V-VM | UATONDCAPP01 | DCNCBSINTBASE2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | D0KHMY3 | Virtual Machine | Non-CBS | Notinuse | Online Banking Technology Mobile Banking Section |  |  |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.111 |  | UAT_Non-CBS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCNCBSINTBASE2 | Pending | Pending
591 | Virtual | AIX-Lpar | DCLACBSESBPRDAP01 | E950-1-9040-MR9-SN78DE92X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE92X | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.21 |  | CBS_INTERFACE_NEW | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-1-9040-MR9-SN78DE92X | Pending | Pending
592 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP01 | E950-1-9040-MR9-SN78DE92X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE92X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.63 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-1-9040-MR9-SN78DE92X | Pending | Pending
593 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP02 | E950-1-9040-MR9-SN78DE92X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE92X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.64 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-1-9040-MR9-SN78DE92X | Pending | Pending
594 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP12 | E950-1-9040-MR9-SN78DE92X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE92X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.74 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-1-9040-MR9-SN78DE92X | Pending | Pending
595 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI01 | E950-1-9040-MR9-SN78DE92X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE92X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.21 |  | CBS_WEB | DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-1-9040-MR9-SN78DE92X | Pending | Pending
596 | Virtual | AIX-Lpar | DCLACBSOLTPPRDAP01 | E950-1-9040-MR9-SN78DE92X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE92X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.151 |  | CBS_OLTP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-1-9040-MR9-SN78DE92X | Pending | Pending
597 | Virtual | AIX-Lpar | AIX73TL3SP0_V | E950-2-9040-MR9-SN78DE93X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | Lpar | CBS | [7 empty] | LPAR |  |  |  | IBM Power |  |  | . |  |  |  | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-2-9040-MR9-SN78DE93X | Pending | Pending
598 | Virtual | AIX-Lpar | DCLACBSESBPRDAP02 | E950-2-9040-MR9-SN78DE93X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.22 |  | CBS_INTERFACE_NEW | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-2-9040-MR9-SN78DE93X | Pending | Pending
599 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP03 | E950-2-9040-MR9-SN78DE93X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.65 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-2-9040-MR9-SN78DE93X | Pending | Pending
600 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP04 | E950-2-9040-MR9-SN78DE93X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.66 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-2-9040-MR9-SN78DE93X | Pending | Pending
601 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP14 | E950-2-9040-MR9-SN78DE93X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.76 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-2-9040-MR9-SN78DE93X | Pending | Pending
602 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI03 | E950-2-9040-MR9-SN78DE93X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.23 |  | CBS_WEB | DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-2-9040-MR9-SN78DE93X | Pending | Pending
603 | Virtual | AIX-Lpar | DCLACBSOLTPPRDAP02 | E950-2-9040-MR9-SN78DE93X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE93X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.152 |  | CBS_OLTP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-2-9040-MR9-SN78DE93X | Pending | Pending
604 | Virtual | AIX-Lpar | DCLACBSESBPRDAP03 | E950-3-9040-MR9-SN78DE94X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE94X | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.23 |  | CBS_INTERFACE_NEW | Internal | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-3-9040-MR9-SN78DE94X | Pending | Pending
605 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP05 | E950-3-9040-MR9-SN78DE94X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE94X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.67 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-3-9040-MR9-SN78DE94X | Pending | Pending
606 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP06 | E950-3-9040-MR9-SN78DE94X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE94X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.68 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-3-9040-MR9-SN78DE94X | Pending | Pending
607 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP15 | E950-3-9040-MR9-SN78DE94X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE94X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.77 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-3-9040-MR9-SN78DE94X | Pending | Pending
608 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI05 | E950-3-9040-MR9-SN78DE94X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE94X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.25 |  | CBS_WEB | DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-3-9040-MR9-SN78DE94X | Pending | Pending
609 | Virtual | AIX-Lpar | DCLACBSOLTPPRDAP03 | E950-3-9040-MR9-SN78DE94X | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K3) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78DE94X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.153 |  | CBS_OLTP | NON DMZ | DC1 | 1 | K3 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-3-9040-MR9-SN78DE94X | Pending | Pending
610 | Virtual | AIX-Lpar | DCLACBSACEPRDAP01 | E950-4-9040-MR9-SN78DE95X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.29,10.32.7.25 |  | CBS_INTERFACE_NEW | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-4-9040-MR9-SN78DE95X | Pending | Pending
611 | Virtual | AIX-Lpar | DCLACBSACEPRDAP03 | E950-4-9040-MR9-SN78DE95X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.33, 10.32.7.27 |  | CBS_INTERFACE_NEW | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-4-9040-MR9-SN78DE95X | Pending | Pending
612 | Virtual | AIX-Lpar | DCLACBSESBPRDAP04 | E950-4-9040-MR9-SN78DE95X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.24 |  | CBS_INTERFACE_NEW | Internal | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-4-9040-MR9-SN78DE95X | Pending | Pending
613 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP07 | E950-4-9040-MR9-SN78DE95X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.69 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-4-9040-MR9-SN78DE95X | Pending | Pending
614 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP08 | E950-4-9040-MR9-SN78DE95X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.70 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-4-9040-MR9-SN78DE95X | Pending | Pending
615 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP17 | E950-4-9040-MR9-SN78DE95X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.79 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-4-9040-MR9-SN78DE95X | Pending | Pending
616 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI07 | E950-4-9040-MR9-SN78DE95X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE95X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.27 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-4-9040-MR9-SN78DE95X | Pending | Pending
617 | Virtual | AIX-Lpar | DCLACBSEXTAPIPRDAP01 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.83 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
618 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP11 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.73 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
619 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP13 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.75 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
620 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI02 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.22 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
621 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI04 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.24 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
622 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI12 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.32 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
623 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI13 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.33 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
624 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI14 | E950-5-9040-MR9-SN78DE96X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE96X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.34 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-5-9040-MR9-SN78DE96X | Pending | Pending
625 | Virtual | AIX-Lpar | DCLACBSEXTAPIPRDAP02 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.84 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
626 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP16 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.78 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
627 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP18 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.80 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
628 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI06 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.26 |  | CBS_WEB | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
629 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI08 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.28 |  | CBS_WEB | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
630 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI15 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.35 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
631 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI16 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.36 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
632 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI17 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.37 |  | CBS_WEB | DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
633 | Virtual | AIX-Lpar | DCLACBSOLTPPRDAP04 | E950-6-9040-MR9-SN78DE97X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K4) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE97X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.154 |  | CBS_OLTP | NON DMZ | DC1 | 1 | K4 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-6-9040-MR9-SN78DE97X | Pending | Pending
634 | Virtual | AIX-Lpar | DCLACBSACEPRDAP02 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.30,10.32.7.26 |  | CBS_INTERFACE_NEW | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
635 | Virtual | AIX-Lpar | DCLACBSACEPRDAP04 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | IIB(DCA) | IIB/ACE/ESB |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.7.34, 10.32.7.28 |  | CBS_INTERFACE_NEW | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
636 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP09 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.71 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
637 | Virtual | AIX-Lpar | DCLACBSHOSTPRDAP10 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.72 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
638 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI09 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.29 |  | CBS_WEB | DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
639 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI10 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.30 |  | CBS_WEB | DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
640 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI11 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.31 |  | CBS_WEB | DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
641 | Virtual | AIX-Lpar | DCLACBSHTTPPRDWI18 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.38 |  | CBS_WEB | DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
642 | Virtual | AIX-Lpar | DCLACBSOLTPPRDAP05 | E950-7-9040-MR9-SN78DE9AX | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE9AX | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.155 |  | CBS_OLTP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-7-9040-MR9-SN78DE9AX | Pending | Pending
643 | Virtual | AIX-Lpar | DCLACBNFSSERVER01 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | CBS NFS Server 1 |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.32 |  | DC-CBS_APP | Internal | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
644 | Virtual | AIX-Lpar | DCLACBSCOREUATDB05 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.33.129.73 |  | UAT_CBS_DB | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
645 | Virtual | AIX-Lpar | DCLACBSFLASHAP-NewLpar | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.1.87 |  | DC-CBS_APP | Internal | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
646 | Virtual | AIX-Lpar | DCLACBSFLASHAP01 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | CBS | Production | Data Center Operations Section (ITI) | DCO | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.85 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
647 | Virtual | AIX-Lpar | DCLACBSHOSTUATAP01 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.8.11 |  | CBS_REPORTS | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
648 | Virtual | AIX-Lpar | DCLACBSOLTPPRDAP06 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.6.156 |  | CBS_OLTP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
649 | Virtual | AIX-Lpar | DCLACBSOLTPUATAP01 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | CBS | UAT | Data Center Operations Section (ITI) | CBS UAT | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.33.129.201 |  | UAT_CBS_OLTP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
650 | Virtual | AIX-Lpar | DCLACBSREPPRDAP01 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.33.129.11 |  | UAT_CBS_APP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
651 | Virtual | AIX-Lpar | DCLACBSREPUATAP01 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | CBS | UAT | Data Center Operations Section (ITI) | DCO | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.33.130.71 |  | UAT_CBS_REPORTS | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
652 | Virtual | AIX-Lpar | DCPOWERVC01 | E950-8-9040-MR9-SN78DE98X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE98X | Lpar | CBS | [7 empty] | LPAR |  |  |  | IBM Power |  |  | . |  |  |  | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-8-9040-MR9-SN78DE98X | Pending | Pending
653 | Virtual | AIX-Lpar | DCLACBNFSSERVER02 | E950-9-9040-MR9-SN78DE99X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE99X | Lpar | CBS | Production | Data Center Operations Section (ITI) | NFS | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.1.33 |  | DC-CBS_APP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-9-9040-MR9-SN78DE99X | Pending | Pending
654 | Virtual | AIX-Lpar | DCLACBSCOREUATDB06 | E950-9-9040-MR9-SN78DE99X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE99X | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.33.129.78 |  | UAT_CBS_DB | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-9-9040-MR9-SN78DE99X | Pending | Pending
655 | Virtual | AIX-Lpar | DCLACBSFLASHAP02 | E950-9-9040-MR9-SN78DE99X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE99X | Lpar | CBS | Production | Data Center Operations Section (ITI) | DCO | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.33.129.13 |  | UAT_CBS_APP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-9-9040-MR9-SN78DE99X | Pending | Pending
656 | Virtual | AIX-Lpar | DCLACBSHOSTUATAP02 | E950-9-9040-MR9-SN78DE99X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE99X | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.33.129.12 |  | UAT_CBS_APP | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-9-9040-MR9-SN78DE99X | Pending | Pending
657 | Virtual | AIX-Lpar | DCLACBSREPPRDAP02 | E950-9-9040-MR9-SN78DE99X | 2 | TR-2.9 | Moves with host (Loaded in OEM rack K5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:30 | 78DE99X | Lpar | CBS | Production | CBS(UTKARSH) | CBS(UTKARSH) | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.8.12 |  | CBS_REPORTS | NON DMZ | DC1 | 1 | K5 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E950-9-9040-MR9-SN78DE99X | Pending | Pending
658 | Virtual | AIX-Lpar | DCAADHARVAULTDB2 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Government Business and Financial Inclusion Section | DC Aadhar Vault DB |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.198 |  | AADHAR_VAULT_DB | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
659 | Virtual | AIX-Lpar | DCAIX72NIM | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | NIM | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.34 |  | Database | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
660 | Virtual | AIX-Lpar | DCDEVFCAPP | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | CBS | Production | Data Center Operations Section (ITI) | DCO | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.37 |  | UAT-2-APP | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
661 | Virtual | AIX-Lpar | DCESBFCDB01 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.255.73 |  | UAT-2-DB | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
662 | Virtual | AIX-Lpar | DCFCCFO | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | FCC Section | FSCM | Manoj Kumar T ¦ 9300331307 ¦ manojkumart@canarabank.com |  | FCC Group | High | LPAR |  |  |  | IBM Power |  |  | 172.16.38.47 |  | Database | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
663 | Virtual | AIX-Lpar | DCFCRARCHFO | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.140 |  | Database | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
664 | Virtual | AIX-Lpar | DCFCRDBFO | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.212 |  | Database | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
665 | Virtual | AIX-Lpar | DCFCUBSPRDAP02 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | SUNIL KASHIKAR | 9900139448 ¦ sunilr.kashikar@kyndryl.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.38 |  | FCUBS_APP | DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
666 | Virtual | AIX-Lpar | DCFRSDB19C | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | CBS | [7 empty] | LPAR |  |  |  | IBM Power |  |  | 172.16.38.227 |  |  |  | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
667 | Virtual | AIX-Lpar | DCINTDB | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.2.132 |  | InternationBrch-DB | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
668 | Virtual | AIX-Lpar | DCINTREP1 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.1.16 |  | InternationBrch-App | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
669 | Virtual | AIX-Lpar | DCLADB1EKYCPRD | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | To Be Confirmed |  |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.11.134 |  | Non-CBS_DB_2 | Internal | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
670 | Virtual | AIX-Lpar | DCLADB1TABBPRD | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | To Be Confirmed |  |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.11.137 |  | Non-CBS_DB_2 | Internal | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
671 | Virtual | AIX-Lpar | DCLAPSPRODDB1 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Online Banking Technology Mobile Banking | UPI | NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com | NPST | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.52.3 |  | NCBS_DB_NEW | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
672 | Virtual | AIX-Lpar | DCMIGFCAPP1 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | CBS | Production | Data Center Operations Section (ITI) | DCO | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.41 |  | UAT-2-APP | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
673 | Virtual | AIX-Lpar | DCMIGFCDB01 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.75 |  | UAT-2-DB | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
674 | Virtual | AIX-Lpar | DCNEFTARCH | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.52.65 |  | NCBS_DB_NEW | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
675 | Virtual | AIX-Lpar | DCNONCBSARCH | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.52.66 |  | NCBS_DB_NEW | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
676 | Virtual | AIX-Lpar | DCNONCBSFLASH | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | GBM flash | Sangeetha ¦ sangeetha_r@canarabank.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.251 |  | Database | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
677 | Virtual | AIX-Lpar | DCREP01 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | CBS | Production | Data Center Operations Section (ITI) | DCO | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.46 |  | UAT-2-APP | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
678 | Virtual | AIX-Lpar | DCSHADOW5 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.4 |  | Database | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
679 | Virtual | AIX-Lpar | DCSITRACDB1 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.81 |  | UAT-2-DB | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
680 | Virtual | AIX-Lpar | DCUATFCAPP1 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | CBS | UAT | Data Center Operations Section (ITI) | FCR Retail | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.40 |  | UAT-2-APP | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
681 | Virtual | AIX-Lpar | DC_TSM_DB | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.96 |  | Database | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
682 | Virtual | AIX-Lpar | SWIFTINSAADR | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | TM Section Integrated Treasury Wing | Swift | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com | SWIFT | SWIFT DOMESTIC ¦ Swapnil ¦ 9743605215 | Low | LPAR |  |  |  | IBM Power |  |  | 172.16.10.163 |  | SWIFT_ALLIANCE_ACCESS | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
683 | Virtual | AIX-Lpar | UATTESTLPAR73 | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.80 |  | UAT-2-DB | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
684 | Virtual | AIX-Lpar | nim | E980-1-9080-M9S-SN78414F8 | 2 | TR-2.7 | Moves with host (Loaded in OEM rack K1) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 9:30 | 78414F8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | NIM | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.93 |  | UAT-2-DB | NON DMZ | DC1 | 1 | K1 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-1-9080-M9S-SN78414F8 | Pending | Pending
685 | Virtual | AIX-Lpar | CBSUATM1 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.36.118 |  | DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
686 | Virtual | AIX-Lpar | CBSUATM3 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.36.117 |  | DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
687 | Virtual | AIX-Lpar | DCAADHARVAULTDB1 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Government Business and Financial Inclusion Section | DB server |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.27.197 |  | AADHAR_VAULT_DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
688 | Virtual | AIX-Lpar | DCFCUBSPRDAP01 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | Production | FCUBS | FCUBS | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com / PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.37 |  | FCUBS_APP | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
689 | Virtual | AIX-Lpar | DCFCUBSPRDDB02 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | SUNIL KASHIKAR | 9900139448 ¦ sunilr.kashikar@kyndryl.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.69 |  | FCUBS_DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
690 | Virtual | AIX-Lpar | DCLADB2EKYCPRD | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Government Business and Financial Inclusion Section | EKYC |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.11.135 |  | Non-CBS_DB_2 | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
691 | Virtual | AIX-Lpar | DCLADB2TABBPRD | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Government Business and Financial Inclusion Section | TAB |  |  |  | Low | LPAR |  |  |  | IBM Power |  |  | 172.16.11.138 |  | Non-CBS_DB_2 | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
692 | Virtual | AIX-Lpar | DCLAPSPRODDB2 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Online Banking Technology Mobile Banking | UPI | NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com | NPST | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.52.4 |  | NCBS_DB_NEW | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
693 | Virtual | AIX-Lpar | DCMIGFCAPP2 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | Production | Data Center Operations Section (ITI) | DCO | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.42 |  | UAT-2-APP | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
694 | Virtual | AIX-Lpar | DCPGRSDBFO | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.3.81 |  | NON-CBS_DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
695 | Virtual | AIX-Lpar | DCPOWERSC02 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.14.37 |  | CBS_POWERSC_PATCH_MGMT | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
696 | Virtual | AIX-Lpar | DCPOWERSCGUI | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.14.38 |  | CBS_POWERSC_PATCH_MGMT | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
697 | Virtual | AIX-Lpar | DCSITESB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.47 |  | UAT-2-APP | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
698 | Virtual | AIX-Lpar | DCSITRACDB2 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.82 |  | UAT-2-DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
699 | Virtual | AIX-Lpar | DCUATFCDB1 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.74 |  | UAT-2-DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
700 | Virtual | AIX-Lpar | DC_SHADOW2_DB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.76 |  | Database | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
701 | Virtual | AIX-Lpar | DC_Shadow4 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.142 |  | Database | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
702 | Virtual | AIX-Lpar | DC_TSM_DB_FO | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.217 |  | Database | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
703 | Virtual | AIX-Lpar | DEVFCUBSAPP | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | FCUBS | FCUBS | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.33.130.132 |  | UAT_FCUBS_VER_UPGRADE | DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
704 | Virtual | AIX-Lpar | DEVFUBSDB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | SUNIL KASHIKAR | 9900139448 ¦ sunilr.kashikar@kyndryl.com | Low | LPAR |  |  |  | IBM Power |  |  | 10.33.130.133 |  | UAT_FCUBS_VER_UPGRADE | DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
705 | Virtual | AIX-Lpar | MBDBUAT | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.36.119 |  | DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
706 | Virtual | AIX-Lpar | MIGFCUBSAPP | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | FCUBS | FCUBS | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.33.130.139 |  | UAT_FCUBS_VER_UPGRADE | DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
707 | Virtual | AIX-Lpar | MIGFCUBSDB2 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | SUNIL KASHIKAR | 9900139448 ¦ sunilr.kashikar@kyndryl.com | Low | LPAR |  |  |  | IBM Power |  |  | 10.33.130.138 |  | UAT_FCUBS_VER_UPGRADE | DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
708 | Virtual | AIX-Lpar | OBUATDB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Online Banking Technology Mobile Banking | MB | Arjun ¦ 9952404855 ¦ hotomb@canarabank.com | NPST | Anandababu ¦ 7975771359 ¦ anandababu.m@npstx.com | High | LPAR |  |  |  | IBM Power |  |  | 172.16.36.76 |  | DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
709 | Virtual | AIX-Lpar | UATFCUBSAPP | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | FCUBS | FCUBS | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.33.130.134 |  | UAT_FCUBS_VER_UPGRADE | DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
710 | Virtual | AIX-Lpar | UATFCUBSDB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | SUNIL KASHIKAR | 9900139448 ¦ sunilr.kashikar@kyndryl.com | Low | LPAR |  |  |  | IBM Power |  |  | 10.33.130.135 |  | UAT_FCUBS_VER_UPGRADE | DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
711 | Virtual | AIX-Lpar | UATGIFTOBDXAPP | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | Online Banking Technology Net banking Section | GIFTCITY OBDX | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.130.137 |  | UAT_FCUBS_VER_UPGRADE | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
712 | Virtual | AIX-Lpar | UATGIFTOBDXDB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | Online Banking Technology Net banking Section | GIFTCITY OBDX | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.130.136 |  | UAT_FCUBS_VER_UPGRADE | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
713 | Virtual | AIX-Lpar | UATGIFTOBDXWEB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | Online Banking Technology Net banking Section | GIFTCITY OBDX | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.192.87 |  | DMZ_UAT | DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
714 | Virtual | AIX-Lpar | UATNIMSERVER | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | NIM | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.36.80 |  | DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
715 | Virtual | AIX-Lpar | UATTESTLPAR72 | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Data Center Operations Section (ITI) | DCO | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.36.81 |  | DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
716 | Virtual | AIX-Lpar | UTKHCOREPFUATDB | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.255.45 |  | UAT-2-APP | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
717 | Virtual | AIX-Lpar | amldbuat | E980-2-9080-M9S-SN78415A8 | 2 | TR-2.8 | Moves with host (Loaded in OEM rack K2) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 10:00 | 78415A8 | Lpar | Non-CBS | UAT | Government Business and Financial Inclusion Section | DB |  |  |  | Low | LPAR |  |  |  | IBM Power |  |  | 172.16.36.84 |  | DB | NON DMZ | DC1 | 1 | K2 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host E980-2-9080-M9S-SN78415A8 | Pending | Pending
718 | Virtual | Hyper-V-VM | UATAPP-SASCOMPUTE.aranac.com | EWIRMUATAPPBASE | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 7V1N0V3 | Virtual Machine | Non-CBS | UAT | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.134.68 |  | IRMS_UAT_App | NON DMZ | DC2 | 2 | X2 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2) | A | [6 empty] | Yes |  | Inherits batch of host EWIRMUATAPPBASE | Pending | Pending
719 | Virtual | Hyper-V-VM | UATAPP-SASMIP.aranac.com | EWIRMUATAPPBASE | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 7V1N0V3 | Virtual Machine | Non-CBS | UAT | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | M/s SAS Institute India Pvt. Ltd | Aljin Ovelil ¦ 6282919328 ¦ Aljin.Ovelil@sas.com | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.33.134.69 |  | IRMS_UAT_App | NON DMZ | DC2 | 2 | X2 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2) | A | [6 empty] | Yes |  | Inherits batch of host EWIRMUATAPPBASE | Pending | Pending
720 | Virtual | AIX-Lpar | DCAMLDBFO | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | MADHAVI GEDELA | 6304027118 ¦ madhavi.gedela@kiya.ai | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.24 |  | Database | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
721 | Virtual | AIX-Lpar | DCCBSUATAP03 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.33.129.14 |  | UAT_CBS_APP | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
722 | Virtual | AIX-Lpar | DCCBSUATDB03 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.33.129.79 |  | UAT_CBS_DB | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
723 | Virtual | AIX-Lpar | DCFCCDB | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.38.43 |  | Database | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
724 | Virtual | AIX-Lpar | DCGIFTOBDXAPP | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | GIFTCITY OBDX | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.39 |  | FCUBS_APP | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
725 | Virtual | AIX-Lpar | DCGIFTOBDXDB | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | GIFTCITY OBDX |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 10.32.27.73,10.32.27.75 |  | FCUBS_DB | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
726 | Virtual | AIX-Lpar | DCGIFTOBDXWEB | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | GIFTCITY OBDX | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.97 |  | DMZ_WEB | DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
727 | Virtual | AIX-Lpar | DCLADB1GBMNPRD | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Government Business and Financial Inclusion Section | CEDGE |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.11.148 |  | Non-CBS_DB_2 | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
728 | Virtual | AIX-Lpar | DCLAPSWEB6 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.13.35 |  | NCBS_WEB | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
729 | Virtual | AIX-Lpar | DCMBRACDB1 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Online Banking Technology Mobile Banking | MOBILE BANKING | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.12.96 |  | NCBS_DB | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
730 | Virtual | AIX-Lpar | DCPOWERSC01 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Anil - Kyndryl ¦ anil.biswal@kyndryl.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 10.32.14.36 |  | CBS_POWERSC_PATCH_MGMT | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
731 | Virtual | AIX-Lpar | DC_SHADOW3 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.83 |  | Database | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
732 | Virtual | AIX-Lpar | FCCPTVU | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | CBS | UAT | CBS(UTKARSH) | CBS(UTKARSH) |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.36.110 |  | DB | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
733 | Virtual | AIX-Lpar | LAPSAPP1 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.11.59 |  | NCBS_APP | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
734 | Virtual | AIX-Lpar | LAPSCONNP1 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.11.61 |  | NCBS_APP | NON DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
735 | Virtual | AIX-Lpar | LAPSWEB1 | Server1-9080-M9S-SN783BFE8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C6) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFE8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.33.1.39 |  | DMZ_WEB | DMZ | DC1 | 1 | C6 | [7 empty] | Via host (Yes) | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2), DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server1-9080-M9S-SN783BFE8 | Pending | Pending
736 | Virtual | AIX-Lpar | DCAMLDB | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | MADHAVI GEDELA | 6304027118 ¦ madhavi.gedela@kiya.ai | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.225 |  | Database | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
737 | Virtual | AIX-Lpar | DCFCRARCH | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.38.80,172.16.38.144 |  | Database | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
738 | Virtual | AIX-Lpar | DCFCRARCH | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Data Warehouse Section | Data Warehouse |  |  |  | Low | LPAR |  |  |  | IBM Power |  |  | 172.16.38.144 |  | Database | Internal | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
739 | Virtual | AIX-Lpar | DCLADB2GBMNPRD | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Government Business and Financial Inclusion Section | CEDGE |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.11.133 |  | Non-CBS_DB_2 | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
740 | Virtual | AIX-Lpar | DCLAPSWEB3 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.13.31 |  | NCBS_WEB | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
741 | Virtual | AIX-Lpar | DCLAPSWEB5 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.13.113 |  | NCBS_WEB | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
742 | Virtual | AIX-Lpar | DCMBRACDB2 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Online Banking Technology Mobile Banking | MOBILE BANKING | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | NPST (Development) | Ramesh Kosuru ¦ 9959391851 ¦ ramesh.kosuru@npstx.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.12.98 |  | NCBS_DB | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
743 | Virtual | AIX-Lpar | DCOBDXDB2 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | CBS | Production | Online Banking Technology Net banking Section | OBDX | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | OFSS | RAGHAV ¦ 9886253123 ¦ raghavendra.shivaram@oracle.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.18.198 |  | INTERNET_BANKING_OBDX_DB | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
744 | Virtual | AIX-Lpar | DCPGRSDB | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Data Center Operations Section (ITI) | DCO |  |  |  | High | LPAR |  |  |  | IBM Power |  |  | 172.16.3.77 |  | NON-CBS_DB | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
745 | Virtual | AIX-Lpar | DCSITMIGFCAPP1 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | CBS | Production | Data Center Operations Section (ITI) | DCO | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com |  |  | Medium | LPAR |  |  |  | IBM Power |  |  | 172.16.255.44 |  | UAT-2-APP | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
746 | Virtual | AIX-Lpar | LAPSAPP2 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.11.60 |  | NCBS_APP | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
747 | Virtual | AIX-Lpar | LAPSCONNP2 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.11.62 |  | NCBS_APP | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
748 | Virtual | AIX-Lpar | LAPSWEB2 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.13.11 |  | NCBS_WEB | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
749 | Virtual | AIX-Lpar | LAPSWEB4 | Server2-9080-M9S-SN783BFC8 | 2 | TR-2.4 | Moves with host (Loaded in OEM rack C5) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 8:00 | 783BFC8 | Lpar | Non-CBS | Production | Digital Lending and LAPS Section | LAPS | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | High | LPAR |  |  |  | IBM Power |  |  | 10.32.13.7 |  | NCBS_WEB | NON DMZ | DC1 | 1 | C5 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | yes |  | Inherits batch of host Server2-9080-M9S-SN783BFC8 | Pending | Pending
750 | Virtual | Hyper-V-VM | DC-CMS-DB | WIN-4JIKE60P6JV | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 90KHMY3 | Virtual Machine | Non-CBS | Production | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | Landmark Solutions | Ajikya Hatim ¦ 9768524076 ¦ ajinkya@lsssoftware.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.52.94 |  | NCBS_DB_NEW | DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-4JIKE60P6JV | Pending | Pending
751 | Virtual | Hyper-V-VM | DC-KYNDRYL-SFTP | WIN-4JIKE60P6JV | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 90KHMY3 | Virtual Machine | Non-CBS | Production | Data Center Operations Section (ITI) | DCO | Mansoor Hussain - Kyndryl ¦ Mansoor.Hussain@kyndryl.com |  |  | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.38 |  | UAT_Non-CBS_APP | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-4JIKE60P6JV | Pending | Pending
752 | Virtual | Hyper-V-VM | DC-SANnav | WIN-4JIKE60P6JV | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 90KHMY3 | Virtual Machine | Non-CBS | Production | Data Center Operations Section (ITI) | SANNAV Tool |  |  |  | Low | Hyper-V VM |  |  |  | X86 |  |  | 10.32.202.60 |  | CBS_STORAGE_MGMT | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-4JIKE60P6JV | Pending | Pending
753 | Virtual | Hyper-V-VM | DC-TNZDB | WIN-4JIKE60P6JV | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 90KHMY3 | Virtual Machine | CBS | Production | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | Karthik Manoharan | +91 8147387273 ¦ mk@wecodee.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.32.52.67 |  | NCBS_DB_NEW | Internal | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-4JIKE60P6JV | Pending | Pending
754 | Virtual | Hyper-V-VM | DC-Tableau-Server | WIN-4JIKE60P6JV | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 90KHMY3 | Virtual Machine | Non-CBS | Production | SPMS | CRM | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | TechMatrix consulting pvt ltd | G V ROSHAN ¦ 9025094423 ¦ gv.roshan@techmatrixconsulting.com | LOW | Hyper-V VM |  |  |  | X86 |  |  | 10.32.51.8 |  | NCBS_APP_NEW | NON DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-4JIKE60P6JV | Pending | Pending
755 | Virtual | Hyper-V-VM | UAT-CDSL-DB | WIN-4JIKE60P6JV | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | 90KHMY3 | Virtual Machine | Non-CBS | UAT | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | Landmark Solutions | Ajikya Hatim ¦ 9768524076 ¦ ajinkya@lsssoftware.com | High | Hyper-V VM |  |  |  | X86 |  |  | 10.33.132.121 |  | UAT_Non-CBS_DB | DMZ | DC1 | 1 | M1 | [7 empty] | Via host (Yes) | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-4JIKE60P6JV | Pending | Pending
756 | Virtual | Hyper-V-VM | DC-JIOMONITOR | WIN-STLAAFKA5J2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | BKJHMY3 | Virtual Machine | [8 empty] | Hyper-V VM |  |  |  | X86 |  |  | 10.32.66.245 |  | JIO_VM_MONITOR | MZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-STLAAFKA5J2 | Pending | Pending
757 | Virtual | Hyper-V-VM | DC-UATLAPS-APP1 | WIN-STLAAFKA5J2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | BKJHMY3 | Virtual Machine | Non-CBS | UAT | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.170 |  | UAT_NCBS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-STLAAFKA5J2 | Pending | Pending
758 | Virtual | Hyper-V-VM | DC-UATLAPS-APP2 | WIN-STLAAFKA5J2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | BKJHMY3 | Virtual Machine | Non-CBS | UAT | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.131.171 |  | UAT_NCBS_APP | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-STLAAFKA5J2 | Pending | Pending
759 | Virtual | Hyper-V-VM | DC-UATLAPSINTER-WEB | WIN-STLAAFKA5J2 | 2 | TR-2.13 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:30 | BKJHMY3 | Virtual Machine | Non-CBS | UAT | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | SysArc Infomatix Private Limited | T S Anand Subramanian ¦ 95000 76773 ¦ anand.subramanian@sysarcinfomatix.com | Medium | Hyper-V VM |  |  |  | X86 |  |  | 10.33.133.30 |  | UAT_Non-CBS_WEB | NON DMZ | DC1 | 1 | M7 | [7 empty] | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host WIN-STLAAFKA5J2 | Pending | Pending
760 | Virtual | Hyper-V-VM | DCHRMAPP1.canarabank.in | DCHVCLSTRN07 | 2 | TR-2.12 | Moves with host (Unracked (loose)) | 2026-10-24 | 20:30 | 2026-10-25 | 0:30 | 12:00 | G3SXMZ3 | Virtual Machine | Non-CBS | [7 empty] | Hyper-V VM |  |  |  | X86 | [6 empty] | DC1 | 1 | J2 |  |  |  | H | H-01 |  |  | Via host (Yes) | DCX-BLR3SSWPC2111 (B2), DCX-BLR3SSWPC2112 (B2) | A+B | [6 empty] | Yes |  | Inherits batch of host DCHVCLSTRN07 | Pending | Pending

## Scope_Racks
Destination Rack @ STT |  | Recommendation | Recommended Rack | Socket Type | Remarks | Requires PDU Change? | Rack Type | Required Power Circuit | Remarks
C-08 | #N/A | Lift & Shift | IBM Rack (C1) | Single Phase 63 Amps |  | Yes | OEM | 2+2 | OEM rack - so need to use existing PDU
J-07 | #N/A | Lift & Shift | Net Rack (X5) | Three Phase 32 Amps |  |  | OLD | 1+1 | New rack - assume STT gives PDU
N-03 | #N/A | Lift & Shift | GR-A2 | Three Phase 32 Amps |  |  | Migration Rack | 1+1 | Migration racks - assume existing PDUs are available
N-04 | #N/A | Lift & Shift | GR-A1 | Three Phase 32 Amps |  |  | Migration Rack | 1+1 | Migration racks - assume existing PDUs are available
N-02 | #N/A | Lift & Shift | GR-A4 | Single Phase 63 Amps |  | Yes | Migration Rack | 2+2 | Migration racks - assume existing PDUs are available
N-01 | #N/A | Lift & Shift | GR-A3 | Three Phase 32 Amps |  |  | Migration Rack | 1+1 | Migration racks - assume existing PDUs are available
G-13 | #N/A | Lift & Shift | IBM rack (A1) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
G-14 | #N/A | Lift & Shift | IBM rack (A2) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
D-13 | #N/A | Lift & Shift | IBM Rack (A5) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
C-12 | #N/A | Lift & Shift | IBM Rack (A6) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
G-15 | #N/A | Lift & Shift | IBM rack (C2) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
H-14 | #N/A | Lift & Shift | IBM rack (C3) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
H-13 | #N/A | Lift & Shift | IBM rack (C4) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
G-17 | #N/A | Lift & Shift | IBM rack (C5) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
H-17 | #N/A | Lift & Shift | IBM rack (C6) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
H-15 | #N/A | Lift & Shift | IBM rack (D1) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
D-09 | #N/A | Lift & Shift | IBM Rack (D3) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
D-04 | #N/A | Lift & Shift | WQ Rack (D5) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
C-07 | #N/A | Lift & Shift | IBM Rack (D6) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU
H-08 | #N/A | Lift & Shift | IBM rack (K3) | Single Phase 32 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU
G-09 | #N/A | Lift & Shift | IBM rack (K2) |  |  |  | OEM | 3+3 | Single Phase 32 A, 3+3 as per installed, need to use existing PDU
H-09 | #N/A | Lift & Shift | IBM rack (K1) | Single Phase 32 Amps | Single Phase 32 A, 2+2 as per installed, need to use existing PDU |  | OEM | 3+3 | Single Phase 32 A, 2+2 as per installed, need to use existing PDU
G-08 | #N/A | Lift & Shift | IBM rack (K4) |  |  |  | OEM | 3+3 | Single Phase 32 A, 3+3 as per installed, need to use existing PDU
G-20 | #N/A | Lift & Shift | IBM rack (K6) |  |  |  | OEM | 1+1 | Single Phase 32 A, 2+2 as per installed, need to use existing PDU
C-01 | #N/A | Lift & Shift | IBM LTO8 tape library (L1) |  |  |  | OEM | 1+1 | Single Phase 32 A, 1+1 as per installed, need to use existing PDU
C-02 | #N/A | Lift & Shift | IBM LTO8 tape library (L2) |  |  |  | OEM | 1+1 | Single Phase 32 A, 1+1 as per installed, need to use existing PDU
C-03 | #N/A | Lift & Shift | IBM LTO8 tape library (L3) |  |  |  | OEM | 1+1 | Single Phase 32 A, 1+1 as per installed, need to use existing PDU
H-19 | #N/A | Lift & Shift | IBM rack (L5) |  |  |  | OEM | 1+1 | Single Phase 32 A, 2+2 as per installed, need to use existing PDU
G-05 | #N/A | Lift & Shift | Dell Rack (W3) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU
G-04 | #N/A | Lift & Shift | Dell Rack (W4) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU
G-03 | #N/A | Lift & Shift | Dell Rack (W5) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU
H-06 | #N/A | Lift & Shift | Dell Rack (W6) |  |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU
H-05 | H-05 | Migrated | WQ Rack (AF2) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
C-05 | C-05 | Migrated | WQ Rack (AA2) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
C-14 | C-14 | Migrated | WQ Rack (AB2) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
D-14 | D-14 | Migrated | WQ Rack (AD2) | Three Phase 32 Amps | Shift the rack from D-20. (The existing rack was moved to L-13 ) |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
D-06 | D-06 | Migrated | WQ Rack (AC6) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
H-02 | H-02 | Migrated | WQ Rack (AE4) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
I-06 | I-06 | Migrated | Net Rack (AA5) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
K-08 | K-08 | Migrated | WQ rack (M1) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
L-01 | #N/A | Shift rack from I-20 | WQ rack (N5) | Three Phase 32 Amps | Active devices present. The rack N5 will be vacated in future waves |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
H-01 | H-01 | Migrated | WQ Rack (AE3) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
L-02 | #N/A | Migrated | WQ rack (AA6) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling
J-08 | #N/A | Move rack from J-09 | Net Rack (X7) | Three Phase 32 Amps | Active deivces present. The rack X7 will be vacated in future waves |  | OLD | 1+1 | In other list says new rack, please verify
J-05 | #N/A | Move rack from J-06 | Net Rack (U2) | Three Phase 32 Amps | Active devices present. The rack U2 will be vacated in future waves |  | OLD | 1+1 | In other list says new rack, please verify
I-08 | I-08 | Migrated | Net Rack (AB4) | Three Phase 32 Amps |  |  | OLD | 1+1 | In other list says new rack, please verify
I-11 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU, they installed 1+1 3ph & 1+1 1 ph
G-10 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
E-16 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
F-01 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
G-11 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
L-11 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU, they installed 1+1 3ph & 1+1 1 ph
D-10 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
H-10 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
D-11 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
H-11 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
C-11 | #N/A | Lift & Shift | IBM Rack (D2) | NA |  |  | OEM | 2+2 | OEM rack, single phase 63A 2+2 installed
A-10 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
B-10 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
F-15 | #N/A | Lift & Shift | IBM Rack (A4) | Three Phase 32 Amps |  |  | OEM | 1+1 | OEM rack, 3 ph 32 A socket installed, need to use existing PDU
E-02 | #N/A | New rack |  | Single Phase 63 Amps |  |  | OLD | 1+1 | OEM rack, single phase 63A 1+1 installed
F-07 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
E-07 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
E-08 | #N/A | New rack |  | NA |  |  | New Rack | 2+2 | 3ph 1+1 and 1 ph 2+2 installed, 3Ph 1+1 PDU to be arranged by STT
F-08 | #N/A | New rack |  | NA |  |  | New Rack | 2+2 | 3ph 1+1 and 1 ph 2+2 installed, 3Ph 1+1 PDU to be arranged by STT
F-09 | #N/A | New rack |  | NA |  |  | New Rack | 4+4 | 3ph 1+1 and 1 ph 4+4 installed, 3Ph 1+1 PDU to be arranged by STT
E-09 | #N/A | New rack |  | NA |  |  | New Rack | 4+4 | 3ph 1+1 and 1 ph 4+4 installed, 3Ph 1+1 PDU to be arranged by STT
E-06 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
F-05 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
A-08 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
A-09 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
I-10 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
F-16 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
E-01 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
E-11 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
F-11 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
F-12 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
E-12 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
E-05 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
F-03 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU
L-10 | #N/A | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU

## Shutdown_Startup_Seq (hidden)
SHUTDOWN & STARTUP SEQUENCE – BY BATCH
Shutdown order: Applications → Databases → LPARs/VMs → Physical servers → Storage/SVC/Tape → SAN switches → Network/Security. Startup at target in reverse order.
Movement Batch | Shutdown Seq Group | Planned Shutdown (from Cutover) | Startup Order at Target | App Owner Group | Application | Physical / Virtual | Serial Number | Server Model | Hostname | Physical Host Name | IP | Application Shutdown | Resource Name | Database Shutdown | Resource | LPAR / VM Shutdown | Resource Name2 | Physical Device Shutdown | Resource Name3 | Shutdown Status | Startup Status
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 |  |  | Hyper-V VM | C8SSN24 |  | NDC-CCIL-APP-1 | NDC-BASENDC-APP | 10.32.230.37 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | DPSecure | Dpsecure | Hyper-V VM | C8SSN24 |  | NDC-DPSECURE-DB | NDC-BASENDC-APP | 10.32.206.199 | Application Team | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | DPSecure | Dpsecure | Hyper-V VM | C8SSN24 |  | NDC-DPSecure-APP | NDC-BASENDC-APP | 10.32.206.134 | Application Team | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78A1DE8 |  | DCP10CBSPRDDB02 | C3-9080-HEX-SN78A1DE8-CORE_DB-2 | 10.32.2.67 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | IT Assets Management Section | RAP Remote | Hyper-V VM | C8SSN24 |  | RAP-DC-PRB1-DB01 | NDC-BASENDC-APP | 10.32.52.201 | Application Team | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | IT Assets Management Section | RAP Remote | Hyper-V VM | C8SSN24 |  | RAP-DC-PRB2-DB01 | NDC-BASENDC-APP | 10.32.52.202 | Application Team | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | IT Assets Management Section | RAP Remote | Hyper-V VM | C8SSN24 |  | RAP-DC-SUM-DB01 | NDC-BASENDC-APP | 10.32.52.200 | Application Team | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | IT Assets Management Section | RAP Remote | Hyper-V VM | C8SSN24 |  | RAP-DC-UAT-SUM01 | NDC-BASENDC-APP | 10.33.131.161 | Application Team | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | SPMS | ASBA | Hyper-V VM | C8SSN24 |  | NDC-ASBAAPP-N01 | NDC-BASENDC-APP | 10.32.206.132 | Application Team | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | SPMS | ASBA | Hyper-V VM | C8SSN24 |  | NDC-ASBAWEB-N01 | NDC-BASENDC-APP | 10.33.9.5 | Application Team | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 1-3 · App → DB → LPAR/VM | 2026-10-24 04:00 | 5 | SPMS | ASBA | Hyper-V VM | C8SSN24 |  | NDC-ASBAWEB-N02 | NDC-BASENDC-APP | 10.33.9.6 | Application Team | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DE8 | Power E1080 | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | 10.32.209.137 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DE8 | Power E1080 | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DE8 | Power E1080 | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DE8 | Power E1080 | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DE8 | Power E1080 | C3-9080-HEX-SN78A1DE8-CORE_DB-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | NDR HMC | Physical | 130RH6A | POwerE950/7063CR1-130RH6A | CR1130RH6A |  | 172.27.97.79 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | Database Server - NDC - ASBA n Dpsecure | Physical | C0GRN24 | Dell Poweredge R760 | DCC0GRN24 |  |  | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | DCO | Physical | C8SSN24 | Dell Poweredge R760 | NDC-BASENDC-APP |  | 10.32.216.5 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DA08X | Power E950 | ndrfccdb |  | 172.27.97.98 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Service Unit Section | SFMS | Physical | 3185702 | HMC | Not Applicable |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 4 · Physical server / frame | 2026-10-24 05:00 | 4 | Service Unit Section | SFMS | Physical | 78DA08X | FC EMX0 | Not Applicable |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) |  | Physical | 5ZWGVP3 | EMC ML3E | Not Applicable |  | 10.32.204.42 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) |  | Physical | H4XGVP3 | EMC ML3E | Not Applicable |  | 10.32.204.42 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78BB816 | TS4500 | Not Applicable |  | 10.32.202.26 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78DB196 | TS4500 | Not Applicable |  | 10.32.202.26 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78DB197 | TS4500 | Not Applicable |  | 10.32.202.26 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E3NKE2 | FLASH SYSTEM 7300 | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4Y8T | MT:2145-SV3 | SANINV378 |  | 10.32.206.18, 10.32.206.17 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4Y9C | MT:2145-SV3 | SANINV379 |  | 10.32.206.19, 10.32.206.17 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4Z1E | MT:2145-SV3 | SANINV380 |  | 10.32.206.20, 10.32.206.17 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E3NPL | FLASH SYSTEM 7300 | SANINV381 |  | 10.32.206.22, 10.32.206.23, 10.32.206.24 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4Z1B | MT:2145-SV3 | SANINV382 |  | 10.32.206.21, 10.32.206.17 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 5 · Storage / SVC / Tape | 2026-10-24 05:30 | 3 | Data Center Operations Section (ITI) |  | Physical | 6G0HVP3 | EMC ML3 | TAPEINV22 |  | 10.32.204.42 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
1 | 6 · SAN switch / director | 2026-10-24 06:00 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 755231F | SAN Director- 64G - F78 | BLR512B-G7-SW2 |  | 10.32.202.106 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
1 | 6 · SAN switch / director | 2026-10-24 06:00 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 786731M | Brocade G720 | BLRNDC_64BG7_SW1 |  | 172.27.97.114 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
1 | 6 · SAN switch / director | 2026-10-24 06:00 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 786729Z | Brocade G720 | BLRNDC_64BG7_SW2 |  | 172.27.97.115 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FG3K2D3Z16800269 | Fortigate 3200D | CAN-NDR-FORTINET-FW1 |  | 172.27.97.245/10.32.255.40 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FG3K2D3Z16800247 | Fortigate 3200D | CAN-NDR-FORTINET-FW2 |  | 172.27.97.245/10.32.255.40 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28050YP1 | C9500 -24Y4C | CB-NDR-P2P-SW |  | 10.32.255.35 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28050YP4 | C9500 -24Y4C | CB-NDR-P2P-SW |  | 10.32.255.35 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO2813130Y | N9K-C93180YC-FX3 | DC-C3-N9K-RAC-SW3 |  | 10.32.200.129 | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28130JMK | N9K-C93180YC-FX3 | DC-C3-N9K-TOR-SW1 |  | 10.32.200.125 | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28140BUK | N9K-C93180YC-FX3 | DC-C3-N9K-TOR-SW2 |  | 10.32.200.126 | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28160D18 | N9K-C93108TC-FX3P | NDR-Cisco-Nexus-SW1 |  | 172.27.97.74 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28160237 | N9K-C93108TC-FX3P | NDR-Cisco-Nexus-SW2 |  | 172.27.97.75 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO281513F3 | N9K-C93108TC-FX3 | NDR-DMZ-SW-01 |  | 10.33.200.25 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28160CZT | N9K-C93108TC-FX3 | NDR_DMZ_SW_02 |  | 10.33.200.26 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | 2161392000161 | MC220L | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | SY2511A-131200531 / SY2304-131203010 | Firbre ethernet Media converter | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
1 | 7 · Network / Security | 2026-10-24 06:30 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | CAEZ2226 | Mx104 | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | LPAR | 78A1DD8 |  | DCADAPIDDB | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.18.222 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | LPAR | 78A1DD8 |  | DCUPIARCHDB | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.52.62 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | 10KHMY3 |  | DC-TAPELES-MIG | CLUSTER1-NODE3 | 10.32.24.91 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | G3SXMZ3 |  | DCHRMAPP1.canarabank.in | DCHVCLSTRN07 |  | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | 9MJHMY3 |  | UAT-CBSPIGMYWEB | DCHYPRVBASE1 | 10.33.192.159 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | 81KHMY3 |  | UAT-INVOICE-GPU | DCHYPRVBASE2 | 10.33.133.208 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | 40KHMY3 |  | DC-UPIFIN-WEB02 | DCNCBSDMZBASE1 | 10.32.2.143 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | 40KHMY3 |  | DC-UPIFIN-WEB03 | DCNCBSDMZBASE1 | 10.33.2.148 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | D0KHMY3 |  | DC-ADRESTORE-TEST | DCNCBSINTBASE2 | 10.32.38.5 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | LPAR | 78DE93X |  | AIX73TL3SP0_V | E950-2-9040-MR9-SN78DE93X | . | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | LPAR | 78DE98X |  | DCPOWERVC01 | E950-8-9040-MR9-SN78DE98X | . | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | LPAR | 78414F8 |  | DCFRSDB19C | E980-1-9080-M9S-SN78414F8 | 172.16.38.227 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 |  |  | Hyper-V VM | BKJHMY3 |  | DC-JIOMONITOR | WIN-STLAAFKA5J2 | 10.32.66.245 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | API Banking Section | APG (Google API Gatway) | Hyper-V VM | 10KHMY3 |  | DC-UAT-API | CLUSTER1-NODE3 | 10.33.131.180 | Application Team | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | API Banking Section | APG (Google API Gatway) | Hyper-V VM | 9MJHMY3 |  | UAT-APIBKG-WEB5 | DCHYPRVBASE1 | 10.33.192.116 | Application Team | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | API Banking Section | APG (Google API Gatway) | Hyper-V VM | 9MJHMY3 |  | UAT-APIBKG-WEB6 | DCHYPRVBASE1 | 10.33.192.117 | Application Team | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | API Banking Section | APG (Google API Gatway) | Hyper-V VM | 81KHMY3 |  | UAT-APIBKG-APP6 | DCHYPRVBASE2 | 10.33.131.151 | Application Team | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | API Banking Section | APG (Google API Gatway) | Hyper-V VM | 81KHMY3 |  | UAT-APIBKG-APP7 | DCHYPRVBASE2 | 10.33.131.152 | Application Team | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-DB | CLUSTER1-NODE4 | 172.16.43.15 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-IBR | CLUSTER1-NODE4 | 172.16.43.18 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-OTP | CLUSTER1-NODE4 | 172.16.43.29 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-Reports | CLUSTER1-NODE4 | 172.16.3.87 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-Reports1 | CLUSTER1-NODE4 | 172.16.26.101 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-Reports2 | CLUSTER1-NODE4 | 172.16.42.174 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-Reports3 | CLUSTER1-NODE4 | 172.16.42.175 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | ATM Section | ATM | Hyper-V VM | 61KHMY3 |  | DC-ATM-WEB | CLUSTER1-NODE4 | 172.16.43.24 | Application Team | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7868 |  | DCCBSUAT2APP | C2-9080-HEX-SN78C7868-UAT | 10.32.7.145 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7868 |  | DCCBSUAT2DB | C2-9080-HEX-SN78C7868-UAT | 10.32.7.144 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7868 |  | DCCBSUAT3APP | C2-9080-HEX-SN78C7868-UAT | 10.32.7.149 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7868 |  | DCCBSUAT3DB | C2-9080-HEX-SN78C7868-UAT | 10.32.7.148 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7848 |  | DCCBSUAT1APP | D1-9080-HEX-SN78C7848-UAT | 10.32.7.139 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7848 |  | DCCBSUAT1DB1 | D1-9080-HEX-SN78C7848-UAT | 10.32.7.132 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7848 |  | DCCBSUATPREPRODAPP | D1-9080-HEX-SN78C7848-UAT | 10.32.7.141 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7848 |  | DCCBSUATPREPRODDB | D1-9080-HEX-SN78C7848-UAT | 10.32.7.140 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7848 |  | DCCBSUATSTGAPP | D1-9080-HEX-SN78C7848-UAT | 10.32.7.147 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78C7848 |  | DCCBSUATSTGDB | D1-9080-HEX-SN78C7848-UAT | 10.32.7.146 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE92X |  | DCLACBSHOSTPRDAP01 | E950-1-9040-MR9-SN78DE92X | 10.32.1.63 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE92X |  | DCLACBSHOSTPRDAP02 | E950-1-9040-MR9-SN78DE92X | 10.32.1.64 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE92X |  | DCLACBSHOSTPRDAP12 | E950-1-9040-MR9-SN78DE92X | 10.32.1.74 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE92X |  | DCLACBSHTTPPRDWI01 | E950-1-9040-MR9-SN78DE92X | 10.32.6.21 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE92X |  | DCLACBSOLTPPRDAP01 | E950-1-9040-MR9-SN78DE92X | 10.32.6.151 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE93X |  | DCLACBSHOSTPRDAP03 | E950-2-9040-MR9-SN78DE93X | 10.32.1.65 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE93X |  | DCLACBSHOSTPRDAP04 | E950-2-9040-MR9-SN78DE93X | 10.32.1.66 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE93X |  | DCLACBSHOSTPRDAP14 | E950-2-9040-MR9-SN78DE93X | 10.32.1.76 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE93X |  | DCLACBSHTTPPRDWI03 | E950-2-9040-MR9-SN78DE93X | 10.32.6.23 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE93X |  | DCLACBSOLTPPRDAP02 | E950-2-9040-MR9-SN78DE93X | 10.32.6.152 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE94X |  | DCLACBSHOSTPRDAP05 | E950-3-9040-MR9-SN78DE94X | 10.32.1.67 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE94X |  | DCLACBSHOSTPRDAP06 | E950-3-9040-MR9-SN78DE94X | 10.32.1.68 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE94X |  | DCLACBSHOSTPRDAP15 | E950-3-9040-MR9-SN78DE94X | 10.32.1.77 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE94X |  | DCLACBSHTTPPRDWI05 | E950-3-9040-MR9-SN78DE94X | 10.32.6.25 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE94X |  | DCLACBSOLTPPRDAP03 | E950-3-9040-MR9-SN78DE94X | 10.32.6.153 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE95X |  | DCLACBSHOSTPRDAP07 | E950-4-9040-MR9-SN78DE95X | 10.32.1.69 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE95X |  | DCLACBSHOSTPRDAP08 | E950-4-9040-MR9-SN78DE95X | 10.32.1.70 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE95X |  | DCLACBSHOSTPRDAP17 | E950-4-9040-MR9-SN78DE95X | 10.32.1.79 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE95X |  | DCLACBSHTTPPRDWI07 | E950-4-9040-MR9-SN78DE95X | 10.32.6.27 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSEXTAPIPRDAP01 | E950-5-9040-MR9-SN78DE96X | 10.32.1.83 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSHOSTPRDAP11 | E950-5-9040-MR9-SN78DE96X | 10.32.1.73 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSHOSTPRDAP13 | E950-5-9040-MR9-SN78DE96X | 10.32.1.75 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSHTTPPRDWI02 | E950-5-9040-MR9-SN78DE96X | 10.32.6.22 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSHTTPPRDWI04 | E950-5-9040-MR9-SN78DE96X | 10.32.6.24 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSHTTPPRDWI12 | E950-5-9040-MR9-SN78DE96X | 10.32.6.32 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSHTTPPRDWI13 | E950-5-9040-MR9-SN78DE96X | 10.32.6.33 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE96X |  | DCLACBSHTTPPRDWI14 | E950-5-9040-MR9-SN78DE96X | 10.32.6.34 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSEXTAPIPRDAP02 | E950-6-9040-MR9-SN78DE97X | 10.32.1.84 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSHOSTPRDAP16 | E950-6-9040-MR9-SN78DE97X | 10.32.1.78 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSHOSTPRDAP18 | E950-6-9040-MR9-SN78DE97X | 10.32.1.80 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSHTTPPRDWI06 | E950-6-9040-MR9-SN78DE97X | 10.32.6.26 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSHTTPPRDWI08 | E950-6-9040-MR9-SN78DE97X | 10.32.6.28 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSHTTPPRDWI15 | E950-6-9040-MR9-SN78DE97X | 10.32.6.35 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSHTTPPRDWI16 | E950-6-9040-MR9-SN78DE97X | 10.32.6.36 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSHTTPPRDWI17 | E950-6-9040-MR9-SN78DE97X | 10.32.6.37 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE97X |  | DCLACBSOLTPPRDAP04 | E950-6-9040-MR9-SN78DE97X | 10.32.6.154 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE9AX |  | DCLACBSHOSTPRDAP09 | E950-7-9040-MR9-SN78DE9AX | 10.32.1.71 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE9AX |  | DCLACBSHOSTPRDAP10 | E950-7-9040-MR9-SN78DE9AX | 10.32.1.72 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE9AX |  | DCLACBSHTTPPRDWI09 | E950-7-9040-MR9-SN78DE9AX | 10.32.6.29 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE9AX |  | DCLACBSHTTPPRDWI10 | E950-7-9040-MR9-SN78DE9AX | 10.32.6.30 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE9AX |  | DCLACBSHTTPPRDWI11 | E950-7-9040-MR9-SN78DE9AX | 10.32.6.31 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE9AX |  | DCLACBSHTTPPRDWI18 | E950-7-9040-MR9-SN78DE9AX | 10.32.6.38 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE9AX |  | DCLACBSOLTPPRDAP05 | E950-7-9040-MR9-SN78DE9AX | 10.32.6.155 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE98X |  | DCLACBSHOSTUATAP01 | E950-8-9040-MR9-SN78DE98X | 10.32.8.11 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE98X |  | DCLACBSOLTPPRDAP06 | E950-8-9040-MR9-SN78DE98X | 10.32.6.156 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE98X |  | DCLACBSREPPRDAP01 | E950-8-9040-MR9-SN78DE98X | 10.33.129.11 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE99X |  | DCLACBSHOSTUATAP02 | E950-9-9040-MR9-SN78DE99X | 10.33.129.12 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78DE99X |  | DCLACBSREPPRDAP02 | E950-9-9040-MR9-SN78DE99X | 10.32.8.12 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 78415A8 |  | UTKHCOREPFUATDB | E980-2-9080-M9S-SN78415A8 | 172.16.255.45 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 783BFE8 |  | DCCBSUATAP03 | Server1-9080-M9S-SN783BFE8 | 10.33.129.14 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 783BFE8 |  | DCCBSUATDB03 | Server1-9080-M9S-SN783BFE8 | 10.33.129.79 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CBS(UTKARSH) | CBS(UTKARSH) | LPAR | 783BFE8 |  | FCCPTVU | Server1-9080-M9S-SN783BFE8 | 172.16.36.110 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | CTS | DEM | Hyper-V VM | 61KHMY3 |  | DC-CTSDEM-APP3 | CLUSTER1-NODE4 | 10.33.133.191 | Application Team | Shakti Narayan Gupta,Bhupesh Piplani,7975142177/9650976622,hoditcts@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | 40KHMY3 |  | DCCCMSWEB2 | DCNCBSDMZBASE1 | 10.33.1.66 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | C0KHMY3 |  | DCCCMSWEB1 | DCNCBSDMZBASE2 | 10.33.1.64 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373/9880283138 ¦ hoccmssection@canarabank.com/hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | C0KHMY3 |  | DCCMSUATWEB1 | DCNCBSDMZBASE2 | 10.33.192.109 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | CKJHMY3 |  | DCCCMSAPPBACK1 | DCNCBSINTBASE1 | 10.32.38.36 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | CKJHMY3 |  | DCCCMSAPPFRONT1 | DCNCBSINTBASE1 | 10.32.38.38 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | CKJHMY3 |  | DCCCMSBATCHAPP3 | DCNCBSINTBASE1 | 10.32.38.45 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | CKJHMY3 |  | DCCCMSREDISCACHE1 | DCNCBSINTBASE1 | 10.32.38.40 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | CKJHMY3 |  | DCCCMSREDISCACHE2 | DCNCBSINTBASE1 | 10.32.38.41 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | D0KHMY3 |  | DCCCMSAPPBACK2 | DCNCBSINTBASE2 | 10.32.38.37 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | D0KHMY3 |  | DCCCMSAPPFRONT2 | DCNCBSINTBASE2 | 10.32.38.39 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | D0KHMY3 |  | DCCCMSBATCHAPP1 | DCNCBSINTBASE2 | 10.32.38.43 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | D0KHMY3 |  | DCCCMSBATCHAPP2 | DCNCBSINTBASE2 | 10.32.38.44 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Hyper-V VM | D0KHMY3 |  | DCCCMSREDISCACHE3 | DCNCBSINTBASE2 | 10.32.38.42 | Application Team | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Compliance Department | Compliance Kartavya | Hyper-V VM | B1KHMY3 |  | DC-COMP-DB | CLUSTER1-NODE1 | 10.32.52.6 | Application Team |  | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Compliance Department | Compliance Kartavya | Hyper-V VM | B1KHMY3 |  | UAT-COMP-DB | CLUSTER1-NODE1 | 10.33.132.21 | Application Team |  | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Compliance Department section | Compliance Kartavya | Hyper-V VM | B1KHMY3 |  | DC-COMP-APP | CLUSTER1-NODE1 | 10.32.51.14 | Application Team | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Compliance Department section | Compliance Kartavya | Hyper-V VM | B1KHMY3 |  | UAT-COMP-APP | CLUSTER1-NODE1 | 10.33.131.159 | Application Team | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | DPSecure | Dpsecure | Hyper-V VM | 90KHMY3 |  | DC-CMS-DB | WIN-4JIKE60P6JV | 10.32.52.94 | Application Team | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | DPSecure | Dpsecure | Hyper-V VM | 90KHMY3 |  | UAT-CDSL-DB | WIN-4JIKE60P6JV | 10.33.132.121 | Application Team | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78A1DD8 |  | DCLACBS3GLPRODDB01 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.2.41,10.32.2.42,10.32.2.44,10.32.33.103,10.32.33.102 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78A1DC8 |  | DCP10CBSPRDDB01 | A2-9080-HEX-SN78A1DC8-CORE_DB-1 | 10.32.2.66 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78C7868 |  | DCARCHDB2 | C2-9080-HEX-SN78C7868-UAT | 10.32.2.39,10.32.2.37,10.32.33.12 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78A1DF8 |  | DCFLASH3 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.2.46 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78A1DF8 |  | DCLACBS3GLPRODDB02 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.2.43 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | AI Alertlog | Hyper-V VM | B1KHMY3 |  | DC-GAURDAI-01 | CLUSTER1-NODE1 | 172.16.38.77 | Application Team | Sangeetha ¦ sangeetha_r@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | AI Alertlog | Hyper-V VM | B1KHMY3 |  | DC-GAURDAI-02 | CLUSTER1-NODE1 | 172.16.38.75 | Application Team | Sangeetha ¦ sangeetha_r@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) |  | Hyper-V VM | 61KHMY3 |  | DC-CANDI-APP2 | CLUSTER1-NODE4 | 10.32.11.247 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78C7848 |  | DCARCHDB1 | D1-9080-HEX-SN78C7848-UAT | 10.32.2.38,10.32.2.36,10.32.33.11 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | Treasuary Dashboard | Hyper-V VM | CKJHMY3 |  | DC-CANDASH-UAT | DCNCBSINTBASE1 | 10.32.11.198 | Application Team | Debjoy - 9874753518 ¦ debjoyroy@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | CBS NFS Server 1 | LPAR | 78DE98X |  | DCLACBNFSSERVER01 | E950-8-9040-MR9-SN78DE98X | 10.32.1.32 | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78DE98X |  | DCLACBSCOREUATDB05 | E950-8-9040-MR9-SN78DE98X | 10.33.129.73 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78DE98X |  | DCLACBSFLASHAP-NewLpar | E950-8-9040-MR9-SN78DE98X | 10.32.1.87 | Application Team | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78DE98X |  | DCLACBSFLASHAP01 | E950-8-9040-MR9-SN78DE98X | 10.32.1.85 | Application Team | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | CBS UAT | LPAR | 78DE98X |  | DCLACBSOLTPUATAP01 | E950-8-9040-MR9-SN78DE98X | 10.33.129.201 | Application Team | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78DE98X |  | DCLACBSREPUATAP01 | E950-8-9040-MR9-SN78DE98X | 10.33.130.71 | Application Team | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | NFS | LPAR | 78DE99X |  | DCLACBNFSSERVER02 | E950-9-9040-MR9-SN78DE99X | 10.32.1.33 | Application Team | anil.biswal@kyndryl.com ¦ anil.biswal@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78DE99X |  | DCLACBSCOREUATDB06 | E950-9-9040-MR9-SN78DE99X | 10.33.129.78 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78DE99X |  | DCLACBSFLASHAP02 | E950-9-9040-MR9-SN78DE99X | 10.33.129.13 | Application Team | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | NIM | LPAR | 78414F8 |  | DCAIX72NIM | E980-1-9080-M9S-SN78414F8 | 172.16.38.34 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCDEVFCAPP | E980-1-9080-M9S-SN78414F8 | 172.16.255.37 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCESBFCDB01 | E980-1-9080-M9S-SN78414F8 | 172.16.255.73 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCFCRARCHFO | E980-1-9080-M9S-SN78414F8 | 172.16.38.140 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCFCRDBFO | E980-1-9080-M9S-SN78414F8 | 172.16.38.212 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCINTDB | E980-1-9080-M9S-SN78414F8 | 172.16.2.132 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCMIGFCAPP1 | E980-1-9080-M9S-SN78414F8 | 172.16.255.41 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCMIGFCDB01 | E980-1-9080-M9S-SN78414F8 | 172.16.255.75 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCNEFTARCH | E980-1-9080-M9S-SN78414F8 | 10.32.52.65 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCNONCBSARCH | E980-1-9080-M9S-SN78414F8 | 10.32.52.66 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | GBM flash | LPAR | 78414F8 |  | DCNONCBSFLASH | E980-1-9080-M9S-SN78414F8 | 172.16.38.251 | Application Team | Sangeetha ¦ sangeetha_r@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCREP01 | E980-1-9080-M9S-SN78414F8 | 172.16.255.46 | Application Team | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCSHADOW5 | E980-1-9080-M9S-SN78414F8 | 172.16.38.4 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DCSITRACDB1 | E980-1-9080-M9S-SN78414F8 | 172.16.255.81 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | FCR Retail | LPAR | 78414F8 |  | DCUATFCAPP1 | E980-1-9080-M9S-SN78414F8 | 172.16.255.40 | Application Team | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | DC_TSM_DB | E980-1-9080-M9S-SN78414F8 | 172.16.38.96 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78414F8 |  | UATTESTLPAR73 | E980-1-9080-M9S-SN78414F8 | 172.16.255.80 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | NIM | LPAR | 78414F8 |  | nim | E980-1-9080-M9S-SN78414F8 | 172.16.255.93 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | CBSUATM1 | E980-2-9080-M9S-SN78415A8 | 172.16.36.118 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | CBSUATM3 | E980-2-9080-M9S-SN78415A8 | 172.16.36.117 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DCMIGFCAPP2 | E980-2-9080-M9S-SN78415A8 | 172.16.255.42 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DCPGRSDBFO | E980-2-9080-M9S-SN78415A8 | 172.16.3.81 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DCPOWERSC02 | E980-2-9080-M9S-SN78415A8 | 10.32.14.37 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DCPOWERSCGUI | E980-2-9080-M9S-SN78415A8 | 10.32.14.38 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DCSITESB | E980-2-9080-M9S-SN78415A8 | 172.16.255.47 | Application Team | Sunil Kashikar ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DCSITRACDB2 | E980-2-9080-M9S-SN78415A8 | 172.16.255.82 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DCUATFCDB1 | E980-2-9080-M9S-SN78415A8 | 172.16.255.74 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DC_SHADOW2_DB | E980-2-9080-M9S-SN78415A8 | 172.16.38.76 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DC_Shadow4 | E980-2-9080-M9S-SN78415A8 | 172.16.38.142 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | DC_TSM_DB_FO | E980-2-9080-M9S-SN78415A8 | 172.16.38.217 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | MBDBUAT | E980-2-9080-M9S-SN78415A8 | 172.16.36.119 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | NIM | LPAR | 78415A8 |  | UATNIMSERVER | E980-2-9080-M9S-SN78415A8 | 172.16.36.80 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 78415A8 |  | UATTESTLPAR72 | E980-2-9080-M9S-SN78415A8 | 172.16.36.81 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 783BFE8 |  | DCPOWERSC01 | Server1-9080-M9S-SN783BFE8 | 10.32.14.36 | Application Team | Anil - Kyndryl ¦ anil.biswal@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 783BFE8 |  | DC_SHADOW3 | Server1-9080-M9S-SN783BFE8 | 172.16.38.83 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 783BFC8 |  | DCFCRARCH | Server2-9080-M9S-SN783BFC8 | 172.16.38.80,172.16.38.144 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 783BFC8 |  | DCPGRSDB | Server2-9080-M9S-SN783BFC8 | 172.16.3.77 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | LPAR | 783BFC8 |  | DCSITMIGFCAPP1 | Server2-9080-M9S-SN783BFC8 | 172.16.255.44 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | DCO | Hyper-V VM | 90KHMY3 |  | DC-KYNDRYL-SFTP | WIN-4JIKE60P6JV | 10.33.131.38 | Application Team | Mansoor Hussain - Kyndryl ¦ Mansoor.Hussain@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Center Operations Section (ITI) | SANNAV Tool | Hyper-V VM | 90KHMY3 |  | DC-SANnav | WIN-4JIKE60P6JV | 10.32.202.60 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Data Warehouse Section | Data Warehouse | LPAR | 783BFC8 |  | DCFCRARCH | Server2-9080-M9S-SN783BFC8 | 172.16.38.144 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | B0KHMY3 |  | DC-LAPS-CONNWEB1 | DCHVCLSTRN02 | 10.33.1.160 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | B0KHMY3 |  | DC-LAPS-CONNWEB2 | DCHVCLSTRN02 | 10.33.1.161 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | B0KHMY3 |  | DC-LAPS-LENDWEB1 | DCHVCLSTRN02 | 10.33.1.162 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | B0KHMY3 |  | DC-LAPS-LENDWEB2 | DCHVCLSTRN02 | 10.33.1.163 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | 40KHMY3 |  | DC-UATLAPSEXT-WEB2 | DCNCBSDMZBASE1 | 10.33.192.24 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | C0KHMY3 |  | DC-UATLAPSEXT-WEB1 | DCNCBSDMZBASE2 | 10.33.192.23 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | GST SAHAY | Hyper-V VM | D0KHMY3 |  | DC-GSTSAHY-APP1 | DCNCBSINTBASE2 | 10.32.11.191 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | GST SAHAY | Hyper-V VM | D0KHMY3 |  | DC-GSTSAHY-APP2 | DCNCBSINTBASE2 | 10.32.11.192 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFE8 |  | DCLAPSWEB6 | Server1-9080-M9S-SN783BFE8 | 10.32.13.35 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFE8 |  | LAPSAPP1 | Server1-9080-M9S-SN783BFE8 | 10.32.11.59 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFE8 |  | LAPSCONNP1 | Server1-9080-M9S-SN783BFE8 | 10.32.11.61 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFE8 |  | LAPSWEB1 | Server1-9080-M9S-SN783BFE8 | 10.33.1.39 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFC8 |  | DCLAPSWEB3 | Server2-9080-M9S-SN783BFC8 | 10.32.13.31 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFC8 |  | DCLAPSWEB5 | Server2-9080-M9S-SN783BFC8 | 10.32.13.113 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFC8 |  | LAPSAPP2 | Server2-9080-M9S-SN783BFC8 | 10.32.11.60 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFC8 |  | LAPSCONNP2 | Server2-9080-M9S-SN783BFC8 | 10.32.11.62 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFC8 |  | LAPSWEB2 | Server2-9080-M9S-SN783BFC8 | 10.32.13.11 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | LAPS | LPAR | 783BFC8 |  | LAPSWEB4 | Server2-9080-M9S-SN783BFC8 | 10.32.13.7 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | BKJHMY3 |  | DC-UATLAPS-APP1 | WIN-STLAAFKA5J2 | 10.33.131.170 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | BKJHMY3 |  | DC-UATLAPS-APP2 | WIN-STLAAFKA5J2 | 10.33.131.171 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Digital Lending and LAPS Section | CORPORATE LOAN MODULE | Hyper-V VM | BKJHMY3 |  | DC-UATLAPSINTER-WEB | WIN-STLAAFKA5J2 | 10.33.133.30 | Application Team | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 8KJHMY3 |  | DCIRMSAPIO1 | DCIRMSBASE1 | 10.32.35.134 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 8KJHMY3 |  | DCIRMSMETA02.aranac.com | DCIRMSBASE1 | 10.32.35.154 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 8KJHMY3 |  | DCIRMSVAAR04.aranac.com | DCIRMSBASE1 | 10.32.35.165 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 8KJHMY3 |  | DCIRMSVAAR08.aranac.com | DCIRMSBASE1 | 10.32.35.164 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 8KJHMY3 |  | DCIRMSWEB01.aranac.com | DCIRMSBASE1 | 10.32.13.65 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 8MJHMY3 |  | DCIRMSMID02.aranac.com | DCIRMSBASE10 | 10.32.35.139 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 8MJHMY3 |  | DCIRMSVAAR11.aranac.com | DCIRMSBASE10 | 10.32.35.172 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 70KHMY3 |  | DCIRMSCOMP02 | DCIRMSBASE11 | 10.32.35.158 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 70KHMY3 |  | DCIRMSVA06.aranac.com | DCIRMSBASE11 | 10.32.35.180 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 7MJHMY3 |  | DCIRMSAPI02 | DCIRMSBASE2 | 10.32.35.135 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 7MJHMY3 |  | DCIRMSMETA03.aranac.com | DCIRMSBASE2 | 10.32.35.155 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 7MJHMY3 |  | DCIRMSVAAR02.aranac.com | DCIRMSBASE2 | 10.32.35.162 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 7MJHMY3 |  | DCIRMSVAAR03.aranac.com | DCIRMSBASE2 | 10.32.35.163 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 7MJHMY3 |  | DCIRMSWEB02.aranac.com | DCIRMSBASE2 | 10.32.13.66 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | HZJHMY3 |  | DCIRMSMID01.aranac.com | DCIRMSBASE3 | 10.32.35.138 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | HZJHMY3 |  | DCIRMSVAAR05.aranac.com | DCIRMSBASE3 | 10.32.35.166 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 50KHMY3 |  | DCIRMSVA01.aranac.com | DCIRMSBASE4 | 10.32.35.175 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 50KHMY3 |  | DCIRMSVAAR06.aranac.com | DCIRMSBASE4 | 10.32.35.167 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 30KHMY3 |  | DCIRMSCOMP01.aranac.com | DCIRMSBASE5 | 10.32.35.159 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 30KHMY3 |  | DCIRMSMETA01.aranac.com | DCIRMSBASE5 | 10.32.35.152 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 74LHMY3 |  | DCIRMSVA02.aranac.com | DCIRMSBASE6 | 10.32.35.176 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 74LHMY3 |  | DCIRMSVAAR07.aranac.com | DCIRMSBASE6 | 10.32.35.168 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | DKJHMY3 |  | DCIRMSVA03.aranac.com | DCIRMSBASE7 | 10.32.35.177 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | DKJHMY3 |  | DCIRMSVAAR01.aranac.com | DCIRMSBASE7 | 10.32.35.169 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 91KHMY3 |  | DCIRMSVA04.aranac.com | DCIRMSBASE8 | 10.32.35.178 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 91KHMY3 |  | DCIRMSVAAR09.aranac.com | DCIRMSBASE8 | 10.32.35.170 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | G0KHMY3 |  | DCIRMSVA05.aranac.com | DCIRMSBASE9 | 10.32.35.179 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | G0KHMY3 |  | DCIRMSVAAR10.aranac.com | DCIRMSBASE9 | 10.32.35.171 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 7V1N0V3 |  | UATAPP-SASCOMPUTE.aranac.com | EWIRMUATAPPBASE | 10.33.134.68 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | EWIRM Section | IRMS | Hyper-V VM | 7V1N0V3 |  | UATAPP-SASMIP.aranac.com | EWIRMUATAPPBASE | 10.33.134.69 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCC Section | FSCM | LPAR | 78414F8 |  | DCFCCFO | E980-1-9080-M9S-SN78414F8 | 172.16.38.47 | Application Team | Manoj Kumar T ¦ 9300331307 ¦ manojkumart@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCR Deposits Section | CKYC | Hyper-V VM | 81KHMY3 |  | DC-UAT-CKYCAPP | DCHYPRVBASE2 | 10.33.131.157 | Application Team | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCR Deposits Section | CKYC | Hyper-V VM | 81KHMY3 |  | DC-UAT-CKYCIMG | DCHYPRVBASE2 | 10.33.131.158 | Application Team | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78A1DD8 |  | DCFCUBSPRDDB01 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.27.68 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78A1DD8 |  | DCFCUBSPRDDB01 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.27.72 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78414F8 |  | DCFCUBSPRDAP02 | E980-1-9080-M9S-SN78414F8 | 10.32.27.38 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78414F8 |  | DCINTREP1 | E980-1-9080-M9S-SN78414F8 | 172.16.1.16 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | DCFCUBSPRDAP01 | E980-2-9080-M9S-SN78415A8 | 10.32.27.37 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com / PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | DCFCUBSPRDDB02 | E980-2-9080-M9S-SN78415A8 | 10.32.27.69 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | DEVFCUBSAPP | E980-2-9080-M9S-SN78415A8 | 10.33.130.132 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | DEVFUBSDB | E980-2-9080-M9S-SN78415A8 | 10.33.130.133 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | MIGFCUBSAPP | E980-2-9080-M9S-SN78415A8 | 10.33.130.139 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | MIGFCUBSDB2 | E980-2-9080-M9S-SN78415A8 | 10.33.130.138 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | UATFCUBSAPP | E980-2-9080-M9S-SN78415A8 | 10.33.130.134 | Application Team | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 78415A8 |  | UATFCUBSDB | E980-2-9080-M9S-SN78415A8 | 10.33.130.135 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 783BFE8 |  | DCAMLDBFO | Server1-9080-M9S-SN783BFE8 | 172.16.38.24 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 783BFE8 |  | DCFCCDB | Server1-9080-M9S-SN783BFE8 | 172.16.38.43 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | LPAR | 783BFC8 |  | DCAMLDB | Server2-9080-M9S-SN783BFC8 | 172.16.38.225 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | FCUBS | FCUBS | Hyper-V VM | 90KHMY3 |  | DC-TNZDB | WIN-4JIKE60P6JV | 10.32.52.67 | Application Team | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Hyper-V VM | C0KHMY3 |  | CBDCUAT1-DTSP-WEB1 | DCNCBSDMZBASE2 | 10.33.193.91 | Application Team | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Hyper-V VM | C0KHMY3 |  | CBDCUAT1-DTSP-WEB2 | DCNCBSDMZBASE2 | 10.33.193.92 | Application Team | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Hyper-V VM | C0KHMY3 |  | CBDCUAT1-RTSP-WEB1 | DCNCBSDMZBASE2 | 10.33.193.89 | Application Team | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Hyper-V VM | C0KHMY3 |  | CBDCUAT1-RTSP-WEB2 | DCNCBSDMZBASE2 | 10.33.193.90 | Application Team | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | LPAR | 78A1DD8 |  | DCGBMPMVIDN1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.52.38 | Application Team | DBA Team | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | LPAR | 78A1DF8 |  | DCGBMPMVIDN2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.52.39 | Application Team | DBA Team | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | FI | Hyper-V VM | 9MJHMY3 |  | UAT-FIG | DCHYPRVBASE1 | 10.33.1.65 | Application Team | Kiran B R ¦ 7619453224 ¦ figsupport@canarabank.com & kiranbr@integramicro.co.in & hoditfimb@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | DC Aadhar Vault DB | LPAR | 78414F8 |  | DCAADHARVAULTDB2 | E980-1-9080-M9S-SN78414F8 | 10.32.27.198 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | DB server | LPAR | 78415A8 |  | DCAADHARVAULTDB1 | E980-2-9080-M9S-SN78415A8 | 10.32.27.197 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | EKYC | LPAR | 78415A8 |  | DCLADB2EKYCPRD | E980-2-9080-M9S-SN78415A8 | 172.16.11.135 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | TAB | LPAR | 78415A8 |  | DCLADB2TABBPRD | E980-2-9080-M9S-SN78415A8 | 172.16.11.138 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | DB | LPAR | 78415A8 |  | amldbuat | E980-2-9080-M9S-SN78415A8 | 172.16.36.84 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | CEDGE | LPAR | 783BFE8 |  | DCLADB1GBMNPRD | Server1-9080-M9S-SN783BFE8 | 172.16.11.148 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Government Business and Financial Inclusion Section | CEDGE | LPAR | 783BFC8 |  | DCLADB2GBMNPRD | Server2-9080-M9S-SN783BFC8 | 172.16.11.133 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DC-HRMES2.aranac.com | DCHVCLSTRN08 | 10.32.45.12 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DC-HRMFILE1.aranac.com | DCHVCLSTRN08 | 10.32.45.68 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DC-HRMWEB1.aranac.com | DCHVCLSTRN08 | 10.32.45.36 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DC-HRMWEB2.aranac.com | DCHVCLSTRN08 | 10.32.45.37 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DC-HRMWEB3.aranac.com | DCHVCLSTRN08 | 10.32.45.38 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DCHRMAPP2.canarabank.in | DCHVCLSTRN08 | 10.32.45.5 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DCHRMAPP3.canarabank.in | DCHVCLSTRN08 | 10.32.45.6 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | H3SXMZ3 |  | DCHRMAPP4.canarabank.in | DCHVCLSTRN08 | 10.32.45.7 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | 83SXMZ3 |  | DC-HRMES1.aranac.com | DCHVCLSTRN09 | 10.32.45.11 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | 83SXMZ3 |  | DC-HRMFILE2.aranac.com | DCHVCLSTRN09 | 10.32.45.69 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | 83SXMZ3 |  | DC-HRMWEB4.aranac.com | DCHVCLSTRN09 | 10.32.45.39 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | 83SXMZ3 |  | DC-HRMWEB5.aranac.com | DCHVCLSTRN09 | 10.32.45.40 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | 83SXMZ3 |  | DCHRMAPP5.canarabank.in | DCHVCLSTRN09 | 10.32.45.8 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | 83SXMZ3 |  | DCHRMAPP6.canarabank.in | DCHVCLSTRN09 | 10.32.45.9 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | HRMS Technical Section | PeopleSoft HRMS | Hyper-V VM | 83SXMZ3 |  | DCHRMAPP7.canarabank.in | DCHVCLSTRN09 | 10.32.45.10 | Application Team | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE92X |  | DCLACBSESBPRDAP01 | E950-1-9040-MR9-SN78DE92X | 10.32.7.21 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE93X |  | DCLACBSESBPRDAP02 | E950-2-9040-MR9-SN78DE93X | 10.32.7.22 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE94X |  | DCLACBSESBPRDAP03 | E950-3-9040-MR9-SN78DE94X | 10.32.7.23 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE95X |  | DCLACBSACEPRDAP01 | E950-4-9040-MR9-SN78DE95X | 10.32.7.29,10.32.7.25 | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE95X |  | DCLACBSACEPRDAP03 | E950-4-9040-MR9-SN78DE95X | 10.32.7.33, 10.32.7.27 | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE95X |  | DCLACBSESBPRDAP04 | E950-4-9040-MR9-SN78DE95X | 10.32.7.24 | Application Team | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE9AX |  | DCLACBSACEPRDAP02 | E950-7-9040-MR9-SN78DE9AX | 10.32.7.30,10.32.7.26 | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | IIB(DCA) | IIB/ACE/ESB | LPAR | 78DE9AX |  | DCLACBSACEPRDAP04 | E950-7-9040-MR9-SN78DE9AX | 10.32.7.34, 10.32.7.28 | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | New Initiatives-Technology Innovation Section |  | Hyper-V VM | CKJHMY3 |  | DC-Vanghee-APP1 | DCNCBSINTBASE1 | 10.32.11.248 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | MOBILE BANKING | Hyper-V VM | B1KHMY3 |  | PUSH-NOTIFICATION-SERVER | CLUSTER1-NODE1 | 10.32.18.52 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | MOBILE BANKING | Hyper-V VM | 10KHMY3 |  | DC-IRCTC-BETA | CLUSTER1-NODE3 | 10.32.18.53 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | IMPS | Hyper-V VM | 9MJHMY3 |  | DC-IMPS-WEB1 | DCHYPRVBASE1 | 10.33.192.80 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | MOBILE BANKING | Hyper-V VM | 9MJHMY3 |  | UAT-MOBILE-WEB01 | DCHYPRVBASE1 | 10.33.192.120 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | IMPS | Hyper-V VM | 81KHMY3 |  | DC-IMPS-APP1 | DCHYPRVBASE2 | 10.33.131.168 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | UPI | LPAR | 78414F8 |  | DCLAPSPRODDB1 | E980-1-9080-M9S-SN78414F8 | 10.32.52.3 | Application Team | NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | UPI | LPAR | 78415A8 |  | DCLAPSPRODDB2 | E980-2-9080-M9S-SN78415A8 | 10.32.52.4 | Application Team | NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | MB | LPAR | 78415A8 |  | OBUATDB | E980-2-9080-M9S-SN78415A8 | 172.16.36.76 | Application Team | Arjun ¦ 9952404855 ¦ hotomb@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | MOBILE BANKING | LPAR | 783BFE8 |  | DCMBRACDB1 | Server1-9080-M9S-SN783BFE8 | 10.32.12.96 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking | MOBILE BANKING | LPAR | 783BFC8 |  | DCMBRACDB2 | Server2-9080-M9S-SN783BFC8 | 10.32.12.98 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking Section |  | Hyper-V VM | D0KHMY3 |  | UATONDCAPP01 | DCNCBSINTBASE2 | 10.33.131.111 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | Hyper-V VM | 40KHMY3 |  | DC-UPI-WEB10 | DCNCBSDMZBASE1 | 10.33.2.155 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | Hyper-V VM | C0KHMY3 |  | uat-capx-web2 | DCNCBSDMZBASE2 | 172.16.14.140 | Application Team | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXAPP1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.18.133 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXAPP3 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.18.135 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXAPP5 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.18.137 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXDB1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.18.199 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBT NET Banking Section - Report Server | LPAR | 78A1DD8 |  | DCOBDXREP1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.18.139 | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXWEB1 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.33.1.44 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXWEB3 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.33.1.46 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXWEB5 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.33.1.60 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DD8 |  | DCOBDXWEB7 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.13.14 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DF8 |  | DCOBDXAPP2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.18.134 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DF8 |  | DCOBDXAPP4 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.18.136 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DF8 |  | DCOBDXAPP6 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.18.138 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBT NET Banking Section - Report Server | LPAR | 78A1DF8 |  | DCOBDXREP2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.18.140 | Application Team |  | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DF8 |  | DCOBDXWEB2 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.33.1.45 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DF8 |  | DCOBDXWEB4 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.33.1.47 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DF8 |  | DCOBDXWEB6 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.33.1.61 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 78A1DF8 |  | DCOBDXWEB8 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.13.15 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBT NET Banking Server - Jenkins Server | Hyper-V VM | 10KHMY3 |  | DC-UAT-OBDX | CLUSTER1-NODE3 | 10.32.41.8 | Application Team | RAGHURAM ¦ 8908226867 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBT NET Banking Server - Jenkins Server | Hyper-V VM | 61KHMY3 |  | DC-PROD-APP-OBDX | CLUSTER1-NODE4 | 10.32.41.9 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | PKI | Hyper-V VM | 40KHMY3 |  | DCPKIWEB01 | DCNCBSDMZBASE1 | 10.33.1.58 | Application Team | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | PKI | Hyper-V VM | CKJHMY3 |  | DCPKIAPP01 | DCNCBSINTBASE1 | 10.32.11.241 | Application Team | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | GIFTCITY OBDX | LPAR | 78415A8 |  | UATGIFTOBDXAPP | E980-2-9080-M9S-SN78415A8 | 10.33.130.137 | Application Team | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | GIFTCITY OBDX | LPAR | 78415A8 |  | UATGIFTOBDXDB | E980-2-9080-M9S-SN78415A8 | 10.33.130.136 | Application Team | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | GIFTCITY OBDX | LPAR | 78415A8 |  | UATGIFTOBDXWEB | E980-2-9080-M9S-SN78415A8 | 10.33.192.87 | Application Team | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | GIFTCITY OBDX | LPAR | 783BFE8 |  | DCGIFTOBDXAPP | Server1-9080-M9S-SN783BFE8 | 10.32.27.39 | Application Team | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | GIFTCITY OBDX | LPAR | 783BFE8 |  | DCGIFTOBDXDB | Server1-9080-M9S-SN783BFE8 | 10.32.27.73,10.32.27.75 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | GIFTCITY OBDX | LPAR | 783BFE8 |  | DCGIFTOBDXWEB | Server1-9080-M9S-SN783BFE8 | 10.33.1.97 | Application Team | VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology Net banking Section | OBDX | LPAR | 783BFC8 |  | DCOBDXDB2 | Server2-9080-M9S-SN783BFC8 | 10.32.18.198 | Application Team | RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology UPI and INFRA Section | UPI DB | LPAR | 78A1DD8 |  | DCUPIDB02 | A1-9080-HEX-SN78A1DD8-MIG-1 | 10.32.12.105 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Online Banking Technology UPI and INFRA Section | UPI DB | LPAR | 78A1DF8 |  | DCUPIDB01 | C4-9080-HEX-SN78A1DF8-MIG-2 | 10.32.12.103 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | CRM | Hyper-V VM | B1KHMY3 |  | DC-CRMENCRYPT-APP1 | CLUSTER1-NODE1 | 10.32.51.15 | Application Team | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | Portal | Hyper-V VM | 10KHMY3 |  | Circular-Module-App | CLUSTER1-NODE3 | 10.32.13.87 | Application Team | Gururaj Pamidi ¦ 9535105108 ¦ gururajnaidu.pamidi@kyndryl.com /Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | Portal | Hyper-V VM | 10KHMY3 |  | Circular-Module-Web | CLUSTER1-NODE3 | 10.32.13.88 | Application Team | Gururaj Pamidi ¦ 9535105108 ¦ gururajnaidu.pamidi@kyndryl.com /Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | CRM | Hyper-V VM | 61KHMY3 |  | DC-CRMENCRYPT-APP2 | CLUSTER1-NODE4 | 10.32.51.16 | Application Team | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | CRM | Hyper-V VM | 9MJHMY3 |  | DC-UAT-CRM-WEB1 | DCHYPRVBASE1 | 10.33.192.59 | Application Team | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | CRM | Hyper-V VM | 9MJHMY3 |  | UAT-CRM-WEB | DCHYPRVBASE1 | 10.33.192.115 | Application Team | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | DOCUMENT MANAGEMENT SYSTEM | Hyper-V VM | 9MJHMY3 |  | UAT-DMS-OFFICENOTE | DCHYPRVBASE1 | 10.33.192.26 | Application Team | Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | Queue Management System | Hyper-V VM | 9MJHMY3 |  | UAT-QMS-WEB | DCHYPRVBASE1 | 10.33.192.63 | Application Team | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | SPMS | Hyper-V VM | 40KHMY3 |  | DC-BRDPAC-WEB01 | DCNCBSDMZBASE1 | 10.33.1.140 | Application Team | Sudheer Kumar K ¦ 7095444823 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | CRM | Hyper-V VM | 40KHMY3 |  | DC-CRMENCRYPT-WEB1 | DCNCBSDMZBASE1 | 10.33.1.155 | Application Team | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | CRM | Hyper-V VM | C0KHMY3 |  | DC-CRMENCRYPT-WEB2 | DCNCBSDMZBASE2 | 10.33.1.156 | Application Team | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | Queue Management System | Hyper-V VM | C0KHMY3 |  | DC-QMS-WEB | DCNCBSDMZBASE2 | 10.33.1.184 | Application Team | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | Queue Management System | Hyper-V VM | C0KHMY3 |  | DCNCBSQMSAPP2 | DCNCBSDMZBASE2 | 10.32.11.92 | Application Team | Saket/Ananda Dharshinee | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | SPMS | Hyper-V VM | CKJHMY3 |  | DC-BRDPAC-APP01 | DCNCBSINTBASE1 | 10.32.11.97 | Application Team | Sudheer Kumar K ¦ 7095444823 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | SPMS | Hyper-V VM | CKJHMY3 |  | DC-BRDPAC-DB01 | DCNCBSINTBASE1 | 10.32.12.43 | Application Team | Sudheer Kumar K ¦ 7095444823 ¦ sudheerkumar.k@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | Queue Management System | Hyper-V VM | CKJHMY3 |  | DC-QMS-APP1 | DCNCBSINTBASE1 | 10.32.11.93 | Application Team | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | Queue Management System | Hyper-V VM | CKJHMY3 |  | DC-QMS-DB1 | DCNCBSINTBASE1 | 10.32.12.113 | Application Team | Sudheer Kumar K/Ananda Dharshinee M S ¦ 7095444823 , 8610940083 ¦ sudheerkumar.k@canarabank.com/anandadharshinee@canarabank.com | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | SPMS | CRM | Hyper-V VM | 90KHMY3 |  | DC-Tableau-Server | WIN-4JIKE60P6JV | 10.32.51.8 | Application Team | K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Service Unit Section |  | Hyper-V VM | 61KHMY3 |  | DC-NACH-APP | CLUSTER1-NODE4 | 172.16.44.78 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | B1KHMY3 |  | DC-UIPATH-DB1 | CLUSTER1-NODE1 | 10.32.38.229 | Application Team |  | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 10KHMY3 |  | DC-RPA-HA1 | CLUSTER1-NODE3 | 10.32.27.244 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 10KHMY3 |  | DC-RPA-NUG1 | CLUSTER1-NODE3 | 10.32.27.214, fe80::250:56ff:fe82:9935 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 10KHMY3 |  | DC-RPA-ORCH1 | CLUSTER1-NODE3 | 10.32.27.212 | Application Team | THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 10KHMY3 |  | DC-RPA-ORCH12 | CLUSTER1-NODE3 | 10.32.38.196 | Application Team | Vijey/Ankit ¦ 9487691736/7038831744 ¦ hotoncbs@canarabank.com;vijeyvr@canarabank.com;ankitsr@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 10KHMY3 |  | DC-RPA-ORCH13 | CLUSTER1-NODE3 | 10.32.38.197 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 10KHMY3 |  | DC-RPA-ORCH2 | CLUSTER1-NODE3 | 10.32.27.213 | Application Team | THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 61KHMY3 |  | DC-CRMENCRYPT-APP3 | CLUSTER1-NODE4 | 10.32.51.17 | Application Team | Saket/Gaurav Baberwal | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 61KHMY3 |  | DC-RPA-HA2 | CLUSTER1-NODE4 | 10.32.27.245 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 61KHMY3 |  | DC-RPA-HA3 | CLUSTER1-NODE4 | 10.32.27.246 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 61KHMY3 |  | DC-UIPATH-DB2 | CLUSTER1-NODE4 | 10.32.38.230 | Application Team | Vijey/Ankit | DB Team |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | Software Project Management Section |  | Hyper-V VM | 9MJHMY3 |  | WIN-RB3EM3SD28I | DCHYPRVBASE1 | 10.33.20.45 | Application Team |  | N/A |  | Kyndryl BAU – Virtualization |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | TM Section Integrated Treasury Wing | Swift | LPAR | 78414F8 |  | SWIFTINSAADR | E980-1-9080-M9S-SN78414F8 | 172.16.10.163 | Application Team | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com | N/A |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | To Be Confirmed |  | LPAR | 78414F8 |  | DCLADB1EKYCPRD | E980-1-9080-M9S-SN78414F8 | 172.16.11.134 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 1-3 · App → DB → LPAR/VM | 2026-10-24 20:00 | 5 | To Be Confirmed |  | LPAR | 78414F8 |  | DCLADB1TABBPRD | E980-1-9080-M9S-SN78414F8 | 172.16.11.137 | Application Team |  | DB Team |  | Kyndryl BAU – AIX |  | N/A (host row) |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Application Development Section (In House) (ADM) | ADM | Physical | 183M6C2 | Dell EMC Power Edge R630 | DC-SFTP-SRV |  | 172.16.41.193 | Application Team | Debarun, Yogesh ¦ 9398989380 ¦ yogeshsai@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 78A1DD8 | Power E1080 9080-HEX | A1-9080-HEX-SN78A1DD8-MIG-1 |  | 10.32.209.133,10.32.209.134 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DD8 | Power E1080 | A1-9080-HEX-SN78A1DD8-MIG-1 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DD8 | Power E1080 | A1-9080-HEX-SN78A1DD8-MIG-1 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DD8 | Power E1080 | A1-9080-HEX-SN78A1DD8-MIG-1 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DC8 | Power E1080 | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | 10.32.209.135,10.32.2.66,10.32.2.68,10.32.2.12,10.32.2.13,10.32.33.100,10.32.2.20,10.32.205.225 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DC8 | Power E1080 | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DC8 | Power E1080 | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DC8 | Power E1080 | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DC8 | Power E1080 | A2-9080-HEX-SN78A1DC8-CORE_DB-1 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78C7868 | Power E1080 and 1 | C2-9080-HEX-SN78C7868-UAT |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78C7868 | FC ENZO | C2-9080-HEX-SN78C7868-UAT |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78C7868 | Power E1080 | C2-9080-HEX-SN78C7868-UAT |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78C7868 | FC ENZO | C2-9080-HEX-SN78C7868-UAT |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78C7868 | FC ENZO | C2-9080-HEX-SN78C7868-UAT |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78C7868 | FC ENZO | C2-9080-HEX-SN78C7868-UAT |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 78C7868 | Power E1080 | C2-9080-HEX-SN78C7868-UAT |  | 10.32.209.164 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78C7868 | Power E1080 | C2-9080-HEX-SN78C7868-UAT |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DF8 | Power E1080 | C4-9080-HEX-SN78A1DF8-MIG-2 |  | 10.32.209.139 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DF8 | Power E1080 | C4-9080-HEX-SN78A1DF8-MIG-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DF8 | Power E1080 | C4-9080-HEX-SN78A1DF8-MIG-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78A1DF8 | Power E1080 | C4-9080-HEX-SN78A1DF8-MIG-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78A1DF8 | FC EMX0 | C4-9080-HEX-SN78A1DF8-MIG-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78A1DF8 | FC EMX0 | C4-9080-HEX-SN78A1DF8-MIG-2 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78C7848 | FC ENZO | D1-9080-HEX-SN78C7848-UAT |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78C7848 | FC ENZO and 1 | D1-9080-HEX-SN78C7848-UAT |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78C7848 | FC ENZO | D1-9080-HEX-SN78C7848-UAT |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 78C7848 | Power E1080 | D1-9080-HEX-SN78C7848-UAT |  | 10.32.201.166 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 78C7848 | Power E1080 | D1-9080-HEX-SN78C7848-UAT |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 78C7848 | Power E1080 | D1-9080-HEX-SN78C7848-UAT |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 78C7848 | Power E1080 | D1-9080-HEX-SN78C7848-UAT |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 78C7848 | Power E1080 | D1-9080-HEX-SN78C7848-UAT |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | No application installed | Physical | 130WA8A | MTM: 7063-CR1 | DC130WA8A |  | 10.32.201.3 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | HMC (NA) | Physical | 78A47CD | Power HMC | DC78A47CD |  | 10.32.201.95 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | PIM | Physical | 21KHMY3 | PowerEdge 750 | DCCANCRKPSM03 |  | 172.16.40.57 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | NCBS RAC | Physical | FCJXJ03 | DELL EMC PowerEdge R640 | DCDLLDB1RAC1NODE1 |  | 172.16.121.4 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | NCBS RAC | Physical | 3DCYM03 | DELL EMC PowerEdge R640 | DCDLLDB1RAC2NODE1 |  | 172.16.121.6 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | RAC DB | Physical | 5DCYM03 | DELL EMC PowerEdge R640 | DCDLLDB1RAC3NODE1 |  | 172.16.121.8 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 8XX5G33 | DELL EMC PowerEdge R640 | DCDLLDB1RAC5NODE2 |  | 10.32.12.13 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 71KHMY3 | PowerEdge 750 | DCDLLDB1RAC6NODE1 |  | 10.32.18.206 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 20KHMY3 | PowerEdge 750 | DCDLLDB1RAC6NODE2 |  | 10.32.18.207 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | D1KHMY3 | PowerEdge 750 | DCDLLDB1RAC7NODE1 |  | 10.32.22.196 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 41KHMY3 | PowerEdge 750 | DCDLLDB1RAC7NODE2 |  | 10.32.22.197 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) |  | Physical | C1A1KW2304376 | CFB1100 | DCHNAS5200-N2 |  | 10.32.202.55,10.32.202.56 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | B0KHMY3 | Dell EMC PowerEdge R750 | DCHVCLSTRN02 |  | 10.33.201.71 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | G3SXMZ3 | Dell EMC PowerEdge R750 | DCHVCLSTRN07 |  | 10.32.51.40 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | H3SXMZ3 | Dell EMC PowerEdge R750 | DCHVCLSTRN08 |  | 10.32.51.39 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 83SXMZ3 | Dell EMC PowerEdge R750 | DCHVCLSTRN09 |  | 10.32.51.38 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 93SXMZ3 | Dell EMC PowerEdge R750 | DCHVCLSTRN10 |  | 10.32.51.37 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 9MJHMY3 | Dell EMC PowerEdge R750 | DCHYPRVBASE1 |  | 10.33.192.14 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 81KHMY3 | PowerEdge 750 | DCHYPRVBASE2 |  | 10.33.131.160 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 40KHMY3 | Dell EMC PowerEdge R750 | DCNCBSDMZBASE1 |  | 10.33.201.80 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | C0KHMY3 | Dell EMC PowerEdge R750 | DCNCBSDMZBASE2 |  | 10.33.201.79 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | CKJHMY3 | Dell EMC PowerEdge R750 | DCNCBSINTBASE1 |  | 10.32.210.79 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | D0KHMY3 | Dell EMC PowerEdge R750 | DCNCBSINTBASE2 |  | 10.32.210.80 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Tracs UAT DB | Physical | 73SXMZ3 | Dell EMC PowerEdge R750 | DCUATDBN2 |  | 10.32.203.212 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Middleware Hyper V Cluster | Physical | D2SXMZ3 | Dell EMC PowerEdge R750 | DCUATDBN4 |  | 10.32.203.113 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Middleware Hyper V Cluster | Physical | D3SXMZ3 | Dell EMC PowerEdge R750 | DCUATDBN5 |  | 10.32.203.112 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Tracs UAT DB | Physical | J3SXMZ3 | Dell EMC PowerEdge R750 | DCUATDBN6 |  | 10.32.203.111 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE92X | Power E950 | E950-1-9040-MR9-SN78DE92X |  | 10.32.207.10 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE93X | Power E950 | E950-2-9040-MR9-SN78DE93X |  | 10.32.207.11 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE94X | Power E950 | E950-3-9040-MR9-SN78DE94X |  | 10.32.207.12 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE95X | Power E950 | E950-4-9040-MR9-SN78DE95X |  | 10.32.207.13 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE96X | Power E950 | E950-5-9040-MR9-SN78DE96X |  | 10.32.207.14 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE97X | Power E950 | E950-6-9040-MR9-SN78DE97X |  | 10.32.207.15 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE9AX | Power E950 | E950-7-9040-MR9-SN78DE9AX |  | 10.32.207.16 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE98X | Power E950 | E950-8-9040-MR9-SN78DE98X |  | 10.32.207.17 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78DE99X | Power E950 | E950-9-9040-MR9-SN78DE99X |  | 10.32.207.18 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78414F8 | Power E980 | E980-1-9080-M9S-SN78414F8 |  | 10.32.207.19 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78414F8 | FC EMX0 | E980-1-9080-M9S-SN78414F8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78414F8 | Power E980 | E980-1-9080-M9S-SN78414F8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78414F8 | Power E980 | E980-1-9080-M9S-SN78414F8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78414F8 | Power E980 | E980-1-9080-M9S-SN78414F8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78414F8 | Power E980 | E980-1-9080-M9S-SN78414F8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78415A8 | Power E980 | E980-2-9080-M9S-SN78415A8 |  | 10.32.207.21, 10.32.207.22 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78415A8 | Power E980 | E980-2-9080-M9S-SN78415A8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78415A8 | Power E980 | E980-2-9080-M9S-SN78415A8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78415A8 | Power E980 | E980-2-9080-M9S-SN78415A8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78415A8 | Power E980 | E980-2-9080-M9S-SN78415A8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 78415A8 | FC EMX0 | E980-2-9080-M9S-SN78415A8 |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 106525Z | Console Monitor | Not Applicable |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | No application installed | Physical | 130897A | MTM: 7063-CR1 | Not Applicable |  | 172.16.38.49 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 102656Y | Console Monitor | Not Applicable |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | FZHFY04 | EMX0 | Not Applicable |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | FZHFY10 | EMX0 | Not Applicable |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | CNB1110959 | Console | Not Applicable |  | Not Applicable | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Audit Vault Database Firewall | Physical | WZP222808BJ | UCS C220 M5 | OAVS2 |  | 172.16.32.180 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 783BFC8 | Power E980 | Server2-9080-M9S-SN783BFC8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 783BFC8 | Power E980 | Server2-9080-M9S-SN783BFC8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 783BFC8 | Power E980 | Server2-9080-M9S-SN783BFC8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Not Applicable | Physical | 783BFC8 | Power E980 | Server2-9080-M9S-SN783BFC8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 783BFC8 | FC EMX0 | Server2-9080-M9S-SN783BFC8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 783BFC8 | FC EMX0 | Server2-9080-M9S-SN783BFC8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | SFMS | Physical | 783BFC8 | FC EMX0 | Server2-9080-M9S-SN783BFC8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 783BFC8 | Power E980 | Server2-9080-M9S-SN783BFC8 |  | 10.32.207.26,10.32.207.25 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | PeopleSoft HRMS | Physical | C3SXMZ3 | Dell EMC PowerEdge R750 | TRAC Setup |  | 10.32.203.110 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 90KHMY3 | PowerEdge 750 | WIN-4JIKE60P6JV |  | 10.32.13.49 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | BKJHMY3 | Dell EMC PowerEdge R750 | WIN-STLAAFKA5J2 |  | 10.32.210.70 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | Audit Vault Database Firewall | Physical | WZP22270KUZ | UCS C220 M5 | avs00451d69b946 |  | 172.16.32.179 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | B1KHMY3 | PowerEdge 750 | cluster1-Node1 |  | 10.32.13.80 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 10KHMY3 | PowerEdge 750 | cluster1-Node3 |  | 10.32.13.44 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 61KHMY3 | PowerEdge 750 | cluster1-Node4 |  | 10.32.13.45 | Application Team | Rajeev ¦ rajeevkumar.j@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 3QGL6C2 | Dell Power Edge R430 | dc-dmz-host2.vmcandomain.com |  | 172.16.38.46 | Application Team | DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Center Operations Section (ITI) | DCO | Physical | 6XX5G33 | DELL EMC PowerEdge R640 | dcdlldb1rac5node1 |  | 10.32.12.12 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Data Warehouse Section | Data Warehouse | Physical | 60KHMY3 | Dell EMC PowerEdge R750 | dwgaipoc |  | 10.32.26.244 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 8KJHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE1 |  | 10.32.35.140 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 8MJHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE10 |  | 10.32.35.149 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 70KHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE11 |  | 10.32.35.150 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 7MJHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE2 |  | 10.32.35.141 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | HZJHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE3 |  | 10.32.35.142 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 50KHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE4 |  | 10.32.35.143 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 30KHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE5 |  | 10.32.35.144 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 74LHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE6 |  | 10.32.35.145 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | DKJHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE7 |  | 10.32.35.146 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 91KHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE8 |  | 10.32.35.147 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | G0KHMY3 | Dell EMC PowerEdge R750 | DCIRMSBASE9 |  | 10.32.35.148 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 84LHMY3 | Dell EMC PowerEdge R750 | DCPIRMSDB01 |  | 10.32.34.140 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 31KHMY3 | Dell EMC PowerEdge R750 | DCPIRMSDB02 |  | 10.32.34.141 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | EWIRM Section | IRMS | Physical | 7V1N0V3 | DELL EMC PowerEdge R650 | EWIRMUATAPPBASE |  | 10.33.134.72 | Application Team | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | FCR Deposits Section | RAC DB | Physical | 5ZHXJ03 | DELL EMC PowerEdge R640 | DCDLLDB1RAC3NODE2 |  | 172.16.121.9 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | Not Applicable | Physical | 783BFE8 | Power E980 | Server1-9080-M9S-SN783BFE8 |  | 10.32.207.28 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | Not Applicable | Physical | 783BFE8 | Power E980 | Server1-9080-M9S-SN783BFE8 |  | Not Applicable | Application Team | arundhatikatolkar@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | SFMS | Physical | 783BFE8 | FC EMX0 | Server1-9080-M9S-SN783BFE8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | SFMS | Physical | 783BFE8 | FC EMX0 | Server1-9080-M9S-SN783BFE8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | SFMS | Physical | 783BFE8 | FC EMX0 | Server1-9080-M9S-SN783BFE8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | Not Applicable | Physical | 783BFE8 | Power E980 | Server1-9080-M9S-SN783BFE8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | Not Applicable | Physical | 783BFE8 | Power E980 | Server1-9080-M9S-SN783BFE8 |  | Not Applicable | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | Not Applicable | Physical | 783BFE8 | Power E980 | Server1-9080-M9S-SN783BFE8 |  | Not Applicable | Application Team | LEEMA ROSELIN K 9741644668 | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Government Business and Financial Inclusion Section | Aadhaar seeding through web | Physical | 3131AG435894 | Infinitty global Line 2700CP | localhost |  | 172.16.44.71 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Network Administration Section | NCCM | Physical | 7PRXDV2 | DELL EMC PowerEdge R640 | DCBLR7PRXDV2 |  | 10.32.23.156 | Application Team | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Network Administration Section | NCCM | Physical | 7PRRDV2 | DELL EMC PowerEdge R640 | DCNCCMDB01 |  | 10.32.23.153 | Application Team | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Online Banking Technology Mobile Banking | MOBILE BANKING | Physical | JZJHMY3 | PowerEdge 750 | DC-MB-APP11 |  | 10.32.18.21, fe80::9053:f862:81cb:40b4 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Online Banking Technology Net banking Section | OFFLINE OTP | Physical | WZP22190GDB | UCS C220 M5 | UATAPP-OTP |  | 172.16.11.4 | Application Team | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Service Unit Section | SFMS | Physical | WZP23050K8T | UCS C220 M5 | DCCSW01SFMSNEFT |  | 172.16.32.120 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Service Unit Section | SFMS | Physical | WZP23050K70 | UCS C220 M5 | DCCSW02SFMSNEFT |  | 172.16.32.121 | Application Team | DEBJOY ROY ¦ 9874753518 ¦ AAQ_CanaraBank_NEFT_RTGS.xlsx | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Service Unit Section | RTGS | Physical | WZP22260A84 | UCS C220 M5 | DCPLCSWDO02RTGS |  | 172.16.32.119 | Application Team | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 4 · Physical server / frame | 2026-10-24 21:30 | 4 | Service Unit Section | RTGS | Physical | WZP22260A7Z | UCS C220 M5 | DCPLCSWQI01RTGS |  | 172.16.32.118 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | C1A1KW2304258 | MDKC810I-SBX | DCHNAS5200-N1 |  | 10.32.202.53,10.32.202.54 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 7813TC8 | Flash System 7000 | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 7813TC5 | Flash System 7000 | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | UATP10 Storage Boxes | Physical | 78E4Z5Z | Flash System 9500 | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | UATP10 Storage Boxes | Physical | 78E3NYR | FLASH SYSTEM 7300 | Not Applicable |  | 10.32.202.123 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 296Z9W3 | Dell Server | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 496Z9W3 | Dell Server | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 696Z9W3 | Dell Server | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 396Z9W3 | Dell Server | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 5C4Z9W3 | Dell Server | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 781V1N9 | Flash System 7000 | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E06F7 | Storewize-V7000 | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78E4F19 | SAN Volume Controller | Not Applicable |  | 10.32.202.87 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | UATP10 Storage Boxes | Physical | 78E4Z6R | Flash System 9500 | Not Applicable |  | 10.32.202.117 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | UATP10 Storage Boxes | Physical | 78E4Z6F | Flash System 9500 | Not Applicable |  | 10.32.202.120 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 7810KX3 | Flash System 7000 | Not Applicable |  | 10.32.202.100 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 7810KT2 | Flash System 7000 | Not Applicable |  | 10.32.202.100 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 7810KT4 | Flash System 7000 | Not Applicable |  | 10.32.202.97 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 7810KR5 | Flash System 7000 | Not Applicable |  | 10.32.202.94 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 7810KX7 | Flash System 7000 | Not Applicable |  | 10.32.202.94 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | CBS Allied Application | Physical | 78E3K6H | FLASH SYSTEM 7300 | Not Applicable |  | 10.32.202.100 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 483313 | Virtual Storage Plateform G350 | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 483313 | Virtual Storage Plateform G350 | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 8JW4L83 | EMC Unity 380F | SANINV170 |  | 172.16.34.171 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | G5KVNT3 | EMC Unity 380F | SANINV170 |  | 172.16.34.171 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | D5KVNT3 | EMC Unity 380F | SANINV170 |  | 172.16.34.171 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | CKM00194301481/22W9MX2 | Dell EMC Unity XT | SANINV170 |  | 172.16.34.171 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 483313 | SFRSVP | SANINV172 |  | 10.32.202.44 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E072T | Flash system 9100 | SANINV179 |  | 10.32.202.12 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E306B | SAN Volume Controller | SANINV180 |  | 10.32.202.18 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E3079 | SAN Volume Controller | SANINV181 |  | 10.32.202.24 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E3072 | SAN Volume Controller | SANINV182 |  | 10.32.202.22 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E306L | SAN Volume Controller | SANINV183 |  | 10.32.202.20 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 78E071K | IBM Flashsystem 9100 MTM: 9848-AF8 | SANINV191 |  | 10.32.202.9 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 78E3071 | IBM SAN Volume Controller MTM: 2145-SV2 | SANINV192 |  | 10.32.202.21 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 78E3078 | IBM SAN Volume Controller MTM: 2145-SV2 | SANINV193 |  | 10.32.202.23 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 78E306K | IBM SAN Volume Controller MTM: 2145-SV2 | SANINV194 |  | 10.32.202.19 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 78E306M | IBM SAN Volume Controller MTM: 2145-SV2 | SANINV195 |  | 10.32.202.25 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 78E3063 | IBM SAN Volume Controller MTM: 2145-SV2 | SANINV196 |  | 10.32.202.17 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 781V1N4 | Flash System 7000 | SANINV220 |  | 10.32.202.3 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 781V1M7 | Flash System 7000 | SANINV221 |  | 10.32.202.3 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E3KFT | FLASH SYSTEM 7300 | SANINV361 |  | 10.32.202.94 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E3KDF | FLASH SYSTEM 7300 | SANINV362 |  | 10.32.202.97 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4G8P | SAN Volume Controller | SANINV368 |  | 10.32.202.79 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4B4D | SAN Volume Controller | SANINV369 |  | 10.32.202.80 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4N36 | SAN Volume Controller | SANINV370 |  | 10.32.202.81 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4T96 | SAN Volume Controller | SANINV371 |  | 10.32.202.82 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4T04 | SAN Volume Controller | SANINV372 |  | 10.32.202.83 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4X74 | SAN Volume Controller | SANINV373 |  | 10.32.202.84 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4W21 | SAN Volume Controller | SANINV374 |  | 10.32.202.85 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4B1H | SAN Volume Controller | SANINV375 |  | 10.32.202.86 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4E54 | Flash System 9500 | SANINV376 |  | 10.32.202.88 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 78E4V30 | Flash System 9500 | SANINV377 |  | 10.32.202.91 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 612909 | Virtual Storage E790 | SANINV383 |  | 10.32.202.71 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | F077103H8LE22120246 | VSP E790 | SANINV383 |  | 10.32.202.71 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | 810675 | Lumada Ready | SANINV383 |  | 10.32.202.71 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 7823KWF | Storewize-V7000 | SANINV66 |  | 172.16.34.220, 172.16.34.221 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 7823KXE | Storewize-V7000 | SANINV68 |  | 172.16.34.220, 172.16.34.221 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 782206V | Storewize-V7000 | SANINV88 |  | 172.16.34.199 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | No application installed | Physical | 7821YYX | Storewize-V7000 | SANINV90 |  | 172.16.34.200, 172.16.34.201 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | DZRH504 | Power Protect DD9900 | candcdd.aranac.com |  | 10.32.24.14,10.32.24.15,10.32.24.16,10.32.24.17,172.16.3.99,172.16.11.158,172.16.38.7,10.32.24.47 | N/A |  | DB Team |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | GZRH504 | Power Protect DD9900 | candcdd.aranac.com |  | 10.32.24.14,10.32.24.15,10.32.24.16,10.32.24.17,172.16.3.99,172.16.11.158,172.16.38.7,10.32.24.47 | N/A |  | DB Team |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | CX4SMZ3 | DELL EMC PowerEdge R650 | candcnwsn01 |  | 10.32.24.61 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | Data Center Operations Section (ITI) | Not Applicable | Physical | BJDXMZ3 | DELL EMC PowerEdge R650 | candcnwsn02 |  | 10.32.24.62 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | NCBS Appication Support | SFMS | Physical | FSC1940004 | Quantum Scalar I6 Drive IBM LTO8 FH FS | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | NCBS Appication Support | SFMS | Physical | FSC1940004 | Quantum Scalar I6 Drive IBM LTO8 FH FS | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 5 · Storage / SVC / Tape | 2026-10-24 22:00 | 3 | NCBS Appication Support | SFMS | Physical | FSC1940004 | Quantum Scalar I6 Drive IBM LTO8 FH FS | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 787413W | Brocade G730 | BLR128B-G7-SW1 |  | 10.32.202.126 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 787414D | Brocade G730 | BLR128B-G7-SW2 |  | 10.32.202.127 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 787100G | SAN Director- 64G - F78 | BLR512B-G7-SW1 |  | 10.32.202.103,10.32.202.104,10.32.202.105 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 786711P | G720 | BLRDCREP_64BG7_SW1 |  | 10.32.202.109 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 786711C | G720 | BLRDCREP_64BG7_SW2 |  | 10.32.202.110 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 10194GB | DCX-8510-8-IBM- SAN Director 16G | DCX-BLR3SSWPC2111 |  | 172.16.38.233 | N/A |  | DB Team |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 10194DD | DCX-8510-8-IBM -SAN Diretcor 16G | DCX-BLR3SSWPC2112 |  | 172.16.38.236 | N/A |  | DB Team |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | No application installed | Physical | 781403F | IBM SAN512B-6 | DCX-BLR512B-1 |  | 10.32.202.27 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 6 · SAN switch / director | 2026-10-24 23:30 | 2 | Data Center Operations Section (ITI) | Not Applicable | Physical | 781405Z | IBM SAN512B-6-SAN Director 32G | DCX-BLR512B-2 |  | 10.32.202.30,10.32.202.31,10.32.202.32 | N/A |  | N/A |  | N/A |  | Kyndryl SAN / IBM |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO26141GLU | N9K-C93108TC-FX | DC-A1-N9K-TOR-SW1 |  | 10.32.200.130 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28130VWK | N9K-C93180YC-FX3 | DC-A1-N9K-TOR-SW2 |  | 10.32.200.122 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28140BNG | N9K-93180YC-FXC | DC-A2-N9K-RAC-SW3 |  | 10.32.200.128 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28140BV3 | N9K-93180YC-FXC | DC-A2-N9K-TOR-SW1 |  | 10.32.200.123 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO2813133P | N9K-93180YC-FXC | DC-A2-N9K-TOR-SW2 |  | 10.32.200.124 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FLM261608D0 | N9K-C93180YC-FX3 | DC-B2-N9K-DMZ-TOR-SW |  | 10.33.200.20 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO2614150K | N9K-C93108TC-EX | DC-C1-N9K-TOR-SW2 |  | 10.32.200.79 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO22273YZS | N9K-C93108TC-EX | DC-C1-N9K-ToR-SW-1 |  | 172.16.39.92 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO261414G3 | N9K-C93108TC-EX | DC-C4-N9K-TOR-SW1 |  | 10.32.200.131 | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28140BNC | N9K-C93180YC-FX3 | DC-C4-N9K-TOR-SW2 |  | 10.32.200.127 | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO281313BE | N9K-C93180YC-FX3 | DC-C5-N9K-TOR-SW N9K-C93180YC-FX3 |  | 10.32.200.141 | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO28140BQT | N9K-C93180YC-FX3 | DC-C6-N9K-TOR-SW N9K-C93180YC-FX3 |  | 10.32.200.142 | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO241208W1 | N9K-C93108YC-FX | DC-K1-N9K-TOR-SW1 |  | 10.32.200.4 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO24120F48 | N9K-C93180YC-FX | DC-K2-N9K-TOR-SW1 |  | 10.32.200.5 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO24120F3W | N9K-C93180YC-FX | DC-K3-N9K-TOR-SW1 |  | 10.32.200.6 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO24120EVL | N9K-C93180YC-FX | DC-K3-N9K-TOR-SW2 |  | 10.32.200.7 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO24120F13 | N9K-C93180YC-FX | DC-K4-N9K-TOR-SW1 |  | 10.32.200.8 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO241208LK | N9K-C93180YC-FX | DC-K4-N9K-TOR-SW2 |  | 10.32.200.9 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO24120F8J | N9K-C93180YC-FX | DC-K4-N9K-TOR-SW3 |  | 10.32.200.10 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO241208W2 | N9K-C93180YC-FX | DC-K5-N9K-TOR-SW1 |  | 10.32.200.11 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FDO24130M76 | N9K-C93180YC-FX | DC-K6-N9K-TOR-SW1 |  | 10.32.200.12 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FLM29290C0T | N9K-C93180YC-FX3 | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FLM29290BRN | N9K-C93180YC-FX3 | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FLM29290BVR | N9K-C93180YC-FX3 | Not Applicable |  | Not Applicable | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | FLM29290GES | N9K-C93180YC-FX3 | Not Applicable |  | Not Applicable | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
2 | 7 · Network / Security | 2026-10-25 | 1 | Data Center Operations Section (ITI) | Not Applicable | Physical | AJ29019530 | OFX5200-48Y | Not Applicable |  | Not Applicable | N/A |  | DB Team |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 4 · Physical server / frame | 2026-10-24 22:15 | 4 | Data Center Operations Section (ITI) | DCO | Physical | FNHTN24 | Dell Poweredge R760 | CAN-DC-CELL7 |  | 172.16.3.234 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
3 | 4 · Physical server / frame | 2026-10-24 22:15 | 4 | Data Warehouse Section | Data Warehouse | Physical | 1PG5MP2 | DELL EMC POWER EDGE R740 | DCDBSYNFRS |  | 10.32.25.5 | Application Team |  | DB Team |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
3 | 4 · Physical server / frame | 2026-10-24 22:15 | 4 | Online Banking Technology Net banking Section | WEB-OTP | Physical | WZP22190GCS | UCS C220 M5 | UATWEB-OTP |  |  | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
3 | 4 · Physical server / frame | 2026-10-24 22:15 | 4 | Service Unit Section | Not Applicable | Physical | 84B6FAW | Power S822 | Server-8284-22A-SN84B6FAW |  | 10.32.207.37 | Application Team |  | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
3 | 4 · Physical server / frame | 2026-10-24 22:15 | 4 | TM Section Integrated Treasury Wing | Swift | Physical | 847C10W | Power S814 | drswift02 |  | 172.16.41.197 | Application Team | Gambhirya Lokhande ¦ 7558713822 ¦ gambhiryatejrao@canarabank.com | N/A |  | N/A |  | Kyndryl BAU / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | FCUBS | OmniEnterprises AML Solution | Physical | 12DGGQ00100002 | netpower datacentre system | canamluat |  | 172.16.45.215 | N/A | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | FCNCA191702270 | Dell Server | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | FCNCA191800100 | Dell Server | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | FCNCA191800042 | Dell Server | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | FCNCA191800014 | Dell Server | Not Applicable |  | To Be Confirmed | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | C6DBTZ3 | ECS PowerEdge R740xd2 | candcex300ecs1d1.aranac.com |  | 10.32.24.104 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | D6DBTZ3 | ECS PowerEdge R740xd2 | candcex300ecs1d10.aranac.com |  | 10.32.24.113 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | F6DBTZ3 | ECS PowerEdge R740xd2 | candcex300ecs1d11.aranac.com |  | 10.32.24.114 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | J5DBTZ3 | ECS PowerEdge R740xd2 | candcex300ecs1d2.aranac.com |  | 10.32.24.105 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | B6DBTZ3 | ECS PowerEdge R740xd2 | candcex300ecs1d3.aranac.com |  | 10.32.24.106 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 96DBTZ3 | ECS PowerEdge R740xd2 | candcex300ecs1d4.aranac.com |  | 10.32.24.107 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 10QLV03 | ECS PowerEdge R740xd2 | candcex300ecs1d5.aranac.com |  | 10.32.24.108 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | JZPLV03 | ECS PowerEdge R740xd2 | candcex300ecs1d6.aranac.com |  | 10.32.24.109 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | HZPLV03 | ECS PowerEdge R740xd2 | candcex300ecs1d7.aranac.com |  | 10.32.24.110 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 30QLV03 | ECS PowerEdge R740xd2 | candcex300ecs1d8.aranac.com |  | 10.32.24.111 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | FZPLV03 | ECS PowerEdge R740xd2 | candcex300ecs1d9.aranac.com |  | 10.32.24.112 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 20QLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d1.aranac.com |  | 10.32.24.115 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | GZPLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d10.aranac.com |  | 10.32.24.124 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | DZPLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d2.aranac.com |  | 10.32.24.116 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | BWTLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d3.aranac.com |  | 10.32.24.117 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 7HLLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d4.aranac.com |  | 10.32.24.118 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 9WTLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d5.aranac.com |  | 10.32.24.119 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | B0QLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d6.aranac.com |  | 10.32.24.120 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 8XPLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d7.aranac.com |  | 10.32.24.121 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 3ZPLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d8.aranac.com |  | 10.32.24.122 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | DYPLV03 | ECS PowerEdge R740xd2 | candcex300ecs2d9.aranac.com |  | 10.32.24.123 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | JYPLV03 | ECS PowerEdge R740xd2 | candcex500ecs3d1.aranac.com |  | 10.32.24.75 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 5WTLV03 | ECS PowerEdge R740xd2 | candcex500ecs3d2.aranac.com |  | 10.32.24.76 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 3WTLV03 | ECS PowerEdge R740xd2 | candcex500ecs3d3.aranac.com |  | 10.32.24.77 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 7WTLV03 | ECS PowerEdge R740xd2 | candcex500ecs3d4.aranac.com |  | 10.32.24.78 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | 4WTLV03 | ECS PowerEdge R740xd2 | candcex500ecs3d5.aranac.com |  | 10.32.24.79 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 5 · Storage / SVC / Tape | 2026-10-24 23:00 | 3 | To Be Confirmed |  | Physical | HJLLV03 | ECS PowerEdge R740xd2 | candcex500ecs3d6.aranac.com |  | 10.32.24.80 | N/A |  | N/A |  | N/A |  | Kyndryl Storage / OEM |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Cyber Security Operations Centre (CSOC) Section | Netscout Anti-DDOS(Network Appliance) | Physical | CG24148159LA | Arbor Edge Defense | DCCANARBOR |  | 10.33.201.10 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center | Physical | 23720020148 | NTB T12a-BP2 | DCCSWNTB01 |  | 10.33.200.63 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center | Physical | 23720020149 | NTB T12a-BP2 | DCCSWNTB02 |  | 10.33.200.64 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Cyber Security Operations Centre (CSOC) Section | Palo Alto Anti-APT(Firewall) | Physical | SR 025409001255 | PA5430 | DCCSWPAPT01 |  | 10.33.201.18 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Cyber Security Operations Centre (CSOC) Section | Palo Alto Anti-APT(Firewall) | Physical | SR 025409001274 | PA5430 | DCCSWPAPT02 |  | 10.33.201.19 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center | Physical | 3377DT33C | ASI9900 | DCCSWPSSL01 |  | 10.33.200.61 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Cyber Security Operations Centre (CSOC) Section | Cyber Security operations Center | Physical | 338BTT3CT | ASI9900 | DCCSWPSSL02 |  | 10.33.200.62 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | NA |  | Physical | W3-KVM Switch | KVM Switch | Not Applicable |  | NA | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | SDWAN | Physical | CS801400000012 | H-CS-XL-4E-R4A2U | DC-H2-P2 CLOUDSTATION |  | 10.37.0.6 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | SDWAN | Physical | IN801400000014 | H-CS-XL-4E-R4A2U | DC-H2-P2 INSIGHTS |  | 10.37.0.7 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | SDWAN | Physical | 801400000008 | H-CPG-10000-4E-R4A2U | DC-H3-P2 CLOUDPORT GATEWAY 2 |  | 172.16.226.153 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | SDWAN | Physical | 801400000007 | H-CPG-10000-4E-R4A2U | DC-H4-P2 CLOUDPORT GATEWAY 1 |  | 172.16.226.152 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | SDWAN | Physical | 501400000011 | Lavelle LN-CP-10G | DC-I1-P1 CLOUDPORT GATEWAY 2 |  | 172.16.226.142 | N/A | nitish kumar ¦ 9964841777 ¦ nitishkumarv@canarabank.com | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | SDWAN | Physical | CS401300000002 | LAVELLE Network CSE813MTQ3-R407CB | DC-J6-P1 CLOUDSTATION |  | 10.37.0.10 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | SDWAN | Physical | IN401300000002 | LAVELLE Network | DC-J6-P1 INSIGHTS |  | 10.37.0.11 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | ADC | Physical | f5-mucx-joiu | BIG-IP i11000 series | DCDMZADC01 |  | 10.32.200.201 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Network Administration Section | ADC | Physical | f5-ctyi-hccy | BIG-IP i11000 series | DCDMZADC02 |  | 10.32.200.202 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | Online Banking Technology Mobile Banking | HSM | Physical | 697640 | Luna HSM | Not Applicable |  | 10.32.18.69 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | LR202402004472 | RR1-CP-26 | CB-DC-CP-CLOUD-FW1 |  | 10.32.209.114 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | HWXRT04 | smart-1 6000-L | CB-DC-CP-EVENT-SRV |  | 10.32.200.243 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | LR202402009885 | RR1-CP-26 | CB-DC-CP-INTERNET-PROXY-FW1 |  | 10.32.209.98 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | LR202402009851 | RR1-CP-26 | CB-DC-CP-INTERNET-PROXY-FW2 |  | 10.32.209.99 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 8xxRT04 | Check point | CB-DC-CP-MGMT-SRV |  | 10.32.200.242 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | LR202401010219 | 29100 | Checkpoint 29100 CB-DC-CP-DMZ-FW1 |  | 10.32.209.66 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | LR202312007390 | 29100 | Checkpoint 29100 CB-DC-CP-DMZ-FW2 |  | 10.32.209.67 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FOC2132R03J | Nexus 3548-X | Cisco Nexus 3548-X DC-N3-DMZ-PXY-WAN-SW-2Y |  | 10.33.5.150 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FOC2132R03L | Nexus 3548-X | Cisco Nexus 3548-X DC-N4-DMZ-PXY-WAN-SW-1 |  | 10.33.5.149 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FG3K2D3Z16800261 | Fortigate 3200D | DC-FORTI-FW-1 |  | 10.32.32.33 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FG3K2D3Z16800276 | Fortigate 3200D | DC-FORTI-FW-2 |  | 10.32.32.33 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FXS2436Q0R1 | ASR 1000 X | DC-H3-CORE-RTR-2 |  | 172.27.100.202 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FXS1741Q27Z | ASR 1006 | DC-H3-GM-RTR-2 |  | 172.27.98.132 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | WS3719420161 | QFX 5110-48S | DC-H3-H4-WAN-L2-SW |  | 10.32.200.23 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | WS3719420123 | QFX 5110-48S | DC-H3-H4-WAN-L2-SW |  | 10.32.200.23 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FOX1740GAHU | ASR 1002 X | DC-H3-KS-RTR-2 |  | 172.27.98.134 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FXS2545Q0Z1 | ASR 1000 X | DC-H4-CORE-RTR-1 |  | 172.27.100.201 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FXS1739Q2UK | ASR 1006 | DC-H4-GM-RTR-1 |  | 172.27.98.131 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FOX1740GAHX | ASR 1002 X | DC-H4-KS-RTR-1 |  | 172.27.98.133 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | JMX2302L035 | FPR - C9300 | DC-I2-FTD-CHASSIS-1 |  | 10.32.10.5 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | JMX2417L00R | FPR - C9300 | DC-I2-FTD-CHASSIS-2 |  | 10.32.10.6 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FGE22334V45 | Nexus 9508 | DC-I2-N9508-CORE-SW1 |  | 172.27.98.36 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | WMP2411007K | Cisco FMC 4600 | DC-I3-FMC-PRIMARY |  | 10.32.10.4 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FGE22334V4X | Nexus 9508 | DC-I3-N9508-CORE-SW2 |  | 172.27.98.37 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | VF3715360067 | QFX 5100-48S | DC-L3-WAN-AGG |  | 10.32.10.130 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | VF3715360265 | QFX 5100-48S | DC-L3-WAN-AGG |  | 10.32.10.130 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FDO28130W1X | N9K-C93180YC-FX3 | DC-N3-AGGEGATION-N9K-SW-2 |  | 172.16.41.12 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FGL2139814C | 4400 | DC-N3-CLOUD-RTR-2 |  | 10.33.5.182 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FDO28130VX8 | N9K-C93180YC-FX3 | DC-N3-CLOUD-WAN-SW-2 |  | 10.33.5.197 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | BJ606 | MX104 | DC-N3-INTERNET-PROXY-RTR2 |  | 10.33.5.166 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FLM261600BU | N9K-C93180YC-FX | DC-N3-N9K-PROXY-CORE-SW-2 |  | 10.33.200.147 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FDO281312YJ | N9K-C93180YC-FX3 | DC-N4-AGGREGATION-N9K-SW-1 |  | 172.16.41.11 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FGL2139814D | 4400 | DC-N4-CLOUD-RTR-1 |  | 10.33.5.181 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FDO28140BUE | N9K-C93180YC-FX3 | DC-N4-CLOUD-WAN-SW-1 |  | 10.33.5.196 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | CG094 | MX104 | DC-N4-INTERNET-PROXY-RTR1 |  | 10.33.5.165 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FLM26160862 | N9K-C93180YC-FX | DC-N4-N9K-PROXY-CORE-SW-1 |  | 10.33.200.146 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FLM281510M1 | C8300-1N-1S-6T | DC-O1-INTERNET-DMZ-RTR-01 |  | 10.33.5.2 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FLM281510M0 | C8300-1N-1S-6T | DC-O1-INTERNET-DMZ-RTR-02 |  | 10.33.5.3 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | VF3715360003 | QFX 5110-48S | DC-O1-INTERNET-JPR-L3 |  | 10.33.200.6 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | VF3715360016 | QFX 5110-48S | DC-O1-INTERNET-JPR-L3 |  | 10.33.200.6 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | F5-RBYB-IWXP | Big IP i5000 | DCINTADC01.aranac.com F5-BIG-LTM-15800 |  | 10.32.200.213 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | f5-pyrs-qtdq | Big IP i5000 | DCINTADC02.aranac.com F5-BIG-LTM-15800 |  | 10.32.200.214 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 8RM4SR3 | S5248F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 8RF8SR3 | S5248F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 8RF6SR3 | S5248F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 8RD6SR3 | S5248F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 9435SR3 | S5248F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 9434SR3 | S5248F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 30YB9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 30XD9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 30YC9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 310C9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 25JD9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 25CD9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 25GC9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 25KD9Z2 | S5148F-ON | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | TSBJC2003784 | LOADMASTER X15 | Not Applicable |  | 10.32.24.41,10.32.24.42,10.32.24.95,10.32.24.96,10.32.24.97 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | TSBJ52004985 | LOADMASTER X15 | Not Applicable |  | 10.32.24.41,10.32.24.42,10.32.24.95,10.32.24.96,10.32.24.97 | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FG4H0FT923914098 | Fortigate 400F | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | LR202402009861 | RR1-CP-26 | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | FG4H0FT923913688 | Fortigate 400F | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending
3 | 7 · Network / Security | 2026-10-24 23:45 | 1 | To Be Confirmed |  | Physical | 1901312380 | Edge safe | Not Applicable |  | Not Applicable | N/A |  | N/A |  | N/A |  | Kyndryl Network / Bank |  | Pending | Pending

## Batch_App_Summary (hidden)
APPLICATION VIEW – DEVICES PER APPLICATION OWNER GROUP AND BATCH (live counts from Scope)
App Owner Group | Applications | Batch 1 | Batch 2 | Batch 3 | Physical | AIX LPAR | Hyper-V VM | Total | Application Bank SPOC(s) | Runbook Walkthrough Done (Y/N) | App Sign-off at Target (Y/N)
API Banking Section | APG (Google API Gatway) | 0 | 5 | 0 | 0 | 0 | 5 | 5 | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com
Application Development Section (In House) (ADM) | ADM | 0 | 1 | 0 | 1 | 0 | 0 | 1 | Debarun, Yogesh ¦ 9398989380 ¦ yogeshsai@canarabank.com
ATM Section | ATM | 0 | 8 | 0 | 0 | 0 | 8 | 8 | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com
Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | 0 | 13 | 0 | 0 | 0 | 13 | 13 | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com ; Rajesh A, Kengal Veerendra Patil ¦ 7810073373/9880283138 ¦ hoccmssection@canarabank.com/hoccpstech@canarabank.com
CBS(UTKARSH) | CBS(UTKARSH) | 0 | 62 | 0 | 0 | 62 | 0 | 62 | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com ; VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM
Compliance Department | Compliance Kartavya | 0 | 2 | 0 | 0 | 0 | 2 | 2
Compliance Department section | Compliance Kartavya | 0 | 2 | 0 | 0 | 0 | 2 | 2 | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com
CTS | DEM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | Shakti Narayan Gupta,Bhupesh Piplani,7975142177/9650976622,hoditcts@canarabank.com
Cyber Security Operations Centre (CSOC) Section | Netscout Anti-DDOS(Network Appliance), Cyber Security operations Center, Palo Alto Anti-APT(Firewall) | 0 | 0 | 7 | 7 | 0 | 0 | 7
Data Center Operations Section (ITI) | SFMS, DCO, UATP10 Storage Boxes, NDR HMC, CBS Allied Application, Database Server - NDC - ASBA n Dpsecure, No application installed, Audit Vault Database Firewall, NCBS RAC, RAC DB, Middleware Hyper V Cluster, Tracs UAT DB … | 39 | 261 | 1 | 241 | 54 | 6 | 301 | Rajeev ¦ rajeevkumar.j@canarabank.com ; DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com ; Sangeetha ¦ sangeetha_r@canarabank.com ; Debjoy - 9874753518 ¦ debjoyroy@canarabank.com
Data Warehouse Section | Data Warehouse | 0 | 2 | 1 | 2 | 1 | 0 | 3
Digital Lending and LAPS Section | CORPORATE LOAN MODULE, GST SAHAY, LAPS | 0 | 21 | 0 | 0 | 10 | 11 | 21 | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com
DPSecure | Dpsecure | 2 | 2 | 0 | 0 | 0 | 4 | 4 | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com
EWIRM Section | IRMS | 0 | 44 | 0 | 14 | 0 | 30 | 44 | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com
FCC Section | FSCM | 0 | 1 | 0 | 0 | 1 | 0 | 1 | Manoj Kumar T ¦ 9300331307 ¦ manojkumart@canarabank.com
FCR Deposits Section | RAC DB, CKYC | 0 | 3 | 0 | 1 | 0 | 2 | 3 | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com
FCUBS | OmniEnterprises AML Solution, FCUBS | 0 | 16 | 1 | 1 | 15 | 1 | 17 | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com ; Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com / PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com ; Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com
Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | 0 | 4 | 0 | 0 | 0 | 4 | 4 | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com
Government Business and Financial Inclusion Section | Aadhaar seeding through web, SFMS, FI, DC Aadhar Vault DB, DB server, EKYC, TAB, DB, CEDGE | 0 | 17 | 0 | 9 | 7 | 1 | 17 | arundhatikatolkar@canarabank.com ; LEEMA ROSELIN K 9741644668 ; Kiran B R ¦ 7619453224 ¦ figsupport@canarabank.com & kiranbr@integramicro.co.in & hoditfimb@canarabank.com
Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | 0 | 2 | 0 | 0 | 2 | 0 | 2 | DBA Team
HRMS Technical Section | PeopleSoft HRMS | 0 | 15 | 0 | 0 | 0 | 15 | 15 | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com
IIB(DCA) | IIB/ACE/ESB | 0 | 8 | 0 | 0 | 8 | 0 | 8 | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM
IT Assets Management Section | RAP Remote | 4 | 0 | 0 | 0 | 0 | 4 | 4 | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com
NA |  | 0 | 0 | 1 | 1 | 0 | 0 | 1
NCBS Appication Support | SFMS | 0 | 3 | 0 | 3 | 0 | 0 | 3
Network Administration Section | NCCM, SDWAN, ADC | 0 | 2 | 9 | 11 | 0 | 0 | 11 | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com ; nitish kumar ¦ 9964841777 ¦ nitishkumarv@canarabank.com
New Initiatives-Technology Innovation Section |  | 0 | 1 | 0 | 0 | 0 | 1 | 1
Online Banking Technology Mobile Banking | MOBILE BANKING, HSM, IMPS, UPI, MB | 0 | 11 | 1 | 2 | 5 | 5 | 12 | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com ; NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com ; Arjun ¦ 9952404855 ¦ hotomb@canarabank.com
Online Banking Technology Mobile Banking Section |  | 0 | 1 | 0 | 0 | 0 | 1 | 1
Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | 0 | 2 | 0 | 0 | 0 | 2 | 2 | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com
Online Banking Technology Net banking Section | OFFLINE OTP, WEB-OTP, OBDX, OBT NET Banking Section - Report Server, OBT NET Banking Server - Jenkins Server, PKI, GIFTCITY OBDX | 0 | 29 | 1 | 2 | 24 | 4 | 30 | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com ; RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com ; RAGHURAM ¦ 8908226867 ¦ RAGHURAMP@canarabank.com ; VEEKASH ¦ 919945680436 ¦ veekashkumar@canarabank.com
Online Banking Technology UPI and INFRA Section | UPI DB | 0 | 2 | 0 | 0 | 2 | 0 | 2
Service Unit Section | SFMS, RTGS | 2 | 5 | 1 | 7 | 0 | 1 | 8 | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com ; DEBJOY ROY ¦ 9874753518 ¦ AAQ_CanaraBank_NEFT_RTGS.xlsx
Software Project Management Section |  | 0 | 12 | 0 | 0 | 0 | 12 | 12 | THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com ; Vijey/Ankit ¦ 9487691736/7038831744 ¦ hotoncbs@canarabank.com;vijeyvr@canarabank.com;ankitsr@canarabank.com ; Saket/Gaurav Baberwal ; Vijey/Ankit
SPMS | ASBA, CRM, Portal, DOCUMENT MANAGEMENT SYSTEM, Queue Management System, SPMS | 3 | 18 | 0 | 0 | 0 | 21 | 21 | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com ; K Sudheer Kumar, Gaurav Baberwal ¦ 7095444823 , 7239851522 ¦ sudheerkumar.k@canarabank.com ; Gururaj Pamidi ¦ 9535105108 ¦ gururajnaidu.pamidi@kyndryl.com /Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com ; Mamidala Nitin Vyas ¦ 81420 00043 ¦ nitinvyas.mamidala@canarabank.com
TM Section Integrated Treasury Wing | Swift | 0 | 1 | 1 | 1 | 1 | 0 | 2 | Gambhirya Lokhande ¦ 7558713822 ¦ gambhiryatejrao@canarabank.com ; DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com
To Be Confirmed |  | 0 | 2 | 93 | 93 | 2 | 0 | 95
TOTAL |  | 50 | 579 | 117 | 396 | 194 | 156 | 746

## Truck_Tracker (hidden)
TRUCK TRACKER – PLANNED vs ACTUAL (planned times linked to Cutover sheet)
Batch | Truck No | Empty Racks | OEM Loaded Racks | Loose Devices | Boxes Used (of 45) | Planned Load Start | Planned Departure (ITI) | Planned Arrival (STT) | Actual Departure | Actual Arrival | Actual Transit (h:mm) | Departure Variance (h:mm) | Vehicle No | Gate Pass No | E-Way Bill No | Seal No | Escort / Driver | Status | Remarks
1 | TR-1 | D5 | C3 | 1 SAN director/switch, 2 storage/backup/tape | 44.75 | 2026-10-24 12:00 | 2026-10-24 12:30 | 2026-10-24 14:30 | [9 empty] | Planned
1 | TR-1.1 | — | L1 | 1 storage/backup/tape | 24.5 | 2026-10-24 12:30 | 2026-10-24 13:00 | 2026-10-24 15:00 | [9 empty] | Planned
1 | TR-1.2 | — | L2, L3 | — | 45 | 2026-10-24 13:00 | 2026-10-24 13:30 | 2026-10-24 15:30 | [9 empty] | Planned
1 | TR-1.3 | GR-A1, GR-A2, GR-A3, GR-A4 | — | — | 45 | 2026-10-24 13:30 | 2026-10-24 14:00 | 2026-10-24 16:00 | [9 empty] | Planned
1 | TR-1.4 | A4 | — | 2 SAN director/switch, 6 storage/backup/tape, 6 server, 11 network/security | 33.25 | 2026-10-24 14:00 | 2026-10-24 14:30 | 2026-10-24 16:30 | [9 empty] | Planned
2 | TR-2 | C1, W6, X5 | — | 2 SAN director/switch, 4 storage/backup/tape | 44.75 | 2026-10-25 05:30 | 2026-10-25 06:00 | 2026-10-25 08:00 | [9 empty] | Planned
2 | TR-2.1 | — | A1, A2 | — | 45 | 2026-10-25 06:00 | 2026-10-25 06:30 | 2026-10-25 08:30 | [9 empty] | Planned
2 | TR-2.2 | — | A5, A6 | — | 45 | 2026-10-25 06:30 | 2026-10-25 07:00 | 2026-10-25 09:00 | [9 empty] | Planned
2 | TR-2.3 | — | C2, C4 | — | 45 | 2026-10-25 07:00 | 2026-10-25 07:30 | 2026-10-25 09:30 | [9 empty] | Planned
2 | TR-2.4 | — | C5, C6 | — | 45 | 2026-10-25 07:30 | 2026-10-25 08:00 | 2026-10-25 10:00 | [9 empty] | Planned
2 | TR-2.5 | — | D1, D2 | — | 45 | 2026-10-25 08:00 | 2026-10-25 08:30 | 2026-10-25 10:30 | [9 empty] | Planned
2 | TR-2.6 | — | D3, D6 | — | 45 | 2026-10-25 08:30 | 2026-10-25 09:00 | 2026-10-25 11:00 | [9 empty] | Planned
2 | TR-2.7 | — | F7, K1 | — | 45 | 2026-10-25 09:00 | 2026-10-25 09:30 | 2026-10-25 11:30 | [9 empty] | Planned
2 | TR-2.8 | — | K2, K3 | — | 45 | 2026-10-25 09:30 | 2026-10-25 10:00 | 2026-10-25 12:00 | [9 empty] | Planned
2 | TR-2.9 | — | K4, K5 | — | 45 | 2026-10-25 10:00 | 2026-10-25 10:30 | 2026-10-25 12:30 | [9 empty] | Planned
2 | TR-2.10 | — | K6, L5 | — | 45 | 2026-10-25 10:30 | 2026-10-25 11:00 | 2026-10-25 13:00 | [9 empty] | Planned
2 | TR-2.11 | — | — | 3 SAN director/switch, 19 storage/backup/tape | 45 | 2026-10-25 11:00 | 2026-10-25 11:30 | 2026-10-25 13:30 | [9 empty] | Planned
2 | TR-2.12 | — | — | 10 storage/backup/tape, 29 server | 45 | 2026-10-25 11:30 | 2026-10-25 12:00 | 2026-10-25 14:00 | [9 empty] | Planned
2 | TR-2.13 | — | — | 32 server, 4 network/security | 32 | 2026-10-25 12:00 | 2026-10-25 12:30 | 2026-10-25 14:30 | [9 empty] | Planned
3 | TR-3 | W3, W4, W5 | — | 11 storage/backup/tape, 1 server | 44.75 | 2026-10-25 11:00 | 2026-10-25 11:30 | 2026-10-25 13:30 | [9 empty] | Planned
3 | TR-3.1 | — | — | 21 storage/backup/tape, 4 server, 12 network/security | 45 | 2026-10-25 11:30 | 2026-10-25 12:00 | 2026-10-25 14:00 | [9 empty] | Planned
3 | TR-3.2 | — | — | 27 network/security | 45 | 2026-10-25 12:00 | 2026-10-25 12:30 | 2026-10-25 14:30 | [9 empty] | Planned
3 | TR-3.3 | — | — | 41 network/security | 27 | 2026-10-25 12:30 | 2026-10-25 13:00 | 2026-10-25 15:00 | [9 empty] | Planned

## Truck_Load_Plan (hidden)
TRUCK LOAD PLAN – LOADING SEQUENCE PER TRUCK (from inventory_Batch_Plan_v3.xlsx)
Per truck: 45 boxes. 1 box = 1 × 2U device or 2 × 1U devices; devices > 2U use ⌈U/2⌉ boxes. Racks: empty rack = 11.25, OEM-loaded rack = 22.5 box-equivalents. Batch 1 order: SAN Director → P10 frame (C3) → tape (D5 + tape drives, L1/L2/L3) → NDC devices in the following trucks.
Batch | Truck No | Truck Movement Time | Load Seq | Load Item | Source Rack | Hostname | Serial(s) | Boxes Used | Target Rack / Note | Loaded at Source (Y/N) | Received at Target (Y/N) | Received at Target (Y/N)
1 | TR-1 | 12:30 | 1 | Loose SAN director/switch | A4 | BLR512B-G7-SW2 | 755231F | 7 | 14U → F-01 / U 4-17
1 | TR-1 | 12:30 | 2 | OEM loaded rack | C3 | C3-9080-HEX-SN78A1DE8-CORE_DB-2, DC-C3-N9K-TOR-SW2, DC-C3-N9K-TOR-SW1, DC-C3-N9K-RAC-SW3 | 78A1DE8, 78A1DE8, 78A1DE8, 78A1DE8, 78A1DE8, FDO28140BUK, FDO28130JMK, FDO2813130Y | 22.5 | Rack → H-14 (travels with 8 device rows)
1 | TR-1 | 12:30 | 3 | Empty rack | D5 |  |  | 11.25 | Rack → D-04 (empty)
1 | TR-1 | 12:30 | 4 | Loose storage/backup/tape | D5 | Not Applicable | 5ZWGVP3 | 2 | 3U → D-04 / U 9-11
1 | TR-1 | 12:30 | 5 | Loose storage/backup/tape | D5 | Not Applicable | H4XGVP3 | 2 | 3U → D-04 / U 12-14
1 | TR-1 | 12:30 |  | TRUCK TOTAL |  |  |  | 44.75 | of 45 boxes
1 | TR-1.1 | 13:00 | 1 | Loose storage/backup/tape | D5 | TAPEINV22 | 6G0HVP3 | 2 | 3U → D-04 / U 15-17
1 | TR-1.1 | 13:00 | 2 | OEM loaded rack | L1 |  | 78BB816 | 22.5 | Rack → C-01 (travels with 1 device rows)
1 | TR-1.1 | 13:00 |  | TRUCK TOTAL |  |  |  | 24.5 | of 45 boxes
1 | TR-1.2 | 13:30 | 1 | OEM loaded rack | L2 |  | 78DB196 | 22.5 | Rack → C-02 (travels with 1 device rows)
1 | TR-1.2 | 13:30 | 2 | OEM loaded rack | L3 |  | 78DB197 | 22.5 | Rack → C-03 (travels with 1 device rows)
1 | TR-1.2 | 13:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
1 | TR-1.3 | 14:00 | 1 | Empty rack | GR-A1 |  |  | 11.25 | Rack → N-01 (empty)
1 | TR-1.3 | 14:00 | 2 | Empty rack | GR-A2 |  |  | 11.25 | Rack → N-02 (empty)
1 | TR-1.3 | 14:00 | 3 | Empty rack | GR-A3 |  |  | 11.25 | Rack → N-03 (empty)
1 | TR-1.3 | 14:00 | 4 | Empty rack | GR-A4 |  |  | 11.25 | Rack → N-04 (empty)
1 | TR-1.3 | 14:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
1 | TR-1.4 | 14:30 | 1 | Loose SAN director/switch | GR-A1 | BLRNDC_64BG7_SW1 | 786731M | 0.5 | 1U → N-03 / U 38
1 | TR-1.4 | 14:30 | 2 | Loose SAN director/switch | GR-A2 | BLRNDC_64BG7_SW2 | 786729Z | 0.5 | 1U → N-04 / U 35
1 | TR-1.4 | 14:30 | 3 | Loose storage/backup/tape | GR-A1 | SANINV379 | 78E4Y9C | 1 | 2U → N-03 / U 17-16
1 | TR-1.4 | 14:30 | 4 | Loose storage/backup/tape | GR-A1 | SANINV378 | 78E4Y8T | 1 | 2U → N-03 / U 15-14
1 | TR-1.4 | 14:30 | 5 | Loose storage/backup/tape | GR-A1 | Not Applicable | 78E3NKE2 | 1 | 2U → N-03 / U 13-12
1 | TR-1.4 | 14:30 | 6 | Loose storage/backup/tape | GR-A2 | SANINV382 | 78E4Z1B | 1 | 2U → N-04 / U 17-16
1 | TR-1.4 | 14:30 | 7 | Loose storage/backup/tape | GR-A2 | SANINV380 | 78E4Z1E | 1 | 2U → N-04 / U 15-14
1 | TR-1.4 | 14:30 | 8 | Loose storage/backup/tape | GR-A2 | SANINV381 | 78E3NPL | 1 | 2U → N-04 / U 13-12
1 | TR-1.4 | 14:30 | 9 | Loose server | GR-A1 | CR1130RH6A | 130RH6A | 0.5 | 1U → N-03 / U 21
1 | TR-1.4 | 14:30 | 10 | Loose server | GR-A1 | Not Applicable | 3185702 | 0.5 | 1U → N-03 / U 23
1 | TR-1.4 | 14:30 | 11 | Loose server | GR-A2 | ndrfccdb | 78DA08X | 2 | 4U → N-04 / U 6-3
1 | TR-1.4 | 14:30 | 12 | Loose server | GR-A2 | Not Applicable | 78DA08X | 2 | 4U → N-04 / U 10-7
1 | TR-1.4 | 14:30 | 13 | Loose server | GR-A4 | NDC-BASENDC-APP | C8SSN24 | 1 | 2U → N-01 / U 6-5
1 | TR-1.4 | 14:30 | 14 | Loose server | GR-A4 | DCC0GRN24 | C0GRN24 | 1 | 2U → N-01 / U 8-7
1 | TR-1.4 | 14:30 | 15 | Loose network/security | GR-A3 | CB-NDR-P2P-SW | FDO28050YP1 | 0.5 | 1U → N-02 / U 39
1 | TR-1.4 | 14:30 | 16 | Loose network/security | GR-A3 | CB-NDR-P2P-SW | FDO28050YP4 | 0.5 | 1U → N-02 / U 37
1 | TR-1.4 | 14:30 | 17 | Loose network/security | GR-A3 | NDR-Cisco-Nexus-SW1 | FDO28160D18 | 0.5 | 1U → L-10 / U U4
1 | TR-1.4 | 14:30 | 18 | Loose network/security | GR-A3 | NDR-Cisco-Nexus-SW2 | FDO28160237 | 0.5 | 1U → L-11 / U U4
1 | TR-1.4 | 14:30 | 19 | Loose network/security | GR-A3 | Not Applicable | 2161392000161 | 0.5 | 0U → N-02 / U Not Mounted
1 | TR-1.4 | 14:30 | 20 | Loose network/security | GR-A3 | Not Applicable | SY2511A-131200531 / SY2304-131203010 | 0.5 | 0U → N-02 / U Not Mounted
1 | TR-1.4 | 14:30 | 21 | Loose network/security | GR-A3 | Not Applicable | CAEZ2226 | 2 | 3U → N-02 / U 4-2
1 | TR-1.4 | 14:30 | 22 | Loose network/security | GR-A4 | CAN-NDR-FORTINET-FW2 | FG3K2D3Z16800247 | 1 | 2U → N-01 / U 36-35
1 | TR-1.4 | 14:30 | 23 | Loose network/security | GR-A4 | CAN-NDR-FORTINET-FW1 | FG3K2D3Z16800269 | 1 | 2U → N-01 / U 34-33
1 | TR-1.4 | 14:30 | 24 | Loose network/security | GR-A4 | NDR-DMZ-SW-01 | FDO281513F3 | 0.5 | 1U → H-10 / U U4
1 | TR-1.4 | 14:30 | 25 | Loose network/security | GR-A4 | NDR_DMZ_SW_02 | FDO28160CZT | 0.5 | 1U → H-11 / U U4
1 | TR-1.4 | 14:30 | 26 | Empty rack | A4 |  |  | 11.25 | Rack → F-15 (empty)
1 | TR-1.4 | 14:30 |  | TRUCK TOTAL |  |  |  | 33.25 | of 45 boxes
2 | TR-2 | 6:00 | 1 | Empty rack | C1 |  |  | 11.25 | Rack → C-08 (empty)
2 | TR-2 | 6:00 | 2 | Empty rack | W6 |  |  | 11.25 | Rack → H-06 (empty)
2 | TR-2 | 6:00 | 3 | Empty rack | X5 |  |  | 11.25 | Rack → J-07 (empty)
2 | TR-2 | 6:00 | 4 | Loose SAN director/switch | A3 | BLR512B-G7-SW1 | 787100G | 7 | 14U → E-16 / U 4-17
2 | TR-2 | 6:00 | 5 | Loose SAN director/switch | D3 | BLR128B-G7-SW2 | 787414D | 0.5 | 1U → D-09 / U 23
2 | TR-2 | 6:00 | 6 | Loose storage/backup/tape | B2 | SANINV90 | 7821YYX | 1 | 2U → C-08 / U 4-5
2 | TR-2 | 6:00 | 7 | Loose storage/backup/tape | B2 | SANINV88 | 782206V | 1 | 2U → C-08 / U 6-7
2 | TR-2 | 6:00 | 8 | Loose storage/backup/tape | B2 | SANINV68 | 7823KXE | 1 | 2U → C-08 / U 8-9
2 | TR-2 | 6:00 | 9 | Loose storage/backup/tape | F5 | SANINV172 | 483313 | 0.5 | 1U → D-06 / U 25
2 | TR-2 | 6:00 |  | TRUCK TOTAL |  |  |  | 44.75 | of 45 boxes
2 | TR-2.1 | 6:30 | 1 | OEM loaded rack | A1 | DC-A1-N9K-TOR-SW1, A1-9080-HEX-SN78A1DD8-MIG-1, DC78A47CD, DC-A1-N9K-TOR-SW2 | FDO26141GLU, 78A1DD8, 78A1DD8, 78A1DD8, 78A47CD, 78A1DD8, FDO28130VWK, FZHFY04, FZHFY10, CNB1110959 | 22.5 | Rack → G-13 (travels with 10 device rows)
2 | TR-2.1 | 6:30 | 2 | OEM loaded rack | A2 | A2-9080-HEX-SN78A1DC8-CORE_DB-1, DC-A2-N9K-TOR-SW2, DC-A2-N9K-TOR-SW1, DC-A2-N9K-RAC-SW3 | 78A1DC8, 78A1DC8, 78A1DC8, 78A1DC8, 78A1DC8, FDO2813133P, FDO28140BV3, FDO28140BNG | 22.5 | Rack → G-14 (travels with 8 device rows)
2 | TR-2.1 | 6:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.2 | 7:00 | 1 | OEM loaded rack | A5 | SANINV368, SANINV369, SANINV370, SANINV371, BLRDCREP_64BG7_SW1, SANINV376 | 78E4G8P, 78E4B4D, 78E4N36, 78E4T96, 786711P, 78E4E54 | 22.5 | Rack → D-13 (travels with 6 device rows)
2 | TR-2.2 | 7:00 | 2 | OEM loaded rack | A6 | SANINV372, SANINV373, SANINV374, SANINV375, BLRDCREP_64BG7_SW2, SANINV377 | 78E4T04, 78E4X74, 78E4W21, 78E4B1H, 78E4F19, 786711C, 78E4V30 | 22.5 | Rack → C-12 (travels with 7 device rows)
2 | TR-2.2 | 7:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.3 | 7:30 | 1 | OEM loaded rack | C2 | C2-9080-HEX-SN78C7868-UAT | 78C7868, 78C7868, 78C7868, 78C7868, 78C7868, 78C7868, FLM29290C0T, FLM29290BRN, 78C7868, 78C7868 | 22.5 | Rack → G-15 (travels with 10 device rows)
2 | TR-2.3 | 7:30 | 2 | OEM loaded rack | C4 | C4-9080-HEX-SN78A1DF8-MIG-2, DC-C4-N9K-TOR-SW1, DC-C4-N9K-TOR-SW2 | 78A1DF8, 78A1DF8, 78A1DF8, 78A1DF8, 78A1DF8, 78A1DF8, FDO261414G3, FDO28140BNC | 22.5 | Rack → H-13 (travels with 8 device rows)
2 | TR-2.3 | 7:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.4 | 8:00 | 1 | OEM loaded rack | C5 | Server2-9080-M9S-SN783BFC8, DC-C5-N9K-TOR-SW N9K-C93180YC-FX3 | 783BFC8, 783BFC8, 783BFC8, 783BFC8, 783BFC8, 783BFC8, 783BFC8, 783BFC8, FDO281313BE | 22.5 | Rack → G-17 (travels with 9 device rows)
2 | TR-2.4 | 8:00 | 2 | OEM loaded rack | C6 | Server1-9080-M9S-SN783BFE8, DC-C6-N9K-TOR-SW N9K-C93180YC-FX3 | 783BFE8, 783BFE8, 783BFE8, 783BFE8, 783BFE8, 783BFE8, 783BFE8, 783BFE8, AJ29019530, FDO28140BQT | 22.5 | Rack → H-17 (travels with 10 device rows)
2 | TR-2.4 | 8:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.5 | 8:30 | 1 | OEM loaded rack | D1 | D1-9080-HEX-SN78C7848-UAT | 78C7848, 78C7848, 78C7848, FLM29290BVR, FLM29290GES, 78C7848, 78C7848, 78C7848, 78C7848, 78C7848 | 22.5 | Rack → H-15 (travels with 10 device rows)
2 | TR-2.5 | 8:30 | 2 | OEM loaded rack | D2 | BLR128B-G7-SW1 | 787413W, 7813TC8, 7813TC5, 78E4Z5Z, 78E3NYR | 22.5 | Rack → C-11 (travels with 5 device rows)
2 | TR-2.5 | 8:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.6 | 9:00 | 1 | OEM loaded rack | D3 |  | 78E4Z6R, 78E4Z6F | 22.5 | Rack → D-09 (travels with 2 device rows)
2 | TR-2.6 | 9:00 | 2 | OEM loaded rack | D6 | SANINV361, SANINV362 | 78E3KFT, 7810KX3, 7810KT2, 7810KT4, 7810KR5, 7810KX7, 78E3K6H, 78E3KDF | 22.5 | Rack → C-07 (travels with 8 device rows)
2 | TR-2.6 | 9:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.7 | 9:30 | 1 | OEM loaded rack | F7 | DCX-BLR3SSWPC2111 | 10194GB | 22.5 | Rack → F-15 (travels with 1 device rows)
2 | TR-2.7 | 9:30 | 2 | OEM loaded rack | K1 | E980-1-9080-M9S-SN78414F8, DC-K1-N9K-TOR-SW1 | 78414F8, 78414F8, 78414F8, 78414F8, 78414F8, 78414F8, FDO241208W1 | 22.5 | Rack → H-09 (travels with 7 device rows)
2 | TR-2.7 | 9:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.8 | 10:00 | 1 | OEM loaded rack | K2 | E980-2-9080-M9S-SN78415A8, DC-K2-N9K-TOR-SW1 | 78415A8, 78415A8, 78415A8, 78415A8, 78415A8, 78415A8, FDO24120F48 | 22.5 | Rack → G-09 (travels with 7 device rows)
2 | TR-2.8 | 10:00 | 2 | OEM loaded rack | K3 | E950-3-9040-MR9-SN78DE94X, E950-1-9040-MR9-SN78DE92X, E950-2-9040-MR9-SN78DE93X, DC-K3-N9K-TOR-SW1, DC-K3-N9K-TOR-SW2, DC130WA8A | 78DE94X, 78DE92X, 78DE93X, 106525Z, FDO24120F3W, FDO24120EVL, 130WA8A | 22.5 | Rack → H-08 (travels with 7 device rows)
2 | TR-2.8 | 10:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.9 | 10:30 | 1 | OEM loaded rack | K4 | E950-6-9040-MR9-SN78DE97X, E950-4-9040-MR9-SN78DE95X, E950-5-9040-MR9-SN78DE96X, DC-K4-N9K-TOR-SW1, DC-K4-N9K-TOR-SW2, DC-K4-N9K-TOR-SW3 | 78DE97X, 78DE95X, 78DE96X, 130897A, FDO24120F13, FDO241208LK, FDO24120F8J, 102656Y | 22.5 | Rack → G-08 (travels with 8 device rows)
2 | TR-2.9 | 10:30 | 2 | OEM loaded rack | K5 | E950-9-9040-MR9-SN78DE99X, E950-7-9040-MR9-SN78DE9AX, E950-8-9040-MR9-SN78DE98X, DC-K5-N9K-TOR-SW1 | 78DE99X, 78DE9AX, 78DE98X, FDO241208W2 | 22.5 | Rack → G-08 (travels with 4 device rows)
2 | TR-2.9 | 10:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.10 | 11:00 | 1 | OEM loaded rack | K6 | SANINV195, SANINV193, SANINV192, SANINV194, SANINV196 | 78E306M, 78E3078, 78E3071, 78E306K, 78E3063 | 22.5 | Rack → G-20 (travels with 5 device rows)
2 | TR-2.10 | 11:00 | 2 | OEM loaded rack | L5 | SANINV181, SANINV182, SANINV183, SANINV180 | 78E3079, 78E3072, 78E306L, 78E306B | 22.5 | Rack → H-19 (travels with 4 device rows)
2 | TR-2.10 | 11:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.11 | 11:30 | 1 | Loose SAN director/switch | G7 | DCX-BLR3SSWPC2112 | 10194DD | 7 | 14U → E-02 / U 4-17
2 | TR-2.11 | 11:30 | 2 | Loose SAN director/switch | K7 | DCX-BLR512B-1 | 781403F | 7 | 14U → F-16 / U 4-17
2 | TR-2.11 | 11:30 | 3 | Loose SAN director/switch | L6 | DCX-BLR512B-2 | 781405Z | 7 | 14U → E-01 / U 4-17
2 | TR-2.11 | 11:30 | 4 | Loose storage/backup/tape | B2 | SANINV66 | 7823KWF | 1 | 2U → C-08 / U 10-11
2 | TR-2.11 | 11:30 | 5 | Loose storage/backup/tape | B2 | Not Applicable | 781V1N9 | 1 | 2U → C-08 / U 14-15
2 | TR-2.11 | 11:30 | 6 | Loose storage/backup/tape | B2 | SANINV221 | 781V1M7 | 1 | 2U → C-08 / U 16-17
2 | TR-2.11 | 11:30 | 7 | Loose storage/backup/tape | B2 | SANINV220 | 781V1N4 | 1 | 2U → C-08 / U 18-19
2 | TR-2.11 | 11:30 | 8 | Loose storage/backup/tape | B2 | Not Applicable | 78E06F7 | 1 | 2U → C-08 / U 12-13
2 | TR-2.11 | 11:30 | 9 | Loose storage/backup/tape | F3 | SANINV170 | 8JW4L83 | 1 | 2U → D-06 / U 34-35
2 | TR-2.11 | 11:30 | 10 | Loose storage/backup/tape | F3 | SANINV170 | G5KVNT3 | 1 | 2U → D-06 / U 32-33
2 | TR-2.11 | 11:30 | 11 | Loose storage/backup/tape | F3 | SANINV170 | D5KVNT3 | 1 | 2U → D-06 / U 30-31
2 | TR-2.11 | 11:30 | 12 | Loose storage/backup/tape | F3 | SANINV170 | CKM00194301481/22W9MX2 | 1 | 2U → D-06 / U 28-29
2 | TR-2.11 | 11:30 | 13 | Loose storage/backup/tape | F5 | DCHNAS5200-N1 | C1A1KW2304258 | 2 | 3U → D-06 / U 21-23
2 | TR-2.11 | 11:30 | 14 | Loose storage/backup/tape | F5 | Not Applicable | 483313 | 1 | 2U → D-06 / U 16-17
2 | TR-2.11 | 11:30 | 15 | Loose storage/backup/tape | F5 | Not Applicable | 483313 | 1 | 2U → D-06 / U 14-15
2 | TR-2.11 | 11:30 | 16 | Loose storage/backup/tape | F6 | SANINV383 | 612909 | 1 | 2U → D-06 / U 4-6
2 | TR-2.11 | 11:30 | 17 | Loose storage/backup/tape | F6 | SANINV383 | F077103H8LE22120246 | 1 | 2U → D-06 / U 7-9
2 | TR-2.11 | 11:30 | 18 | Loose storage/backup/tape | F6 | SANINV383 | 810675 | 1 | 2U → D-06 / U 10-11
2 | TR-2.11 | 11:30 | 19 | Loose storage/backup/tape | K6 | SANINV191 | 78E071K | 1 | 2U → G-20 / U 4-5
2 | TR-2.11 | 11:30 | 20 | Loose storage/backup/tape | L5 | SANINV179 | 78E072T | 1 | 2U → H-19 / U 4-5
2 | TR-2.11 | 11:30 | 21 | Loose storage/backup/tape | S6 | Not Applicable | FSC1940004 | 3 | 6U → C-05 / U 16-21
2 | TR-2.11 | 11:30 | 22 | Loose storage/backup/tape | S6 | Not Applicable | FSC1940004 | 3 | 6U → C-05 / U 4-9
2 | TR-2.11 | 11:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.12 | 12:00 | 1 | Loose storage/backup/tape | S6 | Not Applicable | FSC1940004 | 3 | 6U → C-05 / U 10-15
2 | TR-2.12 | 12:00 | 2 | Loose storage/backup/tape | W6 | candcnwsn01 | CX4SMZ3 | 0.5 | 1U → H-06 / U 35
2 | TR-2.12 | 12:00 | 3 | Loose storage/backup/tape | W6 | candcnwsn02 | BJDXMZ3 | 0.5 | 1U → H-06 / U 36
2 | TR-2.12 | 12:00 | 4 | Loose storage/backup/tape | W6 | candcdd.aranac.com | DZRH504 | 2 | 3U → H-06 / U 24-26
2 | TR-2.12 | 12:00 | 5 | Loose storage/backup/tape | W6 | candcdd.aranac.com | GZRH504 | 2 | 3U → H-06 / U 27-29
2 | TR-2.12 | 12:00 | 6 | Loose storage/backup/tape | W6 | Not Applicable | 296Z9W3 | 2 | 3U → H-06 / U 30-32
2 | TR-2.12 | 12:00 | 7 | Loose storage/backup/tape | W6 | Not Applicable | 496Z9W3 | 3 | 5U → H-06 / U 4-8
2 | TR-2.12 | 12:00 | 8 | Loose storage/backup/tape | W6 | Not Applicable | 696Z9W3 | 3 | 5U → H-06 / U 9-13
2 | TR-2.12 | 12:00 | 9 | Loose storage/backup/tape | W6 | Not Applicable | 396Z9W3 | 3 | 5U → H-06 / U 14-18
2 | TR-2.12 | 12:00 | 10 | Loose storage/backup/tape | W6 | Not Applicable | 5C4Z9W3 | 3 | 5U → H-06 / U 19-23
2 | TR-2.12 | 12:00 | 11 | Loose server | E2 | DCPLCSWDO02RTGS | WZP22260A84 | 0.5 | 1U → C-14 / U 15
2 | TR-2.12 | 12:00 | 12 | Loose server | E2 | OAVS2 | WZP222808BJ | 0.5 | 1U → C-14 / U 23
2 | TR-2.12 | 12:00 | 13 | Loose server | E3 | DCPLCSWQI01RTGS | WZP22260A7Z | 0.5 | 1U → D-14 / U 8
2 | TR-2.12 | 12:00 | 14 | Loose server | E3 | avs00451d69b946 | WZP22270KUZ | 0.5 | 1U → D-14 / U 16
2 | TR-2.12 | 12:00 | 15 | Loose server | E3 | UATAPP-OTP | WZP22190GDB | 0.5 | 1U → D-14 / U 5
2 | TR-2.12 | 12:00 | 16 | Loose server | F2 | DCDLLDB1RAC5NODE2 | 8XX5G33 | 0.5 | 1U → A-10 / U 27
2 | TR-2.12 | 12:00 | 17 | Loose server | F2 | dcdlldb1rac5node1 | 6XX5G33 | 0.5 | 1U → B-10 / U 29
2 | TR-2.12 | 12:00 | 18 | Loose server | F3 | DCDLLDB1RAC1NODE1 | FCJXJ03 | 0.5 | 1U → H-02 / U 30
2 | TR-2.12 | 12:00 | 19 | Loose server | F3 | DCDLLDB1RAC2NODE1 | 3DCYM03 | 0.5 | 1U → H-02 / U 31
2 | TR-2.12 | 12:00 | 20 | Loose server | F3 | DCDLLDB1RAC3NODE1 | 5DCYM03 | 0.5 | 1U → A-10 / U 26
2 | TR-2.12 | 12:00 | 21 | Loose server | F4 | DCDLLDB1RAC3NODE2 | 5ZHXJ03 | 0.5 | 1U → B-10 / U 28
2 | TR-2.12 | 12:00 | 22 | Loose server | F5 | DCHNAS5200-N2 | C1A1KW2304376 | 2 | 3U → D-06 / U 18-20
2 | TR-2.12 | 12:00 | 23 | Loose server | F6 | DCCSW02SFMSNEFT | WZP23050K70 | 0.5 | 1U → D-14 / U 26
2 | TR-2.12 | 12:00 | 24 | Loose server | F6 | DCCSW01SFMSNEFT | WZP23050K8T | 0.5 | 1U → D-14 / U 17
2 | TR-2.12 | 12:00 | 25 | Loose server | J2 | DCUATDBN4 | D2SXMZ3 | 1 | 2U → L-01 / U 6-7
2 | TR-2.12 | 12:00 | 26 | Loose server | J2 | DCUATDBN5 | D3SXMZ3 | 1 | 2U → L-02 / U 6-7
2 | TR-2.12 | 12:00 | 27 | Loose server | J2 | DCUATDBN2 | 73SXMZ3 | 1 | 2U → L-01 / U 14-15
2 | TR-2.12 | 12:00 | 28 | Loose server | J2 | DCHVCLSTRN10 | 93SXMZ3 | 1 | 2U → H-01 / U 6-7
2 | TR-2.12 | 12:00 | 29 | Loose server | J2 | DCHVCLSTRN09 | 83SXMZ3 | 1 | 2U → H-01 / U 8-9
2 | TR-2.12 | 12:00 | 30 | Loose server | J2 | DCHVCLSTRN08 | H3SXMZ3 | 1 | 2U → H-01 / U 10-11
2 | TR-2.12 | 12:00 | 31 | Loose server | J2 | DCHVCLSTRN07 | G3SXMZ3 | 1 | 2U → H-01 / U 23-24
2 | TR-2.12 | 12:00 | 32 | Loose server | J2 | DCUATDBN6 | J3SXMZ3 | 1 | 2U → L-02 / U 8-9
2 | TR-2.12 | 12:00 | 33 | Loose server | J2 | TRAC Setup | C3SXMZ3 | 1 | 2U → H-01 / U 4-5
2 | TR-2.12 | 12:00 | 34 | Loose server | M1 | DCCANCRKPSM03 | 21KHMY3 | 1 | 2U → J-07 / U 16-17
2 | TR-2.12 | 12:00 | 35 | Loose server | M1 | DCHYPRVBASE2 | 81KHMY3 | 1 | 2U → J-07 / U 10-11
2 | TR-2.12 | 12:00 | 36 | Loose server | M1 | cluster1-Node1 | B1KHMY3 | 1 | 2U → J-07 / U 12-13
2 | TR-2.12 | 12:00 | 37 | Loose server | M1 | cluster1-Node3 | 10KHMY3 | 1 | 2U → J-07 / U 18-19
2 | TR-2.12 | 12:00 | 38 | Loose server | M1 | cluster1-Node4 | 61KHMY3 | 1 | 2U → J-07 / U 20-21
2 | TR-2.12 | 12:00 | 39 | Loose server | M5 | DC-SFTP-SRV | 183M6C2 | 0.5 | 1U → I-06 / U 32
2 | TR-2.12 | 12:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
2 | TR-2.13 | 12:30 | 1 | Loose server | M1 | DCDLLDB1RAC7NODE2 | 41KHMY3 | 1 | 2U → A-10 / U 28-29
2 | TR-2.13 | 12:30 | 2 | Loose server | M1 | DCDLLDB1RAC7NODE1 | D1KHMY3 | 1 | 2U → B-10 / U 22-23
2 | TR-2.13 | 12:30 | 3 | Loose server | M1 | DCDLLDB1RAC6NODE2 | 20KHMY3 | 1 | 2U → B-10 / U 30-31
2 | TR-2.13 | 12:30 | 4 | Loose server | M1 | DCDLLDB1RAC6NODE1 | 71KHMY3 | 1 | 2U → A-10 / U 20-21
2 | TR-2.13 | 12:30 | 5 | Loose server | M1 | WIN-4JIKE60P6JV | 90KHMY3 | 1 | 2U → J-07 / U 4-5
2 | TR-2.13 | 12:30 | 6 | Loose server | M1 | DC-MB-APP11 | JZJHMY3 | 1 | 2U → J-07 / U 6-7
2 | TR-2.13 | 12:30 | 7 | Loose server | M5 | dc-dmz-host2.vmcandomain.com | 3QGL6C2 | 0.5 | 1U → J-08 / U 20
2 | TR-2.13 | 12:30 | 8 | Loose server | M7 | DCNCBSDMZBASE2 | C0KHMY3 | 1 | 2U → L-01 / U 12-13
2 | TR-2.13 | 12:30 | 9 | Loose server | M7 | DCNCBSDMZBASE1 | 40KHMY3 | 1 | 2U → J-05 / U 12-13
2 | TR-2.13 | 12:30 | 10 | Loose server | M7 | DCNCBSINTBASE2 | D0KHMY3 | 1 | 2U → J-05 / U 14-15
2 | TR-2.13 | 12:30 | 11 | Loose server | M7 | WIN-STLAAFKA5J2 | BKJHMY3 | 1 | 2U → J-08 / U 18-19
2 | TR-2.13 | 12:30 | 12 | Loose server | M7 | DCHYPRVBASE1 | 9MJHMY3 | 1 | 2U → J-05 / U 8-9
2 | TR-2.13 | 12:30 | 13 | Loose server | M7 | DCHVCLSTRN02 | B0KHMY3 | 1 | 2U → J-05 / U 10-11
2 | TR-2.13 | 12:30 | 14 | Loose server | M7 | dwgaipoc | 60KHMY3 | 1 | 2U → J-05 / U 6-7
2 | TR-2.13 | 12:30 | 15 | Loose server | N5 | DCNCBSINTBASE1 | CKJHMY3 | 1 | 2U → I-08 / U 4-5
2 | TR-2.13 | 12:30 | 16 | Loose server | N5 | DCIRMSBASE11 | 70KHMY3 | 1 | 2U → I-08 / U 6-7
2 | TR-2.13 | 12:30 | 17 | Loose server | N5 | DCIRMSBASE9 | G0KHMY3 | 1 | 2U → J-05 / U 18-19
2 | TR-2.13 | 12:30 | 18 | Loose server | N5 | DCIRMSBASE8 | 91KHMY3 | 1 | 2U → J-05 / U 20-21
2 | TR-2.13 | 12:30 | 19 | Loose server | N5 | DCIRMSBASE7 | DKJHMY3 | 1 | 2U → I-08 / U 8-9
2 | TR-2.13 | 12:30 | 20 | Loose server | N5 | DCIRMSBASE4 | 50KHMY3 | 1 | 2U → I-08 / U 14-15
2 | TR-2.13 | 12:30 | 21 | Loose server | N5 | DCIRMSBASE2 | 7MJHMY3 | 1 | 2U → J-05 / U 22-23
2 | TR-2.13 | 12:30 | 22 | Loose server | N5 | DCIRMSBASE1 | 8KJHMY3 | 1 | 2U → J-05 / U 24-25
2 | TR-2.13 | 12:30 | 23 | Loose server | N5 | DCIRMSBASE10 | 8MJHMY3 | 1 | 2U → J-05 / U 16-17
2 | TR-2.13 | 12:30 | 24 | Loose server | N5 | DCIRMSBASE6 | 74LHMY3 | 1 | 2U → I-08 / U 10-11
2 | TR-2.13 | 12:30 | 25 | Loose server | N5 | DCIRMSBASE5 | 30KHMY3 | 1 | 2U → I-08 / U 12-13
2 | TR-2.13 | 12:30 | 26 | Loose server | N5 | DCIRMSBASE3 | HZJHMY3 | 1 | 2U → I-08 / U 16-17
2 | TR-2.13 | 12:30 | 27 | Loose server | N5 | DCPIRMSDB02 | 31KHMY3 | 1 | 2U → J-05 / U 26-27
2 | TR-2.13 | 12:30 | 28 | Loose server | N5 | DCPIRMSDB01 | 84LHMY3 | 1 | 2U → J-05 / U 28-29
2 | TR-2.13 | 12:30 | 29 | Loose server | O5 | localhost | 3131AG435894 | 1 | 2U → Scrap / U
2 | TR-2.13 | 12:30 | 30 | Loose server | P1 | DCBLR7PRXDV2 | 7PRXDV2 | 0.5 | 1U → E-05 / U 21
2 | TR-2.13 | 12:30 | 31 | Loose server | P1 | DCNCCMDB01 | 7PRRDV2 | 0.5 | 1U → E-05 / U 20
2 | TR-2.13 | 12:30 | 32 | Loose server | X2 | EWIRMUATAPPBASE | 7V1N0V3 | 0.5 | 1U → F-03 / U 24
2 | TR-2.13 | 12:30 | 33 | Loose network/security | B2 | DC-B2-N9K-DMZ-TOR-SW | FLM261608D0 | 0.5 | 1U → G-11 / U U19
2 | TR-2.13 | 12:30 | 34 | Loose network/security | C1 | DC-C1-N9K-ToR-SW-1 | FDO22273YZS | 0.5 | 1U → L-11 / U U6
2 | TR-2.13 | 12:30 | 35 | Loose network/security | C1 | DC-C1-N9K-TOR-SW2 | FDO2614150K | 0.5 | 1U → D-10 / U U6
2 | TR-2.13 | 12:30 | 36 | Loose network/security | K6 | DC-K6-N9K-TOR-SW1 | FDO24130M76 | 0.5 | 1U → I-10 / U Spare
2 | TR-2.13 | 12:30 |  | TRUCK TOTAL |  |  |  | 32 | of 45 boxes
3 | TR-3 | 11:30 | 1 | Empty rack | W3 |  |  | 11.25 | Rack → G-05 (empty)
3 | TR-3 | 11:30 | 2 | Empty rack | W4 |  |  | 11.25 | Rack → G-04 (empty)
3 | TR-3 | 11:30 | 3 | Empty rack | W5 |  |  | 11.25 | Rack → G-03 (empty)
3 | TR-3 | 11:30 | 4 | Loose storage/backup/tape | V3 | canamluat | 12DGGQ00100002 | 0.5 | 1U → NA / U
3 | TR-3 | 11:30 | 5 | Loose storage/backup/tape | W3 | candcex300ecs1d1.aranac.com | C6DBTZ3 | 1 | 2U → G-05 / U 4-5
3 | TR-3 | 11:30 | 6 | Loose storage/backup/tape | W3 | candcex300ecs1d10.aranac.com | D6DBTZ3 | 1 | 2U → G-05 / U 6-7
3 | TR-3 | 11:30 | 7 | Loose storage/backup/tape | W3 | candcex300ecs1d11.aranac.com | F6DBTZ3 | 1 | 2U → G-05 / U 8-9
3 | TR-3 | 11:30 | 8 | Loose storage/backup/tape | W3 | candcex300ecs1d2.aranac.com | J5DBTZ3 | 1 | 2U → G-05 / U 10-11
3 | TR-3 | 11:30 | 9 | Loose storage/backup/tape | W3 | candcex300ecs1d3.aranac.com | B6DBTZ3 | 1 | 2U → G-05 / U 12-13
3 | TR-3 | 11:30 | 10 | Loose storage/backup/tape | W3 | candcex300ecs1d4.aranac.com | 96DBTZ3 | 1 | 2U → G-05 / U 14-15
3 | TR-3 | 11:30 | 11 | Loose storage/backup/tape | W4 | candcex300ecs1d5.aranac.com | 10QLV03 | 1 | 2U → G-04 / U 4-5
3 | TR-3 | 11:30 | 12 | Loose storage/backup/tape | W4 | candcex300ecs1d6.aranac.com | JZPLV03 | 1 | 2U → G-04 / U 6-7
3 | TR-3 | 11:30 | 13 | Loose storage/backup/tape | W4 | candcex300ecs1d7.aranac.com | HZPLV03 | 1 | 2U → G-04 / U 8-9
3 | TR-3 | 11:30 | 14 | Loose storage/backup/tape | W4 | candcex300ecs1d8.aranac.com | 30QLV03 | 1 | 2U → G-04 / U 10-11
3 | TR-3 | 11:30 | 15 | Loose server | M4 | UATWEB-OTP | WZP22190GCS | 0.5 | 1U → D-14 / U 20
3 | TR-3 | 11:30 |  | TRUCK TOTAL |  |  |  | 44.75 | of 45 boxes
3 | TR-3.1 | 12:00 | 1 | Loose storage/backup/tape | W4 | candcex300ecs1d9.aranac.com | FZPLV03 | 1 | 2U → G-04 / U 12-13
3 | TR-3.1 | 12:00 | 2 | Loose storage/backup/tape | W4 | candcex300ecs2d1.aranac.com | 20QLV03 | 1 | 2U → G-04 / U 14-15
3 | TR-3.1 | 12:00 | 3 | Loose storage/backup/tape | W4 | candcex300ecs2d10.aranac.com | GZPLV03 | 1 | 2U → G-04 / U 16-17
3 | TR-3.1 | 12:00 | 4 | Loose storage/backup/tape | W4 | candcex300ecs2d2.aranac.com | DZPLV03 | 1 | 2U → G-04 / U 18-19
3 | TR-3.1 | 12:00 | 5 | Loose storage/backup/tape | W4 | candcex300ecs2d3.aranac.com | BWTLV03 | 1 | 2U → G-04 / U 20-21
3 | TR-3.1 | 12:00 | 6 | Loose storage/backup/tape | W4 | candcex300ecs2d4.aranac.com | 7HLLV03 | 1 | 2U → G-04 / U 22-23
3 | TR-3.1 | 12:00 | 7 | Loose storage/backup/tape | W4 | candcex300ecs2d5.aranac.com | 9WTLV03 | 1 | 2U → G-04 / U 24-25
3 | TR-3.1 | 12:00 | 8 | Loose storage/backup/tape | W5 | candcex300ecs2d6.aranac.com | B0QLV03 | 1 | 2U → G-03 / U 4-5
3 | TR-3.1 | 12:00 | 9 | Loose storage/backup/tape | W5 | candcex300ecs2d7.aranac.com | 8XPLV03 | 1 | 2U → G-03 / U 6-7
3 | TR-3.1 | 12:00 | 10 | Loose storage/backup/tape | W5 | candcex300ecs2d8.aranac.com | 3ZPLV03 | 1 | 2U → G-03 / U 8-9
3 | TR-3.1 | 12:00 | 11 | Loose storage/backup/tape | W5 | candcex300ecs2d9.aranac.com | DYPLV03 | 1 | 2U → G-03 / U 10-11
3 | TR-3.1 | 12:00 | 12 | Loose storage/backup/tape | W5 | candcex500ecs3d1.aranac.com | JYPLV03 | 1 | 2U → G-03 / U 12-13
3 | TR-3.1 | 12:00 | 13 | Loose storage/backup/tape | W5 | candcex500ecs3d2.aranac.com | 5WTLV03 | 1 | 2U → G-03 / U 14-15
3 | TR-3.1 | 12:00 | 14 | Loose storage/backup/tape | W5 | candcex500ecs3d3.aranac.com | 3WTLV03 | 1 | 2U → G-03 / U 16-17
3 | TR-3.1 | 12:00 | 15 | Loose storage/backup/tape | W5 | candcex500ecs3d4.aranac.com | 7WTLV03 | 1 | 2U → G-03 / U 18-19
3 | TR-3.1 | 12:00 | 16 | Loose storage/backup/tape | W5 | candcex500ecs3d5.aranac.com | 4WTLV03 | 1 | 2U → G-03 / U 20-21
3 | TR-3.1 | 12:00 | 17 | Loose storage/backup/tape | W5 | candcex500ecs3d6.aranac.com | HJLLV03 | 1 | 2U → G-03 / U 22-23
3 | TR-3.1 | 12:00 | 18 | Loose storage/backup/tape | W7 | Not Applicable | FCNCA191702270 | 2 | 4U → H-05 / U 8-11
3 | TR-3.1 | 12:00 | 19 | Loose storage/backup/tape | W7 | Not Applicable | FCNCA191800100 | 2 | 4U → H-05 / U 12-15
3 | TR-3.1 | 12:00 | 20 | Loose storage/backup/tape | W7 | Not Applicable | FCNCA191800042 | 2 | 4U → H-05 / U 16-19
3 | TR-3.1 | 12:00 | 21 | Loose storage/backup/tape | W7 | Not Applicable | FCNCA191800014 | 2 | 4U → H-05 / U 20-23
3 | TR-3.1 | 12:00 | 22 | Loose server | G3 | CAN-DC-CELL7 | FNHTN24 | 1 | 2U → I-06 / U 22-23
3 | TR-3.1 | 12:00 | 23 | Loose server | G3 | Server-8284-22A-SN84B6FAW | 84B6FAW | 1 | 2U → OOS / U
3 | TR-3.1 | 12:00 | 24 | Loose server | G6 | DCDBSYNFRS | 1PG5MP2 | 1 | 2U → K-08 / U 8-9
3 | TR-3.1 | 12:00 | 25 | Loose server | N1 | drswift02 | 847C10W | 2 | 4U → Scrap / U
3 | TR-3.1 | 12:00 | 26 | Loose network/security | G3 | Not Applicable | 697640 | 0.5 | 1U → D-10 / U
3 | TR-3.1 | 12:00 | 27 | Loose network/security | H2 | DC-H2-P2 CLOUDSTATION | CS801400000012 | 1 | 2U → F-07 / U 4-5
3 | TR-3.1 | 12:00 | 28 | Loose network/security | H2 | DC-H2-P2 INSIGHTS | IN801400000014 | 1 | 2U → E-07 / U 4-5
3 | TR-3.1 | 12:00 | 29 | Loose network/security | H3 | DC-H3-H4-WAN-L2-SW | WS3719420161 | 0.5 | 1U → E-08 / U 27
3 | TR-3.1 | 12:00 | 30 | Loose network/security | H3 | DC-H3-KS-RTR-2 | FOX1740GAHU | 1 | 2U → F-08 / U 19-20
3 | TR-3.1 | 12:00 | 31 | Loose network/security | H3 | DC-L3-WAN-AGG | VF3715360067 | 0.5 | 1U → E-08 / U 28
3 | TR-3.1 | 12:00 | 32 | Loose network/security | H3 | DC-H3-GM-RTR-2 | FXS1741Q27Z | 3 | 6U → F-08 / U 13-18
3 | TR-3.1 | 12:00 | 33 | Loose network/security | H3 | DCINTADC02.aranac.com F5-BIG-LTM-15800 | f5-pyrs-qtdq | 0.5 | 1U → F-09 / U 24
3 | TR-3.1 | 12:00 | 34 | Loose network/security | H3 | DC-H3-CORE-RTR-2 | FXS2436Q0R1 | 5 | 9U → F-08 / U 4-12
3 | TR-3.1 | 12:00 | 35 | Loose network/security | H3 | DC-H3-P2 CLOUDPORT GATEWAY 2 | 801400000008 | 1 | 2U → F-07 / U 6-7
3 | TR-3.1 | 12:00 | 36 | Loose network/security | H4 | DC-H3-H4-WAN-L2-SW | WS3719420123 | 0.5 | 1U → F-08 / U 23
3 | TR-3.1 | 12:00 | 37 | Loose network/security | H4 | DC-L3-WAN-AGG | VF3715360265 | 0.5 | 1U → F-08 / U 24
3 | TR-3.1 | 12:00 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
3 | TR-3.2 | 12:30 | 1 | Loose network/security | H4 | DC-H4-KS-RTR-1 | FOX1740GAHX | 1 | 2U → E-08 / U 22-23
3 | TR-3.2 | 12:30 | 2 | Loose network/security | H4 | DC-H4-GM-RTR-1 | FXS1739Q2UK | 5 | 9U → E-08 / U 13-21
3 | TR-3.2 | 12:30 | 3 | Loose network/security | H4 | DCINTADC01.aranac.com F5-BIG-LTM-15800 | F5-RBYB-IWXP | 0.5 | 1U → E-09 / U 24
3 | TR-3.2 | 12:30 | 4 | Loose network/security | H4 | DC-H4-P2 CLOUDPORT GATEWAY 1 | 801400000007 | 1 | 2U → E-08 / U 24-25
3 | TR-3.2 | 12:30 | 5 | Loose network/security | H4 | DC-H4-CORE-RTR-1 | FXS2545Q0Z1 | 5 | 9U → E-08 / U 4-12
3 | TR-3.2 | 12:30 | 6 | Loose network/security | I1 | DC-I1-P1 CLOUDPORT GATEWAY 2 | 501400000011 | 0.5 | 1U → F-07 / U 8
3 | TR-3.2 | 12:30 | 7 | Loose network/security | I2 | DC-FORTI-FW-1 | FG3K2D3Z16800261 | 1 | 2U → E-09 / U 22-23
3 | TR-3.2 | 12:30 | 8 | Loose network/security | I2 | DC-I2-FTD-CHASSIS-1 | JMX2302L035 | 2 | 3U → E-09 / U 18-20
3 | TR-3.2 | 12:30 | 9 | Loose network/security | I2 | DC-I2-N9508-CORE-SW1 | FGE22334V45 | 7 | 13U → E-09 / U 4-16
3 | TR-3.2 | 12:30 | 10 | Loose network/security | I3 | DC-FORTI-FW-2 | FG3K2D3Z16800276 | 1 | 2U → F-09 / U 22-23
3 | TR-3.2 | 12:30 | 11 | Loose network/security | I3 | DC-I3-FMC-PRIMARY | WMP2411007K | 0.5 | 1U → E-06 / U 13
3 | TR-3.2 | 12:30 | 12 | Loose network/security | I3 | DC-I2-FTD-CHASSIS-2 | JMX2417L00R | 2 | 3U → F-09 / U 18-20
3 | TR-3.2 | 12:30 | 13 | Loose network/security | I3 | DC-I3-N9508-CORE-SW2 | FGE22334V4X | 7 | 13U → F-09 / U 4-16
3 | TR-3.2 | 12:30 | 14 | Loose network/security | J6 | DC-J6-P1 CLOUDSTATION | CS401300000002 | 0.5 | 1U → E-07 / U 6
3 | TR-3.2 | 12:30 | 15 | Loose network/security | J6 | DC-J6-P1 INSIGHTS | IN401300000002 | 1 | 2U → F-05 / U 4-5
3 | TR-3.2 | 12:30 | 16 | Loose network/security | N3 | DCDMZADC02 | f5-ctyi-hccy | 0.5 | 1U → F-11 / U 20
3 | TR-3.2 | 12:30 | 17 | Loose network/security | N3 | CB-DC-CP-EVENT-SRV | HWXRT04 | 1 | 2U → E-11 / U 11-12
3 | TR-3.2 | 12:30 | 18 | Loose network/security | N3 | Checkpoint 29100 CB-DC-CP-DMZ-FW2 | LR202312007390 | 1 | 2U → F-11 / U 10-11
3 | TR-3.2 | 12:30 | 19 | Loose network/security | N3 | CB-DC-CP-INTERNET-PROXY-FW2 | LR202402009851 | 1 | 2U → F-12 / U 11-12
3 | TR-3.2 | 12:30 | 20 | Loose network/security | N3 | DC-N3-AGGEGATION-N9K-SW-2 | FDO28130W1X | 0.5 | 1U → F-12 / U 23
3 | TR-3.2 | 12:30 | 21 | Loose network/security | N3 | Cisco Nexus 3548-X DC-N3-DMZ-PXY-WAN-SW-2Y | FOC2132R03J | 0.5 | 1U → F-12 / U 24
3 | TR-3.2 | 12:30 | 22 | Loose network/security | N3 | DC-N3-INTERNET-PROXY-RTR2 | BJ606 | 2 | 3U → F-12 / U 4-6
3 | TR-3.2 | 12:30 | 23 | Loose network/security | N3 | DC-N4-N9K-PROXY-CORE-SW-1 | FLM26160862 | 0.5 | 1U → TBD / U 32
3 | TR-3.2 | 12:30 | 24 | Loose network/security | N3 | Not Applicable | FG4H0FT923914098 | 0.5 | 1U → E-11 / U 21
3 | TR-3.2 | 12:30 | 25 | Loose network/security | N3 | DC-N3-CLOUD-WAN-SW-2 | FDO28130VX8 | 0.5 | 1U → TBD / U 32
3 | TR-3.2 | 12:30 | 26 | Loose network/security | N3 | Not Applicable | LR202402009861 | 1 | 2U → F-12 / U 9-10
3 | TR-3.2 | 12:30 | 27 | Loose network/security | N3 | DC-N3-CLOUD-RTR-2 | FGL2139814C | 1 | 2U → F-12 / U 13-14
3 | TR-3.2 | 12:30 |  | TRUCK TOTAL |  |  |  | 45 | of 45 boxes
3 | TR-3.3 | 13:00 | 1 | Loose network/security | N4 | DCDMZADC01 | f5-mucx-joiu | 0.5 | 1U → E-11 / U 33
3 | TR-3.3 | 13:00 | 2 | Loose network/security | N4 | CB-DC-CP-MGMT-SRV | 8xxRT04 | 1 | 2U → F-11 / U 12-13
3 | TR-3.3 | 13:00 | 3 | Loose network/security | N4 | Checkpoint 29100 CB-DC-CP-DMZ-FW1 | LR202401010219 | 1 | 2U → E-11 / U 13-14
3 | TR-3.3 | 13:00 | 4 | Loose network/security | N4 | CB-DC-CP-INTERNET-PROXY-FW1 | LR202402009885 | 1 | 2U → E-12 / U 10-11
3 | TR-3.3 | 13:00 | 5 | Loose network/security | N4 | DC-N4-CLOUD-WAN-SW-1 | FDO28140BUE | 0.5 | 1U → H-11 / U 23
3 | TR-3.3 | 13:00 | 6 | Loose network/security | N4 | DC-N4-INTERNET-PROXY-RTR1 | CG094 | 2 | 4U → E-12 / U 4-7
3 | TR-3.3 | 13:00 | 7 | Loose network/security | N4 | Cisco Nexus 3548-X DC-N4-DMZ-PXY-WAN-SW-1 | FOC2132R03L | 0.5 | 1U → E-12 / U 23
3 | TR-3.3 | 13:00 | 8 | Loose network/security | N4 | DC-N3-N9K-PROXY-CORE-SW-2 | FLM261600BU | 0.5 | 1U → H-11 / U 24
3 | TR-3.3 | 13:00 | 9 | Loose network/security | N4 | Not Applicable | FG4H0FT923913688 | 0.5 | 1U → F-11 / U 21
3 | TR-3.3 | 13:00 | 10 | Loose network/security | N4 | DC-N4-AGGREGATION-N9K-SW-1 | FDO281312YJ | 0.5 | 1U → H-10 / U 23
3 | TR-3.3 | 13:00 | 11 | Loose network/security | N4 | CB-DC-CP-CLOUD-FW1 | LR202402004472 | 1 | 2U → E-12 / U 12-13
3 | TR-3.3 | 13:00 | 12 | Loose network/security | N4 | DC-N4-CLOUD-RTR-1 | FGL2139814D | 1 | 2U → E-12 / U 14-15
3 | TR-3.3 | 13:00 | 13 | Loose network/security | O1 | DC-O1-INTERNET-DMZ-RTR-01 | FLM281510M1 | 0.5 | 1U → E-11 / U 22
3 | TR-3.3 | 13:00 | 14 | Loose network/security | O1 | DC-O1-INTERNET-DMZ-RTR-02 | FLM281510M0 | 0.5 | 1U → F-11 / U 22
3 | TR-3.3 | 13:00 | 15 | Loose network/security | O1 | DC-O1-INTERNET-JPR-L3 | VF3715360003 | 0.5 | 1U → E-11 / U 34
3 | TR-3.3 | 13:00 | 16 | Loose network/security | O1 | DC-O1-INTERNET-JPR-L3 | VF3715360016 | 0.5 | 1U → F-11 / U 33
3 | TR-3.3 | 13:00 | 17 | Loose network/security | O1 | DCCANARBOR | CG24148159LA | 1 | 2U → E-11 / U 15-16
3 | TR-3.3 | 13:00 | 18 | Loose network/security | O6 | Not Applicable | 1901312380 | 0.5 | 1U → F-11 / U 23
3 | TR-3.3 | 13:00 | 19 | Loose network/security | O6 | DCCSWPSSL01 | 3377DT33C | 1 | 2U → E-11 / U 17-18
3 | TR-3.3 | 13:00 | 20 | Loose network/security | O6 | DCCSWPSSL02 | 338BTT3CT | 1 | 2U → F-11 / U 16-17
3 | TR-3.3 | 13:00 | 21 | Loose network/security | O6 | DCCSWNTB01 | 23720020148 | 0.5 | 1U → E-11 / U 7
3 | TR-3.3 | 13:00 | 22 | Loose network/security | O6 | DCCSWNTB02 | 23720020149 | 0.5 | 1U → F-11 / U 24
3 | TR-3.3 | 13:00 | 23 | Loose network/security | O6 | DCCSWPAPT01 | SR 025409001255 | 1 | 2U → E-11 / U 19-20
3 | TR-3.3 | 13:00 | 24 | Loose network/security | O6 | DCCSWPAPT02 | SR 025409001274 | 1 | 2U → F-11 / U 18-19
3 | TR-3.3 | 13:00 | 25 | Loose network/security | W3 | Not Applicable | 8RM4SR3 | 0.5 | 1U → G-05 / U 23
3 | TR-3.3 | 13:00 | 26 | Loose network/security | W3 | Not Applicable | 8RF8SR3 | 0.5 | 1U → G-05 / U 24
3 | TR-3.3 | 13:00 | 27 | Loose network/security | W3 | Not Applicable | 8RF6SR3 | 0.5 | 1U → G-05 / U 25
3 | TR-3.3 | 13:00 | 28 | Loose network/security | W3 | Not Applicable | 8RD6SR3 | 0.5 | 1U → G-05 / U 26
3 | TR-3.3 | 13:00 | 29 | Loose network/security | W3 | Not Applicable | W3-KVM Switch | 0.5 | 1U → N/W / U
3 | TR-3.3 | 13:00 | 30 | Loose network/security | W4 | Not Applicable | 9435SR3 | 0.5 | 1U → G-04 / U 26
3 | TR-3.3 | 13:00 | 31 | Loose network/security | W4 | Not Applicable | 9434SR3 | 0.5 | 1U → G-04 / U 27
3 | TR-3.3 | 13:00 | 32 | Loose network/security | W4 | Not Applicable | 30YB9Z2 | 0.5 | 1U → G-04 / U 28
3 | TR-3.3 | 13:00 | 33 | Loose network/security | W4 | Not Applicable | 30XD9Z2 | 0.5 | 1U → G-04 / U 29
3 | TR-3.3 | 13:00 | 34 | Loose network/security | W4 | Not Applicable | 30YC9Z2 | 0.5 | 1U → G-04 / U 30
3 | TR-3.3 | 13:00 | 35 | Loose network/security | W4 | Not Applicable | 310C9Z2 | 0.5 | 1U → G-04 / U 31
3 | TR-3.3 | 13:00 | 36 | Loose network/security | W5 | Not Applicable | 25JD9Z2 | 0.5 | 1U → G-03 / U 24
3 | TR-3.3 | 13:00 | 37 | Loose network/security | W5 | Not Applicable | 25CD9Z2 | 0.5 | 1U → G-03 / U 25
3 | TR-3.3 | 13:00 | 38 | Loose network/security | W5 | Not Applicable | 25GC9Z2 | 0.5 | 1U → G-03 / U 26
3 | TR-3.3 | 13:00 | 39 | Loose network/security | W5 | Not Applicable | 25KD9Z2 | 0.5 | 1U → G-03 / U 27
3 | TR-3.3 | 13:00 | 40 | Loose network/security | W7 | Not Applicable | TSBJC2003784 | 0.5 | 1U → H-06 / U 37
3 | TR-3.3 | 13:00 | 41 | Loose network/security | W7 | Not Applicable | TSBJ52004985 | 0.5 | 1U → H-05 / U 35
3 | TR-3.3 | 13:00 |  | TRUCK TOTAL |  |  |  | 27 | of 45 boxes

## Racks for CBS (hidden)
RACKS FOR CBS – TARGET RACK POSITIONS @ STT (from rackmap.xlsx) WITH MOVEMENT BATCH & TRUCK
Columns A–K as supplied in rackmap.xlsx. Columns L–Q are derived from the Scope sheet: how the rack reaches the position, batch/truck, and which devices are planned into it.
Destination Rack @ STT | Current (at STT) | Recommendation | Recommended Rack | Socket Type | Remarks | Requires PDU Change? | Rack Type | Required Power Circuit | Remarks (PDU) | Source Rack | Rack Movement | Rack Ships in Batch | Rack Truck | Devices planned into position (rows) | Device Batches | Rack & PDU Ready at STT (Y/N)
C-08 |  | Lift & Shift | IBM Rack (C1) | Single Phase 63 Amps |  | Yes | OEM | 2+2 | OEM rack - so need to use existing PDU | C1 | Lift & Shift – empty rack | 2 | TR-2 | 8 | 2
J-07 |  | Lift & Shift | Net Rack (X5) | Three Phase 32 Amps |  |  | OLD | 1+1 | New rack - assume STT gives PDU | X5 | Lift & Shift – empty rack | 2 | TR-2 | 7 | 2
N-03 |  | Lift & Shift | GR-A3 | Three Phase 32 Amps |  |  | Migration Rack | 1+1 | Migration racks - assume existing PDUs are available | GR-A3 | Lift & Shift – empty rack | 1 | TR-1.3 | 6 | 1
N-04 |  | Lift & Shift | GR-A4 | Three Phase 32 Amps |  |  | Migration Rack | 1+1 | Migration racks - assume existing PDUs are available | GR-A4 | Lift & Shift – empty rack | 1 | TR-1.3 | 6 | 1
N-02 |  | Lift & Shift | GR-A2 | Single Phase 63 Amps |  | Yes | Migration Rack | 2+2 | Migration racks - assume existing PDUs are available | GR-A2 | Lift & Shift – empty rack | 1 | TR-1.3 | 5 | 1
N-01 |  | Lift & Shift | GR-A1 | Three Phase 32 Amps |  |  | Migration Rack | 1+1 | Migration racks - assume existing PDUs are available | GR-A1 | Lift & Shift – empty rack | 1 | TR-1.3 | 4 | 1
G-13 |  | Lift & Shift | IBM rack (A1) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | A1 | Lift & Shift – OEM loaded rack | 2 | TR-2.1 | 8 | 2
G-14 |  | Lift & Shift | IBM rack (A2) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | A2 | Lift & Shift – OEM loaded rack | 2 | TR-2.1 | 5 | 2
D-13 |  | Lift & Shift | IBM Rack (A5) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | A5 | Lift & Shift – OEM loaded rack | 2 | TR-2.2 | 6 | 2
C-12 |  | Lift & Shift | IBM Rack (A6) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | A6 | Lift & Shift – OEM loaded rack | 2 | TR-2.2 | 7 | 2
G-15 |  | Lift & Shift | IBM rack (C2) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | C2 | Lift & Shift – OEM loaded rack | 2 | TR-2.3 | 8 | 2
H-14 |  | Lift & Shift | IBM rack (C3) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | C3 | Lift & Shift – OEM loaded rack | 1 | TR-1 | 6 | 1, 2
H-13 |  | Lift & Shift | IBM rack (C4) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | C4 | Lift & Shift – OEM loaded rack | 2 | TR-2.3 | 6 | 2
G-17 |  | Lift & Shift | IBM rack (C5) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | C5 | Lift & Shift – OEM loaded rack | 2 | TR-2.4 | 8 | 2
H-17 |  | Lift & Shift | IBM rack (C6) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | C6 | Lift & Shift – OEM loaded rack | 2 | TR-2.4 | 8 | 2
H-15 |  | Lift & Shift | IBM rack (D1) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | D1 | Lift & Shift – OEM loaded rack | 2 | TR-2.5 | 8 | 2
D-09 |  | Lift & Shift | IBM Rack (D3) | Single Phase 63 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | D3 | Lift & Shift – OEM loaded rack | 2 | TR-2.6 | 3 | 2
D-04 |  | Lift & Shift | WQ Rack (D5) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | D5 | Lift & Shift – empty rack | 1 | TR-1 | 3 | 1
C-07 |  | Lift & Shift | IBM Rack (D6) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU | D6 | Lift & Shift – OEM loaded rack | 2 | TR-2.6 | 8 | 2
H-08 |  | Lift & Shift | IBM rack (K3) | Single Phase 32 Amps |  |  | OEM | 2+2 | OEM rack - so need to use existing PDU | K3 | Lift & Shift – OEM loaded rack | 2 | TR-2.8 | 8 | 2
G-09 |  | Lift & Shift | IBM rack (K2) |  |  |  | OEM | 3+3 | Single Phase 32 A, 3+3 as per installed, need to use existing PDU | K2 | Lift & Shift – OEM loaded rack | 2 | TR-2.8 | 6 | 2
H-09 |  | Lift & Shift | IBM rack (K1) | Single Phase 32 Amps | Single Phase 32 A, 2+2 as per installed, need to use existing PDU |  | OEM | 3+3 | Single Phase 32 A, 2+2 as per installed, need to use existing PDU | K1 | Lift & Shift – OEM loaded rack | 2 | TR-2.7 | 5 | 2
G-08 |  | Lift & Shift | IBM rack (K4) |  |  |  | OEM | 3+3 | Single Phase 32 A, 3+3 as per installed, need to use existing PDU | K4 | Lift & Shift – OEM loaded rack | 2 | TR-2.9 | 7 | 2
G-20 |  | Lift & Shift | IBM rack (K6) |  |  |  | OEM | 1+1 | Single Phase 32 A, 2+2 as per installed, need to use existing PDU | K6 | Lift & Shift – OEM loaded rack | 2 | TR-2.10 | 6 | 2
C-01 |  | Lift & Shift | IBM LTO8 tape library (L1) |  |  |  | OEM | 1+1 | Single Phase 32 A, 1+1 as per installed, need to use existing PDU | L1 | Lift & Shift – OEM loaded rack | 1 | TR-1.1 | 1 | 1
C-02 |  | Lift & Shift | IBM LTO8 tape library (L2) |  |  |  | OEM | 1+1 | Single Phase 32 A, 1+1 as per installed, need to use existing PDU | L2 | Lift & Shift – OEM loaded rack | 1 | TR-1.2 | 1 | 1
C-03 |  | Lift & Shift | IBM LTO8 tape library (L3) |  |  |  | OEM | 1+1 | Single Phase 32 A, 1+1 as per installed, need to use existing PDU | L3 | Lift & Shift – OEM loaded rack | 1 | TR-1.2 | 1 | 1
H-19 |  | Lift & Shift | IBM rack (L5) |  |  |  | OEM | 1+1 | Single Phase 32 A, 2+2 as per installed, need to use existing PDU | L5 | Lift & Shift – OEM loaded rack | 2 | TR-2.10 | 5 | 2
G-05 |  | Lift & Shift | Dell Rack (W3) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU | W3 | Lift & Shift – empty rack | 3 | TR-3 | 10 | 3
G-04 |  | Lift & Shift | Dell Rack (W4) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU | W4 | Lift & Shift – empty rack | 3 | TR-3 | 17 | 3
G-03 |  | Lift & Shift | Dell Rack (W5) | Single Phase 63 Amps |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU | W5 | Lift & Shift – empty rack | 3 | TR-3 | 14 | 3
H-06 |  | Lift & Shift | Dell Rack (W6) |  |  |  | OEM | 1+1 | OEM rack - so need to use existing PDU | W6 | Lift & Shift – empty rack | 2 | TR-2 | 10 | 2, 3
H-05 | H-05 | Migrated | WQ Rack (AF2) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AF2 | Already at STT (migrated) | — | — | 5 | 3
C-05 | C-05 | Migrated | WQ Rack (AA2) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AA2 | Already at STT (migrated) | — | — | 3 | 2
C-14 | C-14 | Migrated | WQ Rack (AB2) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AB2 | Already at STT (migrated) | — | — | 2 | 2
D-14 | D-14 | Migrated | WQ Rack (AD2) | Three Phase 32 Amps | Shift the rack from D-20. (The existing rack was moved to L-13 ) |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AD2 | Already at STT (migrated) | — | — | 6 | 2, 3
D-06 | D-06 | Migrated | WQ Rack (AC6) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AC6 | Already at STT (migrated) | — | — | 12 | 2
H-02 | H-02 | Migrated | WQ Rack (AE4) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AE4 | Already at STT (migrated) | — | — | 2 | 2
I-06 | I-06 | Migrated | Net Rack (AA5) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AA5 | Already at STT (migrated) | — | — | 2 | 2, 3
K-08 | K-08 | Migrated | WQ rack (M1) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | M1 | Already at STT (migrated) | — | — | 1 | 3
L-01 |  | Shift rack from I-20 | WQ rack (N5) | Three Phase 32 Amps | Active devices present. The rack N5 will be vacated in future waves |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | N5 | Rack shift at STT: Shift rack from I-20 | — | — | 3 | 2
H-01 | H-01 | Migrated | WQ Rack (AE3) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AE3 | Already at STT (migrated) | — | — | 5 | 2
L-02 |  | Migrated | WQ rack (AA6) | Three Phase 32 Amps |  |  | OLD | 1+1 | As it says old rack, need to use existing PDU. Please recheck before dismantling | AA6 | Already at STT (migrated) | — | — | 2 | 2
J-08 |  | Move rack from J-09 | Net Rack (X7) | Three Phase 32 Amps | Active deivces present. The rack X7 will be vacated in future waves |  | OLD | 1+1 | In other list says new rack, please verify | X7 | Rack shift at STT: Move rack from J-09 | — | — | 2 | 2
J-05 |  | Move rack from J-06 | Net Rack (U2) | Three Phase 32 Amps | Active devices present. The rack U2 will be vacated in future waves |  | OLD | 1+1 | In other list says new rack, please verify | U2 | Rack shift at STT: Move rack from J-06 | — | — | 12 | 2
I-08 | I-08 | Migrated | Net Rack (AB4) | Three Phase 32 Amps |  |  | OLD | 1+1 | In other list says new rack, please verify | AB4 | Already at STT (migrated) | — | — | 7 | 2
I-11 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU, they installed 1+1 3ph & 1+1 1 ph |  | New rack at STT | — | — | 1 | 2
G-10 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 5 | 2
E-16 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
F-01 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 1
G-11 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 4 | 1, 2
L-11 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU, they installed 1+1 3ph & 1+1 1 ph |  | New rack at STT | — | — | 2 | 1, 2
D-10 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 2 | 2, 3
H-10 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 6 | 1, 2, 3
D-11 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
H-11 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 6 | 1, 2, 3
C-11 |  | Lift & Shift | IBM Rack (D2) | NA |  |  | OEM | 2+2 | OEM rack, single phase 63A 2+2 installed | D2 | Lift & Shift – OEM loaded rack | 2 | TR-2.5 | 5 | 2
A-10 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 4 | 2
B-10 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 4 | 2
F-15 |  | Lift & Shift | IBM Rack (A4) | Three Phase 32 Amps |  |  | OEM | 1+1 | OEM rack, 3 ph 32 A socket installed, need to use existing PDU | A4 | Lift & Shift – empty rack | 1 | TR-1.4 | 1 | 2
E-02 |  | New rack |  | Single Phase 63 Amps |  |  | OLD | 1+1 | OEM rack, single phase 63A 1+1 installed |  | New rack at STT | — | — | 1 | 2
F-07 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 3 | 3
E-07 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 2 | 3
E-08 |  | New rack |  | NA |  |  | New Rack | 2+2 | 3ph 1+1 and 1 ph 2+2 installed, 3Ph 1+1 PDU to be arranged by STT |  | New rack at STT | — | — | 6 | 3
F-08 |  | New rack |  | NA |  |  | New Rack | 2+2 | 3ph 1+1 and 1 ph 2+2 installed, 3Ph 1+1 PDU to be arranged by STT |  | New rack at STT | — | — | 5 | 3
F-09 |  | New rack |  | NA |  |  | New Rack | 4+4 | 3ph 1+1 and 1 ph 4+4 installed, 3Ph 1+1 PDU to be arranged by STT |  | New rack at STT | — | — | 4 | 3
E-09 |  | New rack |  | NA |  |  | New Rack | 4+4 | 3ph 1+1 and 1 ph 4+4 installed, 3Ph 1+1 PDU to be arranged by STT |  | New rack at STT | — | — | 4 | 3
E-06 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 3
F-05 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 3
A-08 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
A-09 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
I-10 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
F-16 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
E-01 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
E-11 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 10 | 3
F-11 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 10 | 3
F-12 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 6 | 3
E-12 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 5 | 3
E-05 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 2 | 2
F-03 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 2
L-10 |  | New rack |  | Three Phase 32 Amps |  |  | New Rack | 1+1 | New rack - assume STT gives PDU |  | New rack at STT | — | — | 1 | 1

## Rack_Movement_Plan (hidden)
RACK MOVEMENT PLAN – DISPOSITION OF EVERY SOURCE RACK
Source Rack | Destination @ STT | Rackmap Recommendation | Recommended Rack | Rack Type | Inventory Rows | Rows Travelling in Rack | Rows Unracked | Rack Disposition | Rack Ships in Batch | Rack Truck | Earliest Batch needing this position | Check | Target Position Ready (Y/N) | Rack Received (Y/N)
C1 | C-08 | Lift & Shift | IBM Rack (C1) | OEM | 2 | 0 | 2 | Moves – empty (after devices unracked) | 2 | TR-2 | 2 | OK
X5 | J-07 | Lift & Shift | Net Rack (X5) | OLD | 0 | 0 | 0 | Moves – empty (after devices unracked) | 2 | TR-2 | 2 | OK
GR-A3 | N-03 | Lift & Shift | GR-A3 | Migration Rack | 7 | 0 | 7 | Moves – empty (after devices unracked) | 1 | TR-1.3 | 1 | OK
GR-A4 | N-04 | Lift & Shift | GR-A4 | Migration Rack | 6 | 0 | 6 | Moves – empty (after devices unracked) | 1 | TR-1.3 | 1 | OK
GR-A2 | N-02 | Lift & Shift | GR-A2 | Migration Rack | 6 | 0 | 6 | Moves – empty (after devices unracked) | 1 | TR-1.3 | 1 | OK
GR-A1 | N-01 | Lift & Shift | GR-A1 | Migration Rack | 6 | 0 | 6 | Moves – empty (after devices unracked) | 1 | TR-1.3 | 1 | OK
A1 | G-13 | Lift & Shift | IBM rack (A1) | OEM | 10 | 10 | 0 | Moves – OEM loaded | 2 | TR-2.1 |  | OK
A2 | G-14 | Lift & Shift | IBM rack (A2) | OEM | 8 | 8 | 0 | Moves – OEM loaded | 2 | TR-2.1 |  | OK
A5 | D-13 | Lift & Shift | IBM Rack (A5) | OEM | 6 | 6 | 0 | Moves – OEM loaded | 2 | TR-2.2 |  | OK
A6 | C-12 | Lift & Shift | IBM Rack (A6) | OEM | 7 | 7 | 0 | Moves – OEM loaded | 2 | TR-2.2 |  | OK
C2 | G-15 | Lift & Shift | IBM rack (C2) | OEM | 10 | 10 | 0 | Moves – OEM loaded | 2 | TR-2.3 |  | OK
C3 | H-14 | Lift & Shift | IBM rack (C3) | OEM | 8 | 8 | 0 | Moves – OEM loaded | 1 | TR-1 | 2 | OK
C4 | H-13 | Lift & Shift | IBM rack (C4) | OEM | 8 | 8 | 0 | Moves – OEM loaded | 2 | TR-2.3 |  | OK
C5 | G-17 | Lift & Shift | IBM rack (C5) | OEM | 9 | 9 | 0 | Moves – OEM loaded | 2 | TR-2.4 |  | OK
C6 | H-17 | Lift & Shift | IBM rack (C6) | OEM | 10 | 10 | 0 | Moves – OEM loaded | 2 | TR-2.4 |  | OK
D1 | H-15 | Lift & Shift | IBM rack (D1) | OEM | 10 | 10 | 0 | Moves – OEM loaded | 2 | TR-2.5 |  | OK
D3 | D-09 | Lift & Shift | IBM Rack (D3) | OEM | 3 | 2 | 1 | Moves – OEM loaded | 2 | TR-2.6 |  | OK
D5 | D-04 | Lift & Shift | WQ Rack (D5) | OLD | 3 | 0 | 3 | Moves – empty (after devices unracked) | 1 | TR-1 |  | OK
D6 | C-07 | Lift & Shift | IBM Rack (D6) | OEM | 8 | 8 | 0 | Moves – OEM loaded | 2 | TR-2.6 |  | OK
K3 | H-08 | Lift & Shift | IBM rack (K3) | OEM | 7 | 7 | 0 | Moves – OEM loaded | 2 | TR-2.8 | 2 | OK
K2 | G-09 | Lift & Shift | IBM rack (K2) | OEM | 7 | 7 | 0 | Moves – OEM loaded | 2 | TR-2.8 |  | OK
K1 | H-09 | Lift & Shift | IBM rack (K1) | OEM | 7 | 7 | 0 | Moves – OEM loaded | 2 | TR-2.7 | 2 | OK
K4 | G-08 | Lift & Shift | IBM rack (K4) | OEM | 8 | 8 | 0 | Moves – OEM loaded | 2 | TR-2.9 | 2 | OK
K6 | G-20 | Lift & Shift | IBM rack (K6) | OEM | 7 | 5 | 2 | Moves – OEM loaded | 2 | TR-2.10 |  | OK
L1 | C-01 | Lift & Shift | IBM LTO8 tape library (L1) | OEM | 1 | 1 | 0 | Moves – OEM loaded | 1 | TR-1.1 |  | OK
L2 | C-02 | Lift & Shift | IBM LTO8 tape library (L2) | OEM | 1 | 1 | 0 | Moves – OEM loaded | 1 | TR-1.2 |  | OK
L3 | C-03 | Lift & Shift | IBM LTO8 tape library (L3) | OEM | 1 | 1 | 0 | Moves – OEM loaded | 1 | TR-1.2 |  | OK
L5 | H-19 | Lift & Shift | IBM rack (L5) | OEM | 5 | 4 | 1 | Moves – OEM loaded | 2 | TR-2.10 |  | OK
W3 | G-05 | Lift & Shift | Dell Rack (W3) | OEM | 11 | 0 | 11 | Moves – empty (after devices unracked) | 3 | TR-3 |  | OK
W4 | G-04 | Lift & Shift | Dell Rack (W4) | OEM | 17 | 0 | 17 | Moves – empty (after devices unracked) | 3 | TR-3 |  | OK
W5 | G-03 | Lift & Shift | Dell Rack (W5) | OEM | 14 | 0 | 14 | Moves – empty (after devices unracked) | 3 | TR-3 |  | OK
W6 | H-06 | Lift & Shift | Dell Rack (W6) | OEM | 9 | 0 | 9 | Moves – empty (after devices unracked) | 2 | TR-2 | 3 | OK
D2 | C-11 | Lift & Shift | IBM Rack (D2) | OEM | 5 | 5 | 0 | Moves – OEM loaded | 2 | TR-2.5 |  | OK
A4 | F-15 | Lift & Shift | IBM Rack (A4) | OEM | 1 | 0 | 1 | Moves – empty (after devices unracked) | 1 | TR-1.4 | 2 | OK
F7 | F-15 | Not in rackmap |  |  | 1 | 1 | 0 | Moves – OEM loaded | 2 | TR-2.7 |  | CHECK – rack marked loaded in Scope but not 'Lift & Shift' in rackmap; device targets: F-15
K5 | G-08 | Not in rackmap |  |  | 4 | 4 | 0 | Moves – OEM loaded | 2 | TR-2.9 |  | CHECK – rack marked loaded in Scope but not 'Lift & Shift' in rackmap; device targets: H-08, G-08, G-11
A3 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 2 | — |  | OK
B2 | — | Not in rackmap (rack stays at ITI) |  |  | 9 | 0 | 9 | Not moving – all devices unracked | 2 | — |  | OK
E2 | — | Not in rackmap (rack stays at ITI) |  |  | 2 | 0 | 2 | Not moving – all devices unracked | 2 | — |  | OK
E3 | — | Not in rackmap (rack stays at ITI) |  |  | 3 | 0 | 3 | Not moving – all devices unracked | 2 | — |  | OK
F2 | — | Not in rackmap (rack stays at ITI) |  |  | 2 | 0 | 2 | Not moving – all devices unracked | 2 | — |  | OK
F3 | — | Not in rackmap (rack stays at ITI) |  |  | 7 | 0 | 7 | Not moving – all devices unracked | 2 | — |  | OK
F4 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 2 | — |  | OK
F5 | — | Not in rackmap (rack stays at ITI) |  |  | 5 | 0 | 5 | Not moving – all devices unracked | 2 | — |  | OK
F6 | — | Not in rackmap (rack stays at ITI) |  |  | 5 | 0 | 5 | Not moving – all devices unracked | 2 | — |  | OK
G3 | — | Not in rackmap (rack stays at ITI) |  |  | 3 | 0 | 3 | Not moving – all devices unracked | 3 | — |  | OK
G6 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 3 | — |  | OK
G7 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 2 | — |  | OK
H2 | — | Not in rackmap (rack stays at ITI) |  |  | 2 | 0 | 2 | Not moving – all devices unracked | 3 | — |  | OK
H3 | — | Not in rackmap (rack stays at ITI) |  |  | 7 | 0 | 7 | Not moving – all devices unracked | 3 | — |  | OK
H4 | — | Not in rackmap (rack stays at ITI) |  |  | 7 | 0 | 7 | Not moving – all devices unracked | 3 | — |  | OK
I1 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 3 | — |  | OK
I2 | — | Not in rackmap (rack stays at ITI) |  |  | 3 | 0 | 3 | Not moving – all devices unracked | 3 | — |  | OK
I3 | — | Not in rackmap (rack stays at ITI) |  |  | 4 | 0 | 4 | Not moving – all devices unracked | 3 | — |  | OK
J2 | — | Not in rackmap (rack stays at ITI) |  |  | 9 | 0 | 9 | Not moving – all devices unracked | 2 | — |  | OK
J6 | — | Not in rackmap (rack stays at ITI) |  |  | 2 | 0 | 2 | Not moving – all devices unracked | 3 | — |  | OK
K7 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 2 | — |  | OK
L6 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 2 | — |  | OK
M1 | — | Not in rackmap (rack stays at ITI) |  |  | 11 | 0 | 11 | Not moving – all devices unracked | 2 | — |  | OK
M4 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 3 | — |  | OK
M5 | — | Not in rackmap (rack stays at ITI) |  |  | 2 | 0 | 2 | Not moving – all devices unracked | 2 | — |  | OK
M7 | — | Not in rackmap (rack stays at ITI) |  |  | 7 | 0 | 7 | Not moving – all devices unracked | 2 | — |  | OK
N1 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 3 | — |  | OK
N3 | — | Not in rackmap (rack stays at ITI) |  |  | 12 | 0 | 12 | Not moving – all devices unracked | 3 | — |  | OK
N4 | — | Not in rackmap (rack stays at ITI) |  |  | 12 | 0 | 12 | Not moving – all devices unracked | 3 | — |  | OK
N5 | — | Not in rackmap (rack stays at ITI) |  |  | 14 | 0 | 14 | Not moving – all devices unracked | 2 | — |  | OK
O1 | — | Not in rackmap (rack stays at ITI) |  |  | 5 | 0 | 5 | Not moving – all devices unracked | 3 | — |  | OK
O5 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 2 | — |  | OK
O6 | — | Not in rackmap (rack stays at ITI) |  |  | 7 | 0 | 7 | Not moving – all devices unracked | 3 | — |  | OK
P1 | — | Not in rackmap (rack stays at ITI) |  |  | 2 | 0 | 2 | Not moving – all devices unracked | 2 | — |  | OK
S6 | — | Not in rackmap (rack stays at ITI) |  |  | 3 | 0 | 3 | Not moving – all devices unracked | 2 | — |  | OK
V3 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 3 | — |  | OK
W7 | — | Not in rackmap (rack stays at ITI) |  |  | 6 | 0 | 6 | Not moving – all devices unracked | 3 | — |  | OK
X2 | — | Not in rackmap (rack stays at ITI) |  |  | 1 | 0 | 1 | Not moving – all devices unracked | 2 | — |  | OK

## Target_Rack_Readiness (hidden)
TARGET RACK READINESS – WHERE EACH LOOSE DEVICE WILL BE RACKED
Where each loose (unracked) device will be mounted at STT. OK = rack position ready before the device arrives; RISK = rack for that position arrives in a later batch; CHECK = position TBD / not in rackmap / rack shift at STT – confirm with STT and Bank before GO/NO-GO.
Primary Serial | Hostname | Source Rack | Device Batch | Device Truck | Target Rack | Target U | Rackmap Recommendation | Rack moving into position | Rack Batch | Rack Truck | Result | Confirmed by STT/Bank (Y/N) | Remarks
5ZWGVP3 | Not Applicable | D5 | 1 | TR-1 | D-04 | 9-11 | Lift & Shift – WQ Rack (D5) | D5 | 1 | TR-1 | OK – same batch: rack on TR-1 (mount after rack is fixed)
H4XGVP3 | Not Applicable | D5 | 1 | TR-1 | D-04 | 12-14 | Lift & Shift – WQ Rack (D5) | D5 | 1 | TR-1 | OK – same batch: rack on TR-1 (mount after rack is fixed)
755231F | BLR512B-G7-SW2 | A4 | 1 | TR-1 | F-01 | 4-17 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
786731M | BLRNDC_64BG7_SW1 | GR-A1 | 1 | TR-1.4 | N-03 | 38 | Lift & Shift – GR-A3 | GR-A3 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
786729Z | BLRNDC_64BG7_SW2 | GR-A2 | 1 | TR-1.4 | N-04 | 35 | Lift & Shift – GR-A4 | GR-A4 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
6G0HVP3 | TAPEINV22 | D5 | 1 | TR-1.1 | D-04 | 15-17 | Lift & Shift – WQ Rack (D5) | D5 | 1 | TR-1 | OK – same batch: rack on TR-1 (mount after rack is fixed)
130RH6A | CR1130RH6A | GR-A1 | 1 | TR-1.4 | N-03 | 21 | Lift & Shift – GR-A3 | GR-A3 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78E4Y9C | SANINV379 | GR-A1 | 1 | TR-1.4 | N-03 | 17-16 | Lift & Shift – GR-A3 | GR-A3 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78E4Y8T | SANINV378 | GR-A1 | 1 | TR-1.4 | N-03 | 15-14 | Lift & Shift – GR-A3 | GR-A3 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
3185702 | Not Applicable | GR-A1 | 1 | TR-1.4 | N-03 | 23 | Lift & Shift – GR-A3 | GR-A3 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78E3NKE2 | Not Applicable | GR-A1 | 1 | TR-1.4 | N-03 | 13-12 | Lift & Shift – GR-A3 | GR-A3 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78DA08X | ndrfccdb | GR-A2 | 1 | TR-1.4 | N-04 | 6-3 | Lift & Shift – GR-A4 | GR-A4 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78DA08X | Not Applicable | GR-A2 | 1 | TR-1.4 | N-04 | 10-7 | Lift & Shift – GR-A4 | GR-A4 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78E4Z1B | SANINV382 | GR-A2 | 1 | TR-1.4 | N-04 | 17-16 | Lift & Shift – GR-A4 | GR-A4 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78E4Z1E | SANINV380 | GR-A2 | 1 | TR-1.4 | N-04 | 15-14 | Lift & Shift – GR-A4 | GR-A4 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
78E3NPL | SANINV381 | GR-A2 | 1 | TR-1.4 | N-04 | 13-12 | Lift & Shift – GR-A4 | GR-A4 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
FDO28050YP1 | CB-NDR-P2P-SW | GR-A3 | 1 | TR-1.4 | N-02 | 39 | Lift & Shift – GR-A2 | GR-A2 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
FDO28050YP4 | CB-NDR-P2P-SW | GR-A3 | 1 | TR-1.4 | N-02 | 37 | Lift & Shift – GR-A2 | GR-A2 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
FDO28160D18 | NDR-Cisco-Nexus-SW1 | GR-A3 | 1 | TR-1.4 | L-10 | U4 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO28160237 | NDR-Cisco-Nexus-SW2 | GR-A3 | 1 | TR-1.4 | L-11 | U4 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
2161392000161 | Not Applicable | GR-A3 | 1 | TR-1.4 | N-02 | Not Mounted | Lift & Shift – GR-A2 | GR-A2 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
SY2511A-131200531 / SY2304-131203010 | Not Applicable | GR-A3 | 1 | TR-1.4 | N-02 | Not Mounted | Lift & Shift – GR-A2 | GR-A2 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
CAEZ2226 | Not Applicable | GR-A3 | 1 | TR-1.4 | N-02 | 4-2 | Lift & Shift – GR-A2 | GR-A2 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
FG3K2D3Z16800247 | CAN-NDR-FORTINET-FW2 | GR-A4 | 1 | TR-1.4 | N-01 | 36-35 | Lift & Shift – GR-A1 | GR-A1 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
FG3K2D3Z16800269 | CAN-NDR-FORTINET-FW1 | GR-A4 | 1 | TR-1.4 | N-01 | 34-33 | Lift & Shift – GR-A1 | GR-A1 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
FDO281513F3 | NDR-DMZ-SW-01 | GR-A4 | 1 | TR-1.4 | H-10 | U4 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO28160CZT | NDR_DMZ_SW_02 | GR-A4 | 1 | TR-1.4 | H-11 | U4 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
C8SSN24 | NDC-BASENDC-APP | GR-A4 | 1 | TR-1.4 | N-01 | 6-5 | Lift & Shift – GR-A1 | GR-A1 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
C0GRN24 | DCC0GRN24 | GR-A4 | 1 | TR-1.4 | N-01 | 8-7 | Lift & Shift – GR-A1 | GR-A1 | 1 | TR-1.3 | OK – same batch: rack on TR-1.3 (mount after rack is fixed)
787414D | BLR128B-G7-SW2 | D3 | 2 | TR-2 | D-09 | 23 | Lift & Shift – IBM Rack (D3) | D3 | 2 | TR-2.6 | OK – same batch: rack on TR-2.6 (mount after rack is fixed)
7821YYX | SANINV90 | B2 | 2 | TR-2 | C-08 | 4-5 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
782206V | SANINV88 | B2 | 2 | TR-2 | C-08 | 6-7 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
7823KXE | SANINV68 | B2 | 2 | TR-2 | C-08 | 8-9 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
7823KWF | SANINV66 | B2 | 2 | TR-2.11 | C-08 | 10-11 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
781V1N9 | Not Applicable | B2 | 2 | TR-2.11 | C-08 | 14-15 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
787100G | BLR512B-G7-SW1 | A3 | 2 | TR-2 | E-16 | 4-17 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
781V1M7 | SANINV221 | B2 | 2 | TR-2.11 | C-08 | 16-17 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
781403F | DCX-BLR512B-1 | K7 | 2 | TR-2.11 | F-16 | 4-17 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
483313 | SANINV172 | F5 | 2 | TR-2 | D-06 | 25 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
10194DD | DCX-BLR3SSWPC2112 | G7 | 2 | TR-2.11 | E-02 | 4-17 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
78E071K | SANINV191 | K6 | 2 | TR-2.11 | G-20 | 4-5 | Lift & Shift – IBM rack (K6) | K6 | 2 | TR-2.10 | OK – same batch: rack on TR-2.10 (mount after rack is fixed)
78E072T | SANINV179 | L5 | 2 | TR-2.11 | H-19 | 4-5 | Lift & Shift – IBM rack (L5) | L5 | 2 | TR-2.10 | OK – same batch: rack on TR-2.10 (mount after rack is fixed)
CX4SMZ3 | candcnwsn01 | W6 | 2 | TR-2.12 | H-06 | 35 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
BJDXMZ3 | candcnwsn02 | W6 | 2 | TR-2.12 | H-06 | 36 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
781V1N4 | SANINV220 | B2 | 2 | TR-2.11 | C-08 | 18-19 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
78E06F7 | Not Applicable | B2 | 2 | TR-2.11 | C-08 | 12-13 | Lift & Shift – IBM Rack (C1) | C1 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
8JW4L83 | SANINV170 | F3 | 2 | TR-2.11 | D-06 | 34-35 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
G5KVNT3 | SANINV170 | F3 | 2 | TR-2.11 | D-06 | 32-33 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
D5KVNT3 | SANINV170 | F3 | 2 | TR-2.11 | D-06 | 30-31 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
CKM00194301481/22W9MX2 | SANINV170 | F3 | 2 | TR-2.11 | D-06 | 28-29 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
781405Z | DCX-BLR512B-2 | L6 | 2 | TR-2.11 | E-01 | 4-17 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
C1A1KW2304258 | DCHNAS5200-N1 | F5 | 2 | TR-2.11 | D-06 | 21-23 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
483313 | Not Applicable | F5 | 2 | TR-2.11 | D-06 | 16-17 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
483313 | Not Applicable | F5 | 2 | TR-2.11 | D-06 | 14-15 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
612909 | SANINV383 | F6 | 2 | TR-2.11 | D-06 | 4-6 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
F077103H8LE22120246 | SANINV383 | F6 | 2 | TR-2.11 | D-06 | 7-9 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
810675 | SANINV383 | F6 | 2 | TR-2.11 | D-06 | 10-11 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
DZRH504 | candcdd.aranac.com | W6 | 2 | TR-2.12 | H-06 | 24-26 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
GZRH504 | candcdd.aranac.com | W6 | 2 | TR-2.12 | H-06 | 27-29 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
296Z9W3 | Not Applicable | W6 | 2 | TR-2.12 | H-06 | 30-32 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
496Z9W3 | Not Applicable | W6 | 2 | TR-2.12 | H-06 | 4-8 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
696Z9W3 | Not Applicable | W6 | 2 | TR-2.12 | H-06 | 9-13 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
396Z9W3 | Not Applicable | W6 | 2 | TR-2.12 | H-06 | 14-18 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
WZP22260A84 | DCPLCSWDO02RTGS | E2 | 2 | TR-2.12 | C-14 | 15 | Migrated – WQ Rack (AB2) | — | — | — | OK – rack already at STT (migrated)
WZP222808BJ | OAVS2 | E2 | 2 | TR-2.12 | C-14 | 23 | Migrated – WQ Rack (AB2) | — | — | — | OK – rack already at STT (migrated)
WZP22260A7Z | DCPLCSWQI01RTGS | E3 | 2 | TR-2.12 | D-14 | 8 | Migrated – WQ Rack (AD2) | — | — | — | OK – rack already at STT (migrated)
FSC1940004 | Not Applicable | S6 | 2 | TR-2.11 | C-05 | 16-21 | Migrated – WQ Rack (AA2) | — | — | — | OK – rack already at STT (migrated)
FSC1940004 | Not Applicable | S6 | 2 | TR-2.11 | C-05 | 4-9 | Migrated – WQ Rack (AA2) | — | — | — | OK – rack already at STT (migrated)
FSC1940004 | Not Applicable | S6 | 2 | TR-2.11 | C-05 | 10-15 | Migrated – WQ Rack (AA2) | — | — | — | OK – rack already at STT (migrated)
5C4Z9W3 | Not Applicable | W6 | 2 | TR-2.12 | H-06 | 19-23 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
WZP22270KUZ | avs00451d69b946 | E3 | 2 | TR-2.12 | D-14 | 16 | Migrated – WQ Rack (AD2) | — | — | — | OK – rack already at STT (migrated)
WZP22190GDB | UATAPP-OTP | E3 | 2 | TR-2.12 | D-14 | 5 | Migrated – WQ Rack (AD2) | — | — | — | OK – rack already at STT (migrated)
8XX5G33 | DCDLLDB1RAC5NODE2 | F2 | 2 | TR-2.12 | A-10 | 27 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
6XX5G33 | dcdlldb1rac5node1 | F2 | 2 | TR-2.12 | B-10 | 29 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FCJXJ03 | DCDLLDB1RAC1NODE1 | F3 | 2 | TR-2.12 | H-02 | 30 | Migrated – WQ Rack (AE4) | — | — | — | OK – rack already at STT (migrated)
3DCYM03 | DCDLLDB1RAC2NODE1 | F3 | 2 | TR-2.12 | H-02 | 31 | Migrated – WQ Rack (AE4) | — | — | — | OK – rack already at STT (migrated)
5DCYM03 | DCDLLDB1RAC3NODE1 | F3 | 2 | TR-2.12 | A-10 | 26 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
5ZHXJ03 | DCDLLDB1RAC3NODE2 | F4 | 2 | TR-2.12 | B-10 | 28 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
D2SXMZ3 | DCUATDBN4 | J2 | 2 | TR-2.12 | L-01 | 6-7 | Shift rack from I-20 – WQ rack (N5) | — | — | — | CHECK – rack shift at STT required: Shift rack from I-20
D3SXMZ3 | DCUATDBN5 | J2 | 2 | TR-2.12 | L-02 | 6-7 | Migrated – WQ rack (AA6) | — | — | — | OK – rack already at STT (migrated)
73SXMZ3 | DCUATDBN2 | J2 | 2 | TR-2.12 | L-01 | 14-15 | Shift rack from I-20 – WQ rack (N5) | — | — | — | CHECK – rack shift at STT required: Shift rack from I-20
93SXMZ3 | DCHVCLSTRN10 | J2 | 2 | TR-2.12 | H-01 | 6-7 | Migrated – WQ Rack (AE3) | — | — | — | OK – rack already at STT (migrated)
83SXMZ3 | DCHVCLSTRN09 | J2 | 2 | TR-2.12 | H-01 | 8-9 | Migrated – WQ Rack (AE3) | — | — | — | OK – rack already at STT (migrated)
H3SXMZ3 | DCHVCLSTRN08 | J2 | 2 | TR-2.12 | H-01 | 10-11 | Migrated – WQ Rack (AE3) | — | — | — | OK – rack already at STT (migrated)
G3SXMZ3 | DCHVCLSTRN07 | J2 | 2 | TR-2.12 | H-01 | 23-24 | Migrated – WQ Rack (AE3) | — | — | — | OK – rack already at STT (migrated)
J3SXMZ3 | DCUATDBN6 | J2 | 2 | TR-2.12 | L-02 | 8-9 | Migrated – WQ rack (AA6) | — | — | — | OK – rack already at STT (migrated)
183M6C2 | DC-SFTP-SRV | M5 | 2 | TR-2.12 | I-06 | 32 | Migrated – Net Rack (AA5) | — | — | — | OK – rack already at STT (migrated)
C3SXMZ3 | TRAC Setup | J2 | 2 | TR-2.12 | H-01 | 4-5 | Migrated – WQ Rack (AE3) | — | — | — | OK – rack already at STT (migrated)
21KHMY3 | DCCANCRKPSM03 | M1 | 2 | TR-2.12 | J-07 | 16-17 | Lift & Shift – Net Rack (X5) | X5 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
81KHMY3 | DCHYPRVBASE2 | M1 | 2 | TR-2.12 | J-07 | 10-11 | Lift & Shift – Net Rack (X5) | X5 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
B1KHMY3 | cluster1-Node1 | M1 | 2 | TR-2.12 | J-07 | 12-13 | Lift & Shift – Net Rack (X5) | X5 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
10KHMY3 | cluster1-Node3 | M1 | 2 | TR-2.12 | J-07 | 18-19 | Lift & Shift – Net Rack (X5) | X5 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
C1A1KW2304376 | DCHNAS5200-N2 | F5 | 2 | TR-2.12 | D-06 | 18-20 | Migrated – WQ Rack (AC6) | — | — | — | OK – rack already at STT (migrated)
WZP23050K70 | DCCSW02SFMSNEFT | F6 | 2 | TR-2.12 | D-14 | 26 | Migrated – WQ Rack (AD2) | — | — | — | OK – rack already at STT (migrated)
WZP23050K8T | DCCSW01SFMSNEFT | F6 | 2 | TR-2.12 | D-14 | 17 | Migrated – WQ Rack (AD2) | — | — | — | OK – rack already at STT (migrated)
61KHMY3 | cluster1-Node4 | M1 | 2 | TR-2.12 | J-07 | 20-21 | Lift & Shift – Net Rack (X5) | X5 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
41KHMY3 | DCDLLDB1RAC7NODE2 | M1 | 2 | TR-2.13 | A-10 | 28-29 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
D1KHMY3 | DCDLLDB1RAC7NODE1 | M1 | 2 | TR-2.13 | B-10 | 22-23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
20KHMY3 | DCDLLDB1RAC6NODE2 | M1 | 2 | TR-2.13 | B-10 | 30-31 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
71KHMY3 | DCDLLDB1RAC6NODE1 | M1 | 2 | TR-2.13 | A-10 | 20-21 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
90KHMY3 | WIN-4JIKE60P6JV | M1 | 2 | TR-2.13 | J-07 | 4-5 | Lift & Shift – Net Rack (X5) | X5 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
JZJHMY3 | DC-MB-APP11 | M1 | 2 | TR-2.13 | J-07 | 6-7 | Lift & Shift – Net Rack (X5) | X5 | 2 | TR-2 | OK – same batch: rack on TR-2 (mount after rack is fixed)
3QGL6C2 | dc-dmz-host2.vmcandomain.com | M5 | 2 | TR-2.13 | J-08 | 20 | Move rack from J-09 – Net Rack (X7) | — | — | — | CHECK – rack shift at STT required: Move rack from J-09
C0KHMY3 | DCNCBSDMZBASE2 | M7 | 2 | TR-2.13 | L-01 | 12-13 | Shift rack from I-20 – WQ rack (N5) | — | — | — | CHECK – rack shift at STT required: Shift rack from I-20
40KHMY3 | DCNCBSDMZBASE1 | M7 | 2 | TR-2.13 | J-05 | 12-13 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
D0KHMY3 | DCNCBSINTBASE2 | M7 | 2 | TR-2.13 | J-05 | 14-15 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
BKJHMY3 | WIN-STLAAFKA5J2 | M7 | 2 | TR-2.13 | J-08 | 18-19 | Move rack from J-09 – Net Rack (X7) | — | — | — | CHECK – rack shift at STT required: Move rack from J-09
9MJHMY3 | DCHYPRVBASE1 | M7 | 2 | TR-2.13 | J-05 | 8-9 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
B0KHMY3 | DCHVCLSTRN02 | M7 | 2 | TR-2.13 | J-05 | 10-11 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
60KHMY3 | dwgaipoc | M7 | 2 | TR-2.13 | J-05 | 6-7 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
CKJHMY3 | DCNCBSINTBASE1 | N5 | 2 | TR-2.13 | I-08 | 4-5 | Migrated – Net Rack (AB4) | — | — | — | OK – rack already at STT (migrated)
70KHMY3 | DCIRMSBASE11 | N5 | 2 | TR-2.13 | I-08 | 6-7 | Migrated – Net Rack (AB4) | — | — | — | OK – rack already at STT (migrated)
G0KHMY3 | DCIRMSBASE9 | N5 | 2 | TR-2.13 | J-05 | 18-19 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
91KHMY3 | DCIRMSBASE8 | N5 | 2 | TR-2.13 | J-05 | 20-21 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
DKJHMY3 | DCIRMSBASE7 | N5 | 2 | TR-2.13 | I-08 | 8-9 | Migrated – Net Rack (AB4) | — | — | — | OK – rack already at STT (migrated)
50KHMY3 | DCIRMSBASE4 | N5 | 2 | TR-2.13 | I-08 | 14-15 | Migrated – Net Rack (AB4) | — | — | — | OK – rack already at STT (migrated)
7MJHMY3 | DCIRMSBASE2 | N5 | 2 | TR-2.13 | J-05 | 22-23 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
8KJHMY3 | DCIRMSBASE1 | N5 | 2 | TR-2.13 | J-05 | 24-25 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
FDO24130M76 | DC-K6-N9K-TOR-SW1 | K6 | 2 | TR-2.13 | I-10 | Spare | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FLM261608D0 | DC-B2-N9K-DMZ-TOR-SW | B2 | 2 | TR-2.13 | G-11 | U19 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO22273YZS | DC-C1-N9K-ToR-SW-1 | C1 | 2 | TR-2.13 | L-11 | U6 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO2614150K | DC-C1-N9K-TOR-SW2 | C1 | 2 | TR-2.13 | D-10 | U6 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
8MJHMY3 | DCIRMSBASE10 | N5 | 2 | TR-2.13 | J-05 | 16-17 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
74LHMY3 | DCIRMSBASE6 | N5 | 2 | TR-2.13 | I-08 | 10-11 | Migrated – Net Rack (AB4) | — | — | — | OK – rack already at STT (migrated)
30KHMY3 | DCIRMSBASE5 | N5 | 2 | TR-2.13 | I-08 | 12-13 | Migrated – Net Rack (AB4) | — | — | — | OK – rack already at STT (migrated)
HZJHMY3 | DCIRMSBASE3 | N5 | 2 | TR-2.13 | I-08 | 16-17 | Migrated – Net Rack (AB4) | — | — | — | OK – rack already at STT (migrated)
31KHMY3 | DCPIRMSDB02 | N5 | 2 | TR-2.13 | J-05 | 26-27 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
84LHMY3 | DCPIRMSDB01 | N5 | 2 | TR-2.13 | J-05 | 28-29 | Move rack from J-06 – Net Rack (U2) | — | — | — | CHECK – rack shift at STT required: Move rack from J-06
3131AG435894 | localhost | O5 | 2 | TR-2.13 | Scrap |  |  | — | — | — | CHECK – target 'Scrap' to be confirmed
7PRXDV2 | DCBLR7PRXDV2 | P1 | 2 | TR-2.13 | E-05 | 21 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
7PRRDV2 | DCNCCMDB01 | P1 | 2 | TR-2.13 | E-05 | 20 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
7V1N0V3 | EWIRMUATAPPBASE | X2 | 2 | TR-2.13 | F-03 | 24 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
12DGGQ00100002 | canamluat | V3 | 3 | TR-3 | NA |  |  | — | — | — | CHECK – target 'NA' to be confirmed
C6DBTZ3 | candcex300ecs1d1.aranac.com | W3 | 3 | TR-3 | G-05 | 4-5 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
D6DBTZ3 | candcex300ecs1d10.aranac.com | W3 | 3 | TR-3 | G-05 | 6-7 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
F6DBTZ3 | candcex300ecs1d11.aranac.com | W3 | 3 | TR-3 | G-05 | 8-9 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
J5DBTZ3 | candcex300ecs1d2.aranac.com | W3 | 3 | TR-3 | G-05 | 10-11 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
B6DBTZ3 | candcex300ecs1d3.aranac.com | W3 | 3 | TR-3 | G-05 | 12-13 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
WZP22190GCS | UATWEB-OTP | M4 | 3 | TR-3 | D-14 | 20 | Migrated – WQ Rack (AD2) | — | — | — | OK – rack already at STT (migrated)
96DBTZ3 | candcex300ecs1d4.aranac.com | W3 | 3 | TR-3 | G-05 | 14-15 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
10QLV03 | candcex300ecs1d5.aranac.com | W4 | 3 | TR-3 | G-04 | 4-5 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
JZPLV03 | candcex300ecs1d6.aranac.com | W4 | 3 | TR-3 | G-04 | 6-7 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
HZPLV03 | candcex300ecs1d7.aranac.com | W4 | 3 | TR-3 | G-04 | 8-9 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
30QLV03 | candcex300ecs1d8.aranac.com | W4 | 3 | TR-3 | G-04 | 10-11 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
FZPLV03 | candcex300ecs1d9.aranac.com | W4 | 3 | TR-3.1 | G-04 | 12-13 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
20QLV03 | candcex300ecs2d1.aranac.com | W4 | 3 | TR-3.1 | G-04 | 14-15 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
GZPLV03 | candcex300ecs2d10.aranac.com | W4 | 3 | TR-3.1 | G-04 | 16-17 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
DZPLV03 | candcex300ecs2d2.aranac.com | W4 | 3 | TR-3.1 | G-04 | 18-19 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
BWTLV03 | candcex300ecs2d3.aranac.com | W4 | 3 | TR-3.1 | G-04 | 20-21 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
7HLLV03 | candcex300ecs2d4.aranac.com | W4 | 3 | TR-3.1 | G-04 | 22-23 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
9WTLV03 | candcex300ecs2d5.aranac.com | W4 | 3 | TR-3.1 | G-04 | 24-25 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
B0QLV03 | candcex300ecs2d6.aranac.com | W5 | 3 | TR-3.1 | G-03 | 4-5 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
8XPLV03 | candcex300ecs2d7.aranac.com | W5 | 3 | TR-3.1 | G-03 | 6-7 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
3ZPLV03 | candcex300ecs2d8.aranac.com | W5 | 3 | TR-3.1 | G-03 | 8-9 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
DYPLV03 | candcex300ecs2d9.aranac.com | W5 | 3 | TR-3.1 | G-03 | 10-11 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
JYPLV03 | candcex500ecs3d1.aranac.com | W5 | 3 | TR-3.1 | G-03 | 12-13 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
5WTLV03 | candcex500ecs3d2.aranac.com | W5 | 3 | TR-3.1 | G-03 | 14-15 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
3WTLV03 | candcex500ecs3d3.aranac.com | W5 | 3 | TR-3.1 | G-03 | 16-17 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
7WTLV03 | candcex500ecs3d4.aranac.com | W5 | 3 | TR-3.1 | G-03 | 18-19 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
4WTLV03 | candcex500ecs3d5.aranac.com | W5 | 3 | TR-3.1 | G-03 | 20-21 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
HJLLV03 | candcex500ecs3d6.aranac.com | W5 | 3 | TR-3.1 | G-03 | 22-23 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
FNHTN24 | CAN-DC-CELL7 | G3 | 3 | TR-3.1 | I-06 | 22-23 | Migrated – Net Rack (AA5) | — | — | — | OK – rack already at STT (migrated)
697640 | Not Applicable | G3 | 3 | TR-3.1 | D-10 |  | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
84B6FAW | Server-8284-22A-SN84B6FAW | G3 | 3 | TR-3.1 | OOS |  |  | — | — | — | CHECK – target 'OOS' to be confirmed
1PG5MP2 | DCDBSYNFRS | G6 | 3 | TR-3.1 | K-08 | 8-9 | Migrated – WQ rack (M1) | — | — | — | OK – rack already at STT (migrated)
CS801400000012 | DC-H2-P2 CLOUDSTATION | H2 | 3 | TR-3.1 | F-07 | 4-5 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FCNCA191702270 | Not Applicable | W7 | 3 | TR-3.1 | H-05 | 8-11 | Migrated – WQ Rack (AF2) | — | — | — | OK – rack already at STT (migrated)
FCNCA191800100 | Not Applicable | W7 | 3 | TR-3.1 | H-05 | 12-15 | Migrated – WQ Rack (AF2) | — | — | — | OK – rack already at STT (migrated)
FCNCA191800042 | Not Applicable | W7 | 3 | TR-3.1 | H-05 | 16-19 | Migrated – WQ Rack (AF2) | — | — | — | OK – rack already at STT (migrated)
FCNCA191800014 | Not Applicable | W7 | 3 | TR-3.1 | H-05 | 20-23 | Migrated – WQ Rack (AF2) | — | — | — | OK – rack already at STT (migrated)
IN801400000014 | DC-H2-P2 INSIGHTS | H2 | 3 | TR-3.1 | E-07 | 4-5 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
WS3719420161 | DC-H3-H4-WAN-L2-SW | H3 | 3 | TR-3.1 | E-08 | 27 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FOX1740GAHU | DC-H3-KS-RTR-2 | H3 | 3 | TR-3.1 | F-08 | 19-20 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
VF3715360067 | DC-L3-WAN-AGG | H3 | 3 | TR-3.1 | E-08 | 28 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FXS1741Q27Z | DC-H3-GM-RTR-2 | H3 | 3 | TR-3.1 | F-08 | 13-18 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
f5-pyrs-qtdq | DCINTADC02.aranac.com F5-BIG-LTM-15800 | H3 | 3 | TR-3.1 | F-09 | 24 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
801400000008 | DC-H3-P2 CLOUDPORT GATEWAY 2 | H3 | 3 | TR-3.1 | F-07 | 6-7 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
WS3719420123 | DC-H3-H4-WAN-L2-SW | H4 | 3 | TR-3.1 | F-08 | 23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
847C10W | drswift02 | N1 | 3 | TR-3.1 | Scrap |  |  | — | — | — | CHECK – target 'Scrap' to be confirmed
FXS2436Q0R1 | DC-H3-CORE-RTR-2 | H3 | 3 | TR-3.1 | F-08 | 4-12 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FOX1740GAHX | DC-H4-KS-RTR-1 | H4 | 3 | TR-3.2 | E-08 | 22-23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
VF3715360265 | DC-L3-WAN-AGG | H4 | 3 | TR-3.1 | F-08 | 24 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FXS1739Q2UK | DC-H4-GM-RTR-1 | H4 | 3 | TR-3.2 | E-08 | 13-21 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
F5-RBYB-IWXP | DCINTADC01.aranac.com F5-BIG-LTM-15800 | H4 | 3 | TR-3.2 | E-09 | 24 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
801400000007 | DC-H4-P2 CLOUDPORT GATEWAY 1 | H4 | 3 | TR-3.2 | E-08 | 24-25 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
501400000011 | DC-I1-P1 CLOUDPORT GATEWAY 2 | I1 | 3 | TR-3.2 | F-07 | 8 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FXS2545Q0Z1 | DC-H4-CORE-RTR-1 | H4 | 3 | TR-3.2 | E-08 | 4-12 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FG3K2D3Z16800261 | DC-FORTI-FW-1 | I2 | 3 | TR-3.2 | E-09 | 22-23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
JMX2302L035 | DC-I2-FTD-CHASSIS-1 | I2 | 3 | TR-3.2 | E-09 | 18-20 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FG3K2D3Z16800276 | DC-FORTI-FW-2 | I3 | 3 | TR-3.2 | F-09 | 22-23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
WMP2411007K | DC-I3-FMC-PRIMARY | I3 | 3 | TR-3.2 | E-06 | 13 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
JMX2417L00R | DC-I2-FTD-CHASSIS-2 | I3 | 3 | TR-3.2 | F-09 | 18-20 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FGE22334V45 | DC-I2-N9508-CORE-SW1 | I2 | 3 | TR-3.2 | E-09 | 4-16 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
CS401300000002 | DC-J6-P1 CLOUDSTATION | J6 | 3 | TR-3.2 | E-07 | 6 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
IN401300000002 | DC-J6-P1 INSIGHTS | J6 | 3 | TR-3.2 | F-05 | 4-5 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
f5-ctyi-hccy | DCDMZADC02 | N3 | 3 | TR-3.2 | F-11 | 20 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
HWXRT04 | CB-DC-CP-EVENT-SRV | N3 | 3 | TR-3.2 | E-11 | 11-12 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
LR202312007390 | Checkpoint 29100 CB-DC-CP-DMZ-FW2 | N3 | 3 | TR-3.2 | F-11 | 10-11 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
LR202402009851 | CB-DC-CP-INTERNET-PROXY-FW2 | N3 | 3 | TR-3.2 | F-12 | 11-12 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO28130W1X | DC-N3-AGGEGATION-N9K-SW-2 | N3 | 3 | TR-3.2 | F-12 | 23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FOC2132R03J | Cisco Nexus 3548-X DC-N3-DMZ-PXY-WAN-SW-2Y | N3 | 3 | TR-3.2 | F-12 | 24 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FGE22334V4X | DC-I3-N9508-CORE-SW2 | I3 | 3 | TR-3.2 | F-09 | 4-16 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
BJ606 | DC-N3-INTERNET-PROXY-RTR2 | N3 | 3 | TR-3.2 | F-12 | 4-6 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FLM26160862 | DC-N4-N9K-PROXY-CORE-SW-1 | N3 | 3 | TR-3.2 | TBD | 32 |  | — | — | — | CHECK – target 'TBD' to be confirmed
FG4H0FT923914098 | Not Applicable | N3 | 3 | TR-3.2 | E-11 | 21 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO28130VX8 | DC-N3-CLOUD-WAN-SW-2 | N3 | 3 | TR-3.2 | TBD | 32 |  | — | — | — | CHECK – target 'TBD' to be confirmed
f5-mucx-joiu | DCDMZADC01 | N4 | 3 | TR-3.3 | E-11 | 33 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
8RM4SR3 | Not Applicable | W3 | 3 | TR-3.3 | G-05 | 23 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
8RF8SR3 | Not Applicable | W3 | 3 | TR-3.3 | G-05 | 24 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
8RF6SR3 | Not Applicable | W3 | 3 | TR-3.3 | G-05 | 25 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
8RD6SR3 | Not Applicable | W3 | 3 | TR-3.3 | G-05 | 26 | Lift & Shift – Dell Rack (W3) | W3 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
LR202402009861 | Not Applicable | N3 | 3 | TR-3.2 | F-12 | 9-10 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FGL2139814C | DC-N3-CLOUD-RTR-2 | N3 | 3 | TR-3.2 | F-12 | 13-14 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
8xxRT04 | CB-DC-CP-MGMT-SRV | N4 | 3 | TR-3.3 | F-11 | 12-13 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
LR202401010219 | Checkpoint 29100 CB-DC-CP-DMZ-FW1 | N4 | 3 | TR-3.3 | E-11 | 13-14 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
LR202402009885 | CB-DC-CP-INTERNET-PROXY-FW1 | N4 | 3 | TR-3.3 | E-12 | 10-11 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO28140BUE | DC-N4-CLOUD-WAN-SW-1 | N4 | 3 | TR-3.3 | H-11 | 23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
CG094 | DC-N4-INTERNET-PROXY-RTR1 | N4 | 3 | TR-3.3 | E-12 | 4-7 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FOC2132R03L | Cisco Nexus 3548-X DC-N4-DMZ-PXY-WAN-SW-1 | N4 | 3 | TR-3.3 | E-12 | 23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FLM261600BU | DC-N3-N9K-PROXY-CORE-SW-2 | N4 | 3 | TR-3.3 | H-11 | 24 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FG4H0FT923913688 | Not Applicable | N4 | 3 | TR-3.3 | F-11 | 21 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FDO281312YJ | DC-N4-AGGREGATION-N9K-SW-1 | N4 | 3 | TR-3.3 | H-10 | 23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
LR202402004472 | CB-DC-CP-CLOUD-FW1 | N4 | 3 | TR-3.3 | E-12 | 12-13 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FGL2139814D | DC-N4-CLOUD-RTR-1 | N4 | 3 | TR-3.3 | E-12 | 14-15 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FLM281510M1 | DC-O1-INTERNET-DMZ-RTR-01 | O1 | 3 | TR-3.3 | E-11 | 22 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
FLM281510M0 | DC-O1-INTERNET-DMZ-RTR-02 | O1 | 3 | TR-3.3 | F-11 | 22 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
VF3715360003 | DC-O1-INTERNET-JPR-L3 | O1 | 3 | TR-3.3 | E-11 | 34 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
VF3715360016 | DC-O1-INTERNET-JPR-L3 | O1 | 3 | TR-3.3 | F-11 | 33 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
CG24148159LA | DCCANARBOR | O1 | 3 | TR-3.3 | E-11 | 15-16 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
1901312380 | Not Applicable | O6 | 3 | TR-3.3 | F-11 | 23 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
3377DT33C | DCCSWPSSL01 | O6 | 3 | TR-3.3 | E-11 | 17-18 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
338BTT3CT | DCCSWPSSL02 | O6 | 3 | TR-3.3 | F-11 | 16-17 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
23720020148 | DCCSWNTB01 | O6 | 3 | TR-3.3 | E-11 | 7 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
23720020149 | DCCSWNTB02 | O6 | 3 | TR-3.3 | F-11 | 24 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
SR 025409001255 | DCCSWPAPT01 | O6 | 3 | TR-3.3 | E-11 | 19-20 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
SR 025409001274 | DCCSWPAPT02 | O6 | 3 | TR-3.3 | F-11 | 18-19 | New rack | — | — | — | OK – new rack at STT (STT to provide PDU)
W3-KVM Switch | Not Applicable | W3 | 3 | TR-3.3 | N/W |  |  | — | — | — | CHECK – target 'N/W' to be confirmed
9435SR3 | Not Applicable | W4 | 3 | TR-3.3 | G-04 | 26 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
9434SR3 | Not Applicable | W4 | 3 | TR-3.3 | G-04 | 27 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
30YB9Z2 | Not Applicable | W4 | 3 | TR-3.3 | G-04 | 28 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
30XD9Z2 | Not Applicable | W4 | 3 | TR-3.3 | G-04 | 29 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
30YC9Z2 | Not Applicable | W4 | 3 | TR-3.3 | G-04 | 30 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
310C9Z2 | Not Applicable | W4 | 3 | TR-3.3 | G-04 | 31 | Lift & Shift – Dell Rack (W4) | W4 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
25JD9Z2 | Not Applicable | W5 | 3 | TR-3.3 | G-03 | 24 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
25CD9Z2 | Not Applicable | W5 | 3 | TR-3.3 | G-03 | 25 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
25GC9Z2 | Not Applicable | W5 | 3 | TR-3.3 | G-03 | 26 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
25KD9Z2 | Not Applicable | W5 | 3 | TR-3.3 | G-03 | 27 | Lift & Shift – Dell Rack (W5) | W5 | 3 | TR-3 | OK – same batch: rack on TR-3 (mount after rack is fixed)
TSBJC2003784 | Not Applicable | W7 | 3 | TR-3.3 | H-06 | 37 | Lift & Shift – Dell Rack (W6) | W6 | 2 | TR-2 | OK – rack arrives in same/earlier batch
TSBJ52004985 | Not Applicable | W7 | 3 | TR-3.3 | H-05 | 35 | Migrated – WQ Rack (AF2) | — | — | — | OK – rack already at STT (migrated)

## SAN_Fabric_Map (hidden)
SAN FABRIC MAP – SWITCHES, ISLs, BATCHES & STORAGE ENDPOINTS (SAN-MAP + CBS_SAN_Connectivity.pptx)
Fabric A (ISL chain) | BLR128B-G7-SW1 (D2) → BLR512B-G7-SW1 (A3) → DCX-BLR512B-1 (K7) → DCX-BLR3SSWPC2111 (F7)
Fabric B (ISL chain) | BLR128B-G7-SW2 (D3) → BLR512B-G7-SW2 (A4) → DCX-BLR512B-2 (L6) → DCX-BLR3SSWPC2112 (G7)
Replication | BLRDCREP_64BG7_SW1/SW2 (A5/A6, principal, PDC) ⇄ DWDM/FCIP ⇄ BLRNDC_64BG7_SW1/SW2 (GR-A1/GR-A2, subordinate, NDC)
Design rule (PPT) | Dual-HBA hosts; independent Fabric A/B; no cross-fabric connections; separate zoning per fabric.
Switch Name | Switch Serial | Fabric | Source Rack | Target Rack | Movement Batch | Truck No | ISL Peers (SAN-MAP) & Batch | Inventory Rows Cabled | ISL Verified at Target (Y/N) | Fabric Health OK (Y/N)
BLR128B-G7-SW1 | 787413W | Fabric A | D2 | C-11 | 2 | TR-2.5 | BLR512B-G7-SW1 (B2) | 20
BLRNDC_64BG7_SW1 | 786731M | Fabric A | GR-A1 | N-03 | 1 | TR-1.3 | BLRDCREP_64BG7_SW1 (B2) | 9
BLR128B-G7-SW2 | 787414D | Fabric B | D3 | D-09 | 2 | TR-2 | BLR512B-G7-SW2 (B1) | 20
BLR512B-G7-SW2 | 755231F | Fabric B | A4 | F-01 | 1 | TR-1.3 | DCX-BLR512B-2 (B2), BLR128B-G7-SW2 (B2) | 52
BLRNDC_64BG7_SW2 | 786729Z | Fabric B | GR-A2 | N-04 | 1 | TR-1.3 | BLRDCREP_64BG7_SW2 (B2) | 9
BLR512B-G7-SW1 | 787100G | Fabric A | A3 | E-16 | 2 | TR-2.11 | DCX-BLR512B-1 (B2), BLR128B-G7-SW1 (B2) | 52
BLRDCREP_64BG7_SW1 | 786711P | Fabric A | A5 | D-13 | 2 | TR-2.2 | BLRNDC_64BG7_SW1 (B1) | 18
DCX-BLR3SSWPC2111 | 10194GB | Fabric A | F7 | F-15 | 2 | TR-2.7 | DCX-BLR512B-1 (B2) | 78
DCX-BLR512B-1 | 781403F | Fabric A | K7 | F-16 | 2 | TR-2.11 | DCX-BLR3SSWPC2111 (B2), BLR512B-G7-SW1 (B2) | 92
BLRDCREP_64BG7_SW2 | 786711C | Fabric B | A6 | C-12 | 2 | TR-2.2 | BLRNDC_64BG7_SW2 (B1) | 18
DCX-BLR3SSWPC2112 | 10194DD | Fabric B | G7 | E-02 | 2 | TR-2.11 | DCX-BLR512B-2 (B2) | 78
DCX-BLR512B-2 | 781405Z | Fabric B | L6 | E-01 | 2 | TR-2.12 | DCX-BLR3SSWPC2112 (B2), BLR512B-G7-SW2 (B1) | 91
Storage endpoints per PPT vs inventory / SAN-MAP
PPT Storage Endpoint | Rack (PPT) | Switch Pair per PPT | Pair Switches & Batch | Inventory Serials | SAN-MAP Switches (actual) | Endpoint Batch | Truck(s) | Result | Note
BLRDCSV3 (IBM multi-node) | A5/A6 | BLR512B-G7-SW1/SW2 + BLRDCREP_64BG7_SW1/SW2 (replication principal) | BLR512B-G7-SW2 (B1), BLRDCREP_64BG7_SW1 (B2), BLR512B-G7-SW1 (B2), BLRDCREP_64BG7_SW2 (B2) | 78E4G8P, 78E4B4D, 78E4N36, 78E4T96, 78E4T04, 78E4X74, 78E4W21, 78E4B1H, 78E4F19 | BLR512B-G7-SW1, BLR512B-G7-SW2, BLRDCREP_64BG7_SW1, BLRDCREP_64BG7_SW2 | 2 | TR-2.3, TR-2.4 | OK | Slide 1 on G7 pair; slide 2 replication source via BLRDCREP.
BLRSV3DC_FS9500_PROD | A5 | BLR512B-G7-SW1/SW2 | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | 78E4E54 | BLR512B-G7-SW1, BLR512B-G7-SW2 | 2 | TR-2.3 | OK
BLRSV3DC_FS9500_FCPROD | A6 | BLR512B-G7-SW1/SW2 | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | 78E4V30 | BLR512B-G7-SW1, BLR512B-G7-SW2 | 2 | TR-2.4 | OK
BLRDC_FS7300_PROD01 | D6 | BLR512B-G7-SW1/SW2 | BLR512B-G7-SW2 (B1), BLR512B-G7-SW1 (B2) | 78E3KFT | BLR512B-G7-SW1, BLR512B-G7-SW2 | 2 | TR-2.7 | OK
BLRDC_FS7300_UAT_01 | D2 | BLR128B-G7-SW1/SW2 | BLR128B-G7-SW2 (B2), BLR128B-G7-SW1 (B2) | 78E3NYR | BLR128B-G7-SW1, BLR128B-G7-SW2 | 1 | TR-1.1 | OK
BLRDC_FS9500_ARCH_01 | D2 | BLR128B-G7-SW1/SW2 | BLR128B-G7-SW2 (B2), BLR128B-G7-SW1 (B2) | 78E4Z5Z | BLR128B-G7-SW1, BLR128B-G7-SW2 | 1 | TR-1.1 | OK
BLRDC_FS9150_UAT_01 | K6 | BLR128B-G7-SW1/SW2 | BLR128B-G7-SW2 (B2), BLR128B-G7-SW1 (B2) | 78E071K | BLR128B-G7-SW1, BLR128B-G7-SW2 | 1 | TR-1.4 | CHECK – unrack from OEM production rack | Sits in production rack K6.
BLRDC_FS9150_UAT_02 | L5 | BLR128B-G7-SW1/SW2 | BLR128B-G7-SW2 (B2), BLR128B-G7-SW1 (B2) | 78E072T | BLR128B-G7-SW1, BLR128B-G7-SW2 | 1 | TR-1.4 | CHECK – unrack from OEM production rack | Sits in production rack L5.
BLRDCSV2 (IBM storage) | L5/K6 | DCX-BLR512B-1/2 + BLRDCREP_64BG7_SW1/SW2 (replication principal) | DCX-BLR512B-1 (B2), BLRDCREP_64BG7_SW1 (B2), BLRDCREP_64BG7_SW2 (B2), DCX-BLR512B-2 (B2) | 78E306M, 78E3078, 78E3071, 78E306K, 78E3063, 78E3079, 78E3072, 78E306L, 78E306B | BLRDCREP_64BG7_SW1, BLRDCREP_64BG7_SW2, DCX-BLR512B-1, DCX-BLR512B-2 | 2 | TR-2.12 | OK | Slide 1 on DCX pair; slide 2 replication source via BLRDCREP.
BLRDC_FS9500_SV2_FCPROD | D3 | DCX-BLR512B-1/2 | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | 78E4Z6R, 78E4Z6F | DCX-BLR512B-1, DCX-BLR512B-2 | 2 | TR-2.6 | OK | Production back-end of BLRDCSV2, in rack D3 with BLR128B-G7-SW2.
BLRSV2DC_FS7300_PROD2 | D6 | DCX-BLR512B-1/2 | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | 78E3KDF | DCX-BLR512B-1, DCX-BLR512B-2 | 2 | TR-2.7 | OK
BLRDC_FS7300_ARCHIVAL | D6 | DCX-BLR512B-1/2 + DCX-BLR3SSWPC2111/2112 | DCX-BLR512B-1 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-2 (B2), DCX-BLR3SSWPC2111 (B2) | 78E3K6H | DCX-BLR3SSWPC2111, DCX-BLR3SSWPC2112, DCX-BLR512B-1, DCX-BLR512B-2 | 2 | TR-2.7 | OK | SAN-MAP shows it on both DCX-BLR512B and DCX-BLR3SSWPC pairs.
BLRDC_V7KG3_ARCHIVAL | B2 | DCX-BLR512B-1/2 | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | 78E06F7, 781V1N9, 781V1M7, 781V1N4, 7821YYX, 782206V, 7823KXE, 7823KWF | DCX-BLR512B-1, DCX-BLR512B-2 | 2 | TR-2.13, TR-2.14 | OK | Controller + enclosures.
Hitachi OneBlock | F6 | DCX-BLR512B-1/2 | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | 810675 | DCX-BLR512B-1, DCX-BLR512B-2 | 2 | TR-2.8 | OK
DELL DATA DOMAIN | W6 | DCX-BLR512B-1/2 + DCX-BLR3SSWPC2111/2112 | DCX-BLR512B-1 (B2), DCX-BLR3SSWPC2112 (B2), DCX-BLR512B-2 (B2), DCX-BLR3SSWPC2111 (B2) | — | — | — | — | GAP – not in inventory | SAN-MAP serials CRK00234104830/31 are not in the inventory.
HPE StoreOnce | D5 | DCX-BLR512B-1/2 | DCX-BLR512B-1 (B2), DCX-BLR512B-2 (B2) | — | — | — | — | GAP – not in inventory | SAN-MAP serial SOH405MQVF is not in the inventory; rack D5 moves in Batch 1.
DC-VSP E790 | F6 | DCX-BLR3SSWPC2111/2112 | DCX-BLR3SSWPC2112 (B2), DCX-BLR3SSWPC2111 (B2) | 612909 | DCX-BLR3SSWPC2111, DCX-BLR3SSWPC2112 | 2 | TR-2.8 | OK
HNAS 5200 CU | F5 | DCX-BLR3SSWPC2111/2112 | DCX-BLR3SSWPC2112 (B2), DCX-BLR3SSWPC2111 (B2) | C1A1KW2304376, C1A1KW2304258 | DCX-BLR3SSWPC2111, DCX-BLR3SSWPC2112 | 2 | TR-2.7 | OK
Hitachi G350 | F5 | DCX-BLR3SSWPC2111/2112 | DCX-BLR3SSWPC2112 (B2), DCX-BLR3SSWPC2111 (B2) | 483313 | DCX-BLR3SSWPC2111, DCX-BLR3SSWPC2112 | 2 | TR-2.7 | OK
DCDLRACSTORAGE (EMC) | F3 | DCX-BLR3SSWPC2111/2112 | DCX-BLR3SSWPC2112 (B2), DCX-BLR3SSWPC2111 (B2) | CKM00194301481/22W9MX2 | — | 2 | TR-2.14 | MISMATCH – SAN-MAP differs from PPT | Serial mismatch: SAN-MAP CKM00194600130 vs inventory CKM00194301481/22W9MX2.
HPE StoreOnce | D4 | DCX-BLR3SSWPC2111/2112 | DCX-BLR3SSWPC2112 (B2), DCX-BLR3SSWPC2111 (B2) | — | — | — | — | GAP – not in inventory | Rack D4 is not in the inventory (SAN-MAP: CZJ74809QV, SGH107HS01; MSL6480 DEC75100ZG).
BLRNDC storage (FS7300_PROD01 / NDCSV3 / FS7300_PROD02) | GR-A1/GR-A2 | BLRNDC_64BG7_SW1/SW2 (replication subordinate) | BLRNDC_64BG7_SW1 (B1), BLRNDC_64BG7_SW2 (B1) | 78E4Y9C, 78E4Y8T, 78E4Z1B, 78E4Z1E, 78E3NPL, 78E3KE2 | BLRNDC_64BG7_SW1, BLRNDC_64BG7_SW2 | 1 | TR-1.3, TR-1.4 | OK | Slide 2 replication subordinate.

## Migration Squad (hidden)
Migration Squad
Names carried from the Bubble runbook (v2.2). Add CBS-specific application and OEM contacts before the event.
Application/Team Name | Name | Role | Phone | Email
Kyndryl Migration Squad | Prasenjit Pal/Sudipta Goswamy | Wave Architect | 9980155667 | sudipta.goswami@kyndryl.com
| Prasenjit Pal/Sudipta Goswamy | Migration Architect | 9980155667 | prasenjit.pal@kyndryl.com
| Swarup | Wave PM | 9986021228 | pradeep.doddaiah@kyndryl.com
| Ramesh | Windows SME | 9600123777 | ramesh.gopal@kyndryl.com
| Sudeep | Storage
| Sushant | Backup
| Praveen | Linux SME
| Akhilesh | Kyndryl Network Team
| Shabari | PowerIT Focal | 9940036997
| Arpu Rajan | PowerIT Focal | 89397979848
| Nidhil & Annamalai | STT
| Arvind | Royal International | 9022312399 | arvind@royalint.in
| Mithun | Royal International |  | kbanoop@royalintl.in
Kyndryl BAU Team | Prajay | Storage
| Anil | AIX
| Mansoor | Virtualization
| Praveen | Linux SME
| Ramesh | Windows SME | 9600123777 | ramesh.gopal@kyndryl.com
OEM / Vendors |  | IBM (Power / FlashSystem / SVC / SAN)
Hitachi Vantara (VSP / HNAS / OneBlock)
Dell (Servers / ECS / Data Domain)
Management Team | Deepak Kotnala | Canara Bank | 9920181055 | deepak@canarabank.com
| Anandmani | Canara Bank
| Deepak Khurana | Kyndryl | 9811881097 | Deepak.Khurana1@kyndryl.com
| Shweta Sharma | Kyndryl | 9910225999 | Shweta.Sharma@kyndryl.com

## Roster (hidden)
Event Roster
Plan shifts per batch: Batch 1 day (23/10), Batch 2 night & day (23–25/10), Batch 3 (24/10). Include standby resources.
Resource Name | Domain | Email Id | Phone Number | Batch | Shift Date | Shift timings | Shift End date | Shift End Timings | Work location (ITI / STT / Remote)

## Stakeholder List (hidden)
Stakeholder List
Name | Email Id | Mobile Number | Role | Organisation | Prefer Call? | Prefer TXT? | Email Only?

## Escalation Detail (hidden)
Escalation Process & Contacts
If a task is unlikely to finish at the scheduled time, or may impact other cutover activities, the Task Owner must immediately report it to the Migration Lead / PMO Lead, who raises it on the Command Centre bridge.
For issues requiring escalation, the Migration Lead / PMO Lead contacts the appropriate management representative(s) and technical leader(s) on the bridge and initiates a teleconference for resolution.
Escalation levels: L1 Task owner (15 min) → L2 Migration Lead / Event PM (30 min) → L3 Management / OEM escalation (60 min).
Project Management Team
Name | Location during Cutover | Mobile Number | Role | Organisation | Escalation Level
Swarup | ITI / STT | 9986021228 | Wave PM | Kyndryl
Prasenjit Pal / Sudipta Goswamy |  | 9980155667 | Migration / Wave Architect | Kyndryl
Management / Leadership Team (Canara Bank & Kyndryl)
Name | Location during Cutover | Mobile Number | Role | Organisation | Escalation Level
Deepak Kotnala |  | 9920181055 |  | Canara Bank
Anandmani |  |  |  | Canara Bank
Deepak Khurana |  | 9811881097 |  | Kyndryl
Shweta Sharma |  | 9910225999 |  | Kyndryl
Kyndryl BAU Team
Name | Location during Cutover | Mobile Number | Role | Organisation | Escalation Level
Prajay |  |  | Storage | Kyndryl
Anil |  |  | AIX | Kyndryl
Mansoor |  |  | Virtualization | Kyndryl
Logistics & Facility
Name | Location during Cutover | Mobile Number | Role | Organisation | Escalation Level
Arvind | ITI / STT | 9022312399 | Royal International | Royal International
Nidhil & Annamalai | STT |  | STT Facility | STT
Vendor Support
Name | Location during Cutover | Mobile Number | Role | Organisation | Escalation Level
|  |  | IBM – Power / Storage / SAN | IBM
|  |  | Hitachi Vantara – VSP / HNAS / OneBlock | Hitachi Vantara
|  |  | Dell – Servers / ECS / Data Domain | Dell

## Command Centre Comms (hidden)
Command Centre Communications
A Command Centre is set up to (1) monitor and communicate progress of the cutover activities; (2) enable escalation and resolution of issues encountered during the cutover. All communications are managed by the Migration PM and Client PM.
Communication Method | Purpose | Description | Key Participants / Leads | Audience | Details
Meeting room (physical presence preferred) or Command Centre bridge | Checkpoint meetings, GO/NO-GO, call-in for updates | Scheduled checkpoints are listed below (linked to the Cutover sheet). People not at ITI / STT dial in to the bridge. Invitations sent before cutover. | Migration Manager, PMO Lead, Project Directors (Kyndryl & Client), Technical Director (Client), Application Leads | All names in Migration Squad / Stakeholder List | Bridge: ____
Email | Status of key tasks; checkpoint summaries; dashboard | Email sent at every notification point in the runbook (Checkpoint / Notification column) and after each checkpoint. | Migration Manager, PMO Lead, Client Applications Head | All names in Stakeholder List
Group chat (Teams / WhatsApp) | Real-time truck and task updates | Truck departures / arrivals (Truck_Tracker) and task closures posted in real time. | Event PM, Royal, STT | Event core team
Checkpoint & notification schedule (live from Cutover)
Task ID | Checkpoint / Notification | Planned Time | Batch | Status | Owner
P-05 | Checkpoint | 2026-10-24 | Pre-Event | Open | Kyndryl Migration / Bank
B1-01 | Bridge open | 2026-10-24 03:00 | 1 | Open | Kyndryl Migration / Bank
B1-02 | GO/NO-GO | 2026-10-24 03:15 | 1 | Open | Kyndryl Migration / Bank
B1-19 | Notify: Batch 1 down | 2026-10-24 07:30 | 1 | Open | Kyndryl Migration / Bank
B1-20 | Handover to Royal | 2026-10-24 06:00 | 1 | Open | Royal International / Bank / Kyndryl
B1-58 | Notify: Batch 1 complete | 2026-10-26 06:50 | 1 | Open | Migration / BAU / Bank
B2-01 | Bridge open | 2026-10-24 17:00 | 2 | Open | Kyndryl Migration / Bank
B2-02 | GO/NO-GO | 2026-10-24 17:30 | 2 | Open | Kyndryl Migration / Bank
B2-47 | Notify: Batch 2 down | 2026-10-25 00:30 | 2 | Open | Kyndryl Migration / Bank
B2-48 | Handover to Royal | 2026-10-25 00:30 | 2 | Open | Royal International / Bank / Kyndryl
B2-122 | Checkpoint: fabrics merged | 2026-10-26 05:45 | 2 | Open | SAN / IBM
B2-167 | Notify: Batch 2 complete | 2026-10-27 20:45 | 2 | Open | Migration / BAU / Bank
B3-09 | Notify: Batch 3 down | 2026-10-25 | 3 | Open | Kyndryl Migration / Bank
B3-10 | Handover to Royal | 2026-10-25 09:30 | 3 | Open | Royal International / Bank / Kyndryl
B3-50 | Notify: Batch 3 complete | 2026-10-26 10:45 | 3 | Open | Migration / BAU / Bank

## Runbook Calls_SS (hidden)
Runbook Walkthrough Calls – per Application Group & Batch
Date | Session | Batch | App Owner Group | Applications | Bank SPOC | Kyndryl Migration | Kyndryl PM | Kyndryl NW | Application Team – Bank | OEM | OEM Contact | Status | Minutes / Remarks
| Batch 1 – runbook walkthrough | 1 | Data Center Operations Section (ITI) | CBS Allied Application, SFMS, DCO, NDR HMC, Database Server - NDC - ASBA n Dpsecure | Rajeev ¦ rajeevkumar.j@canarabank.com | [6 empty] | Planned
| Batch 1 – runbook walkthrough | 1 | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | [6 empty] | Planned
| Batch 1 – runbook walkthrough | 1 | IT Assets Management Section | RAP Remote | Subash Kumar M ¦ 8754185345 ¦ hoditnwc@canarabank.com | [6 empty] | Planned
| Batch 1 – runbook walkthrough | 1 | SPMS | ASBA | Anand R K ¦ 9995571461 ¦ anandrk@canarabank.com | [6 empty] | Planned
| Batch 1 – runbook walkthrough | 1 | Service Unit Section | SFMS | [7 empty] | Planned
| Batch 1 – runbook walkthrough | 1 | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | [6 empty] | Planned
| Batch 1 – runbook walkthrough | 1 | To Be Confirmed | [8 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Data Center Operations Section (ITI) | CBS Allied Application, SFMS, DCO, HMC (NA), NCBS RAC, Middleware Hyper V Cluster | Rajeev ¦ rajeevkumar.j@canarabank.com, DCO/DCA ¦ hoddcitm@canarabank.com,dcsystem@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | CBS(UTKARSH) | CBS(UTKARSH) | Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com, VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | EWIRM Section | IRMS | Ashish Upadhyay ¦ 9457323390 ¦ ashishu@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Online Banking Technology Net banking Section | OFFLINE OTP, OBDX, GIFTCITY OBDX, OBT NET Banking Section - Report Server, PKI, OBT NET Banking Server - Jenkins Server | VIVEK ¦ 919786261374 ¦ vivek.r@canarabank.com, RAGHURAM ¦ 919136192161 ¦ RAGHURAMP@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Digital Lending and LAPS Section | LAPS, CORPORATE LOAN MODULE, GST SAHAY | PRITAM NATH ¦ ditlaps@canarabank.com,hodbsdl@canarabank.com,pritamnath@canarabank.com,rajat3@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | SPMS | SPMS, Queue Management System, Portal, CRM, DOCUMENT MANAGEMENT SYSTEM | Sudheer Kumar K ¦ 7095444823 ¦ sudheerkumar.k@canarabank.com, Saket/Ananda Dharshinee | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Government Business and Financial Inclusion Section | SFMS, Aadhaar seeding through web, CEDGE, DC Aadhar Vault DB, DB, DB server | arundhatikatolkar@canarabank.com, LEEMA ROSELIN K 9741644668 | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | FCUBS | FCUBS | PREETH HARI ¦ NAGENDRA SHIVA KUMAR ¦ 8848709042 ¦ 7396581281 ¦ preethhari@canarabank.com ¦ nagendra.siva@canarabank.com, Sunil ¦ 9900139448 ¦ sunilr.kashikar@kyndryl.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | HRMS Technical Section | PeopleSoft HRMS | Sandeep Kumar patel ¦ 6363951135 ¦ hotohrms@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | To Be Confirmed | [8 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Canara Collection and Payment Services Section | CCPS-Canara Collections and Payments system | Rajesh A, Kengal Veerendra Patil ¦ 7810073373 / 9880283138 ¦ hoccmssection@canarabank.com ¦ hoccpstech@canarabank.com, Rajesh A, Kengal Veerendra Patil ¦ 7810073373/9880283138 ¦ hoccmssection@canarabank.com/hoccpstech@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Software Project Management Section |  | Saket/Gaurav Baberwal, THIRU/RANI/SRAVYA ¦ 9944279850/9442002210/8125003095 ¦ m.thirunavukkarasu@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Online Banking Technology Mobile Banking | MOBILE BANKING, UPI, MB, IMPS | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com, NAGASHREE M. ¦ 9640479308 ¦ hotoupi@canarabank.com ¦ nagashreem@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | IIB(DCA) | IIB/ACE/ESB | VENKAT ¦ 9343171468 ¦ VENKATARAO.SOLA@KYNDRYL.COM | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | ATM Section | ATM | Santhosh & Prathap / Yogesh Dewan ¦ 8825960842, 9444177925 / 9972244755 ¦ hoatm@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Service Unit Section | RTGS, SFMS | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com, DEBJOY ROY ¦ 9874753518 ¦ AAQ_CanaraBank_NEFT_RTGS.xlsx | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | API Banking Section | APG (Google API Gatway) | Ghulam Rabbani Khan ¦ 8317035139 ¦ ghulamrabbanikhan@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Fintech Engagement & Partnership Section | Canara Digital Rupee Application, Canara Digital Rupee Merchant Application, PM Vidyalaxmi Digital Rupee Application | Sreejith V P/Arti ¦ 917907131653/918910141355 ¦ cbdcsupport@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | FCR Deposits Section | RAC DB, CKYC | ALOK GOSWAMI,Harikrishnan B Nair ¦ 6263967295, 9400946854 ¦ alok@canarabank.com, harikrishnanbnair@canarabank.comn , hotockyc@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Network Administration Section | NCCM | Jentiha ¦ 8056910971 ¦ jenithaj@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Data Warehouse Section | Data Warehouse | [7 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Government Business Module (GBM) IT Hub -New delhI | PM-Vidyalaxmi | DBA Team | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Online Banking Technology UPI and INFRA Section | UPI DB | [7 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Compliance Department section | Compliance Kartavya | Manish Naharia ¦ 8892248430 ¦ manishanaharia@canarabank.com, hocompliancedept@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Compliance Department | Compliance Kartavya | [7 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | DPSecure | Dpsecure | Vasanthan Naikar ¦ 9987513941 ¦ cb15076@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Online Banking Technology Mobile Banking,Digital Banking Wing | UPI | KIRAN ¦ 8892832954 ¦ kirankumard@kyndryl.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Application Development Section (In House) (ADM) | ADM | Debarun, Yogesh ¦ 9398989380 ¦ yogeshsai@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | TM Section Integrated Treasury Wing | Swift | DEBJOY ROY ¦ 9874753518 ¦ hopsg@canarabank.com, debjoyroy@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | FCC Section | FSCM | Manoj Kumar T ¦ 9300331307 ¦ manojkumart@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | CTS | DEM | Shakti Narayan Gupta,Bhupesh Piplani,7975142177/9650976622,hoditcts@canarabank.com | [6 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | Online Banking Technology Mobile Banking Section | [8 empty] | Planned
| Batch 2 – runbook walkthrough | 2 | New Initiatives-Technology Innovation Section | [8 empty] | Planned
| Batch 3 – runbook walkthrough | 3 | Data Center Operations Section (ITI) | DCO | [7 empty] | Planned
| Batch 3 – runbook walkthrough | 3 | Data Warehouse Section | Data Warehouse | [7 empty] | Planned
| Batch 3 – runbook walkthrough | 3 | Service Unit Section | [8 empty] | Planned
| Batch 3 – runbook walkthrough | 3 | TM Section Integrated Treasury Wing | Swift | Gambhirya Lokhande ¦ 7558713822 ¦ gambhiryatejrao@canarabank.com | [6 empty] | Planned
| Batch 3 – runbook walkthrough | 3 | Online Banking Technology Net banking Section | WEB-OTP | [7 empty] | Planned

## Change Records (hidden)
Change Records
Sr # | Change record | Date | Batch | Description | Servers / Scope | Status
1 |  | 2026-10-23 | 1 | CBS Batch 1 – UAT fabric, BLR512B-G7-SW2, NDC and CBS tape movement | Scope sheet, Movement Batch = 1 | To be raised
2 |  | 2026-10-23 | 2 | CBS Batch 2 – merged SAN batch (production CBS SAN island) | Scope sheet, Movement Batch = 2 | To be raised
3 |  | 2026-10-23 | 3 | CBS Batch 3 – standalone servers, object storage, network and security | Scope sheet, Movement Batch = 3 | To be raised

## Action log (hidden)
Action Log
S No | Action Items | Owner | Target Date | Status | Comments
1 | Confirm truck capacity rule (45 boxes; 1 box = 1×2U or 2×1U) and 23-truck plan with Royal International | Kyndryl Migration / Royal |  | Open
2 | Confirm target positions for loose devices flagged CHECK / RISK in Target_Rack_Readiness | Migration / STT / Bank |  | Open
3 | Decision on DC-K6-N9K-TOR-SW1 (FDO24130M76) | Network / Bank |  | Open
4 | Add rack D4 devices (HPE StoreOnce CZJ74809QV, SGH107HS01; MSL6480 DEC75100ZG) to the inventory or confirm out of scope | Storage / Bank |  | Open
5 | Confirm Data Domain (W6) and DCDLRACSTORAGE serials against SAN-MAP | Storage / Bank |  | Open
6 | Confirm scrap / OOS devices to be moved | Bank |  | Open
7 | Collect zoning (cfgshow) and host-to-volume exports, if obtainable, to validate SAN dependencies | SAN / Storage |  | Open
8 | Fill Roster, Stakeholder List and vendor escalation contacts | Event PM |  | Open

## Issue Log (hidden)
Issue Log
ID | Client Facing (Y/N) | Date | Raised by | Phase / Tower / Area | Batch | Task ID | Issue Summary | Priority (L/M/H) | Action | Owner | Target Resolution Date | Action Status | Issue Status | Date Closed | Remarks | Related Risk
I-01
I-02
I-03
I-04
I-05
I-06
I-07
I-08
I-09
I-10
I-11
I-12
I-13
I-14
I-15
I-16
I-17
I-18
I-19
I-20

## Risk Log (hidden)
Risk Log
ID | Client Facing (Y/N) | Date Added | Raised By | Risk Description | Risk Category / Phase | Parent Risk ID | Impact Description | Probability | Impact | Risk Rating | Risk Mitigation / Actions | Owner | Target Resolution Date | Action Status | Risk Status | Date Resolved | Risk Trigger(s) | Contingency Plan / Actions | Remarks | Related Issue No
R-01 | Y | 2026-10-17 | Kyndryl Migration | Single-fabric CBS production: CBS production runs on Fabric A only (BLR512B-G7-SW1) from removal of BLR512B-G7-SW2 in Batch 1 (24/10 06:00) until Batch 2 is up at target. | Batch 1 |  | Loss of Fabric A path = CBS outage | Medium | High | 6 | Multipath health check on all CBS hosts before removal (B1-04); keep a Fabric-B fallback decision point. | SAN / AIX BAU |  | Open | Open |  | Any host with a single active path | Defer BLR512B-G7-SW2 removal to Batch 2
R-02 | Y | 2026-10-17 | Kyndryl Migration | P10 frame 78A1DE8 (Core DB-2, rack C3) moves in Batch 1: its LPAR(s) depend on BLR512B-G7-SW2 (B1) and BLR512B-G7-SW1 (B2) – only one fabric available at target until Batch 2; Core DB-2 copy unavailable during Batch 1–2. | Batch 1 |  | Core DB-2 on one fabric at target until Batch 2; path loss = DB-2 outage | High | Medium | 6 | Bank acceptance; confirm DB-2 role (standby) and that DB-1 (78A1DC8) carries production; validate single-path boot before power-on. | Network / Bank |  | Open | Open |  | Re-patch not completed | Keep switch at source until Batch 2
R-03 | Y | 2026-10-17 | Kyndryl Migration | Rackmap vs Scope mismatch: racks K5 and F7 are marked 'Loaded in OEM rack' in Scope but are not 'Lift & Shift' in rackmap; their devices target G-08/H-08 and F-15 (positions of K4/K3/A4). | Batch 2 |  | Rack/position conflict at STT; re-planning on event day | High | Low | 3 | Confirm with Bank/STT whether K5 and F7 travel loaded (and where they stand) or devices are unracked; update Transport Mode accordingly. | Migration / STT |  | Open | Open |  | No temporary position available | Keep devices powered off until racks arrive
R-04 | Y | 2026-10-17 | Kyndryl Migration | DC→NDC replication gap: Replication paused from Batch 1 (NDC switches move) until Batch 2 BLRDCREP switches are up at target. | Batch 1 / 2 |  | RPO exposure for NDC copy | High | Medium | 6 | Bank acceptance; inter-site DWDM/FCIP link verified at target before Batch 2. | Storage / Bank |  | Open | Open |  | Link not ready | Extend replication gap with Bank approval
R-05 | Y | 2026-10-17 | Kyndryl Migration | Target rack positions to confirm: 24 loose rows have TBD / N/W / Spare / Scrap targets or need a rack shift at STT (Target_Rack_Readiness). | All |  | Devices cannot be racked on arrival | High | High | 9 | Confirm every position with STT/Bank before GO/NO-GO. | Migration / STT |  | Open | Open |  | Open CHECK rows at GO/NO-GO | Stage devices in store room
R-06 | Y | 2026-10-17 | Kyndryl Migration | Storage endpoints missing / mismatched: Data Domain (W6) serials, HPE StoreOnce D5/D4 (rack D4 not in inventory) and DCDLRACSTORAGE serial differ from SAN-MAP / PPT. | Batch 2 |  | Backup target not moved / not validated | Medium | Medium | 4 | Reconcile with Storage team; add rack D4 to inventory if in scope. | Storage / Bank |  | Open | Open |  | Unresolved at GO/NO-GO | Move as a separate controlled batch
R-07 | Y | 2026-10-17 | Kyndryl Migration | Tight shutdown window: 198 LPARs and 155 VMs planned to be down within 22:00–23:00 (DR runbook took 120 min for 66 LPARs and 180 min for frame power-down). | Batch 2 |  | Storage / SAN shutdown delayed; cascade to trucks | High | Medium | 6 | Parallel teams per frame / cluster; pre-staged scripts; start app stop earlier if Bank allows. | AIX BAU / Virtualization |  | Open | Open |  | Shutdown overrun > 30 min | Re-baseline truck slots
R-08 | Y | 2026-10-17 | Kyndryl Migration | Truck capacity assumption: 45 boxes per truck (1 box = 1×2U or 2×1U device; >2U = ⌈U/2⌉ boxes); empty rack 11.25 and OEM-loaded rack 22.5 box-equivalents (23 trucks, 30-min sequential departures per batch). | All |  | Truck count / timing wrong | Medium | High | 6 | Confirm box size, rack equivalents and loading order with Royal; load trucks in parallel where docks allow. | Royal / Migration |  | Open | Open |  | Royal confirms different capacity | Re-run truck plan
R-09 | Y | 2026-10-17 | Kyndryl Migration | Network core moves last: Batch 3 carries core / DMZ / firewalls; shutdown at 23:45 removes management access at source; arrives at target from 24/10 13:30. | Batch 3 |  | Target connectivity for Batches 1–2 depends on target core readiness | Medium | High | 6 | Confirm target core network independently serves Batches 1–2 (P-03, GO/NO-GO). | Network / Bank |  | Open | Open |  | Target core not ready | Move core network earlier
R-10 | Y | 2026-10-17 | Kyndryl Migration | Single-fabric devices: D2SXMZ3, 3QGL6C2, 7PRRDV2, 7V1N0V3 show one fabric only in SAN-MAP. | Batch 2 |  | No path redundancy at target | Medium | Medium | 4 | Confirm second HBA before shutdown. | SAN / Server Teams |  | Open | Open |  | Second HBA not found | Accept single path / remediate
R-11 | Y | 2026-10-17 | Kyndryl Migration | Devices not in inventory inside moving racks: W2W shows in-scope devices inside moving racks that are not in the CBS inventory (e.g. 8 in D5). | All |  | Unplanned devices travel / not validated | Medium | Medium | 4 | Confirm ownership and add to scope or remove before move. | Migration / Bank |  | Open | Open |  | Unlisted device found | Hold rack until resolved
R-12 | Y | 2026-10-17 | Kyndryl Migration | Scrap / OOS devices moving: 3131AG435894, 847C10W, 84B6FAW, 12DGGQ00100002 are flagged Scrap / OOS but included on dependency basis. | Batch 2 / 3 |  | Unnecessary effort / space | Low | Low | 1 | Bank confirmation before loading. | Bank |  | Open | Open |  | Bank declines move | Leave at source
R-13 | Y | 2026-10-17 | Kyndryl Migration | Fabric merge at target: Batch 2 directors re-join Batch 1 switches at target; config changes in between can segment the fabric. | Batch 2 |  | Hosts lose paths / storage | Low | High | 3 | Zoning freeze from P-02 until all directors re-joined; config backups. | SAN / IBM |  | Open | Open |  | Segmented ISL | Restore configs from backup
R-14 | Y | 2026-10-17 | Kyndryl Migration | No zoning / host-to-volume data: Batching uses cabling (SAN-MAP) and PPT only; zoning exports not available. | Batch 2 |  | Hidden cross-batch storage dependency | Low | Medium | 2 | Merged Batch 2 contains all SAN-connected production; collect exports if possible. | SAN / Storage |  | Open | Open |  | Host cannot see disks | Investigate zoning on bridge
R-15 | Y | 2026-10-17 | Kyndryl Migration | Devices OFF at source: Devices powered off at source (W2W OFF) must stay off at target (Wave 2 lesson). | All |  | Unexpected services / IP conflicts | Low | Medium | 2 | Scope sheet highlights W2W OFF; do not power on at target. | Migration / BAU |  | Open | Open |  | Device powered on at target | Power off and report
R-16 | Y | 2026-10-17 | Kyndryl Migration | Batch 3 idle downtime: Batch 3 devices shut down 23/10 22:00 but handed over 24/10 09:30 (trucks follow Batch 2). | Batch 3 |  | Longer outage for standalone services | High | Low | 3 | Shift Batch 3 shutdown later if Bank allows; or load in parallel with Batch 2. | Event PM / Bank |  | Open | Open |  | Bank requires shorter outage | Re-plan Batch 3 window

## Lessons Learnt (hidden)
Lessons Learnt (carried forward)
S.No. | Short Description | Identified in Phase | Actions Needed | Action owner | Recommendation | Source Event
1 | Resource management – team worked 24/7 for consecutive days | Migration | Plan resources in shifts / increase resource count |  |  | DR migration
2 | Juniper switch compatibility issue tested only at migration | Migration | Complete all compatibility checks before the event |  |  | DR migration
3 | Cabling assessments | Migration | Reassess cabling requirements; more focus on cabling plan |  |  | DR migration
4 | Application confirmation delay | Migration | Applications to confirm within the agreed timelines |  |  | DR migration
5 | Application owner availability | Migration | Ensure availability of application owners during the event |  |  | DR migration
6 | Servers not coming into network / cable connectivity issues after lift & shift | Migration | Port-map validation and cable labelling before power-on (P-01, cabling tasks) |  |  | Wave 2 lift & shift
7 | Not-in-use servers powered off at source were powered on at target | Migration | Keep W2W OFF devices powered off at target (Scope highlight) |  |  | Wave 2 lift & shift
8 | NGSOC cable connection issues | Migration | Pre-validate NGSOC / security cabling at target |  |  | Wave 2 lift & shift

## Assumptions (hidden)
Assumptions & Basis of Plan
Item | Assumption / Basis
Locations | Source ITI, target STT and 2-hour travel as used in the Bubble runbook (v2.2).
Batches, trucks, times | Movement Batch per Scope (V2) with changes of 19/10: rack C3 incl. P10 frame 78A1DE8 → Batch 1; UAT switch 787413W/787414D and all connected devices → Batch 2. Trucks re-planned.
Virtual devices | Each LPAR / Hyper-V VM inherits batch, truck and times of its physical host; 364 virtual rows incl. new VM DCHRMAPP1 (host DCHVCLSTRN07).
Task durations | Customer dates/times entered in Cutover (V2) retained as anchors: Batch 1 from 24/10 03:00, Batch 2/3 from 24/10 21:00–22:00. Scope dates/times now link live to the Cutover sheet.
Live schedule | Only anchor tasks (bold blue) carry fixed dates/times; all others = latest end of their Dependencies. HIGH-LEVEL, Truck_Tracker, Command Centre and Shutdown_Startup_Seq times are linked to the Cutover sheet.
T-1 tasks | Pre-event tasks scheduled 22/10/2026 as placeholders – adjust to the agreed date.
Teams | Team names follow the Bubble / DR runbooks; individual resource names to be filled in Allocated Resource, Roster and Escalation Detail.
Database shutdown flag | Shutdown_Startup_Seq marks "DB Team" where hostname or Device Role contains "DB"; confirm with application teams.
Truck Ft | Truck size (ft) not available in source data – to be confirmed by Royal International.
Overall duration | With 30-minute sequential truck departures the plan completes Batch 2 target validation on 25/10/2026 early morning (see Wave Dashboard). Parallel loading would shorten it.
Rack movement | Racks move only when 'Lift & Shift' in rackmap (Racks for CBS). Loaded = Transport Mode 'Loaded in OEM rack X' (IBM racks); all other Lift & Shift racks travel empty after their devices are unracked.
Truck capacity | 45 boxes per truck; 1 box = 1 × 2U device or 2 × 1U devices; devices > 2U use ⌈U/2⌉ boxes (e.g. 14U SAN director = 7 boxes); unknown/0U items = 0.5 box. Empty rack = 11.25 and OEM-loaded rack = 22.5 box-equivalents (to be confirmed by Royal). Batch 1 order: SAN Director → P10 frame rack C3 → tape (rack D5 + tape drives, L1/L2/L3) → NDC racks/devices in consecutive trucks (no back-filling). Batches 2–3: empty racks → loaded racks → SAN → storage → servers → network (first-fit).